GAVI Alliance

Application Form for Country Proposals

For Support to New and Under-Used Vaccines (NVS)

Submitted by

The Government of

Timor-Leste (East Timor)

Date of submission: 26.05.2011 19:53:40

Deadline for submission: 1 Jun 2011

Select Start and End Year of your Comprehensive Multi-Year Plan (cMYP)

| Start Year | 2011 | End Year | 2015 |
| --- | --- | --- | --- |

Revised in January 2011

(To be used with Guidelines of December 2010)

Please submit the Proposal using the online platform https://AppsPortal.gavialliance.org/PDExtranet.

Enquiries to: proposals@gavialliance.org or representatives of a GAVI partner agency. The documents can be shared with GAVI partners, collaborators and general public. The Proposal and attachments must be submitted in English, French, Spanish, or Russian.

Note: Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline.

The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents will be shared with the GAVI Alliance partners and the general public.

GAVI ALLIANCE GRANT TERMS AND CONDITIONS FUNDING USED SOLELY FOR APPROVED PROGRAMMES The applicant country (“Country”) confirms that all funding provided by the GAVI Alliance will be used and applied for the sole purpose of fulfilling the programme(s) described in the Country’s application. Any significant change from the approved programme(s) must be reviewed and approved in advance by the GAVI Alliance. All funding decisions for the application are made at the discretion of the GAVI Alliance Board and are subject to IRC processes and the availability of funds. AMENDMENT TO THE APPLICATION The Country will notify the GAVI Alliance in its Annual Progress Report if it wishes to propose any change to the programme(s) description in its application. The GAVI Alliance will document any change approved by the GAVI Alliance, and the Country’s application will be amended. RETURN OF FUNDS The Country agrees to reimburse to the GAVI Alliance all funding amounts that are not used for the programme(s) described in its application. The country’s reimbursement must be in US dollars and be provided, unless otherwise decided by the GAVI Alliance, within sixty (60) days after the Country receives the GAVI Alliance’s request for a reimbursement and be paid to the account or accounts as directed by the GAVI Alliance. SUSPENSION/ TERMINATION The GAVI Alliance may suspend all or part of its funding to the Country if it has reason to suspect that funds have been used for purpose other than for the programmes described in the Country’s application, or any GAVI Alliance-approved amendment to the application. The GAVI Alliance retains the right to terminate its support to the Country for the programmes described in its application if a misuse of GAVI Alliance funds is confirmed. ANTICORRUPTION The Country confirms that funds provided by the GAVI Alliance shall not be offered by the Country to any third person, nor will the Country seek in connection with its application any gift, payment or benefit directly or indirectly that could be construed as an illegal or corrupt practice. AUDITS AND RECORDS The Country will conduct annual financial audits, and share these with the GAVI Alliance, as requested. The GAVI Alliance reserves the right, on its own or through an agent, to perform audits or other financial management assessment to ensure the accountability of funds disbursed to the Country. The Country will maintain accurate accounting records documenting how GAVI Alliance funds are used. The Country will maintain its accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of GAVI Alliance funds. If there is any claims of misuse of funds, Country will maintain such records until the audit findings are final. The Country agrees not to assert any documentary privilege against the GAVI Alliance in connection with any audit. CONFIRMATION OF LEGAL VALIDITY The Country and the signatories for the Country confirm that its application, and Annual Progress Report, are accurate and correct and form legally binding obligations on the Country, under the Country’s law, to perform the programmes described in its application, as amended, if applicable, in the APR. CONFIRMATION OF COMPLIANCE WITH THE GAVI ALLIANCE TRANSPARANCY AND ACCOUNTABILITY POLICY The Country confirms that it is familiar with the GAVI Alliance Transparency and Accountability Policy (TAP) and complies with the requirements therein. USE OF COMMERCIAL BANK ACCOUNTS The Country is responsible for undertaking the necessary due diligence on all commercial banks used to manage GAVI cash-based support. The Country confirms that it will take all responsibility for replenishing GAVI cash support lost due to bank insolvency, fraud or any other unforeseen event. ARBITRATION Any dispute between the Country and the GAVI Alliance arising out of or relating to its application that is not settled amicably within a reasonable period of time, will be submitted to arbitration at the request of either the GAVI Alliance or the Country. The arbitration will be conducted in accordance with the then-current UNCITRAL Arbitration Rules. The parties agree to be bound by the arbitration award, as the final adjudication of any such dispute. The place of arbitration will be Geneva, Switzerland. The language of the arbitration will be English. For any dispute for which the amount at issue is US$ 100,000 or less, there will be one arbitrator appointed by the GAVI Alliance. For any dispute for which the amount at issue is greater than US $100,000 there will be three arbitrators appointed as follows: The GAVI Alliance and the Country will each appoint one arbitrator, and the two arbitrators so appointed will jointly appoint a third arbitrator who shall be the chairperson. The GAVI Alliance will not be liable to the country for any claim or loss relating to the programmes described in the application, including without limitation, any financial loss, reliance claims, any harm to property, or personal injury or death. Country is solely responsible for all aspects of managing and implementing the programmes described in its application.

# Application Specification

Please specify for which type of GAVI support you would like to apply to.

Important note: To enable proper functioning of the form, please first select the cMYP years on the previous page.

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Type of Support | Vaccine | Start Year | End Year | Preferred second presentation[1] | Action |
| --- | --- | --- | --- | --- | --- |
| New Vaccines Support | DTP-HepB-Hib, 10 doses/vial, Liquid | 2012 | 2015 |  |  |

[1] This "Preferred second presentation" will be used in case there is no supply available for the preferred presentation of the selected vaccine ("Vaccine" column). If left blank, it will be assumed that the country will prefer waiting until the selected vaccine becomes available.

# Table of Contents

Sections

Main

Cover Page

GAVI Alliance Grants Terms and Conditions

1. Application Specification

2. Table of Contents

3. Executive Summary

4. Signatures

4.1. Signatures of the Government and National Coordinating Bodies

4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation

4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation

4.1.3. The Inter-Agency Coordinating Committee for Immunisation

4.2. National Immunization Technical Advisory Group for Immunisation

4.2.1. The NITAG Group for Immunisation

5. Immunisation Programme Data

5.1. Basic facts

5.2. Current vaccination schedule

5.3. Trends of immunisation coverage and disease burden

5.4. Baseline and Annual Targets

Table 1: baseline figures

5.5. Summary of current and future immunisation budget

5.6. Summary of current and future financing and sources of funds

6. NVS

6.1. Capacity and cost (for positive storage)

6.2. Assessment of burden of relevant diseases (if available)

6.3.1. Requested vaccine ( DTP-HepB-Hib, 10 doses/vial, Liquid )

6.3.2. Co-financing information

6.3.3. Wastage factor

6.3.4. Specifications of vaccinations with new vaccine

6.3.5. Portion of supply to be procured by the country (and cost estimate, US$)

6.3.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

6.3.7. New and Under-Used Vaccine Introduction Grant

7. Procurement and Management of New and Under-Used Vaccines

7.1. Vaccine management (EVSM/EVM/VMA)

8. Additional Comments and Recommendations

9. Annexes

Annex 1

Annex 1.1 - DTP-HepB-Hib, 10 doses/vial, Liquid

Table 1.1  A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

Table 1.1  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

Table 1.1  C - Summary table for vaccine DTP-HepB-Hib, 10 doses/vial, Liquid

Table 1.1  D - Estimated number of doses for vaccine DTP-HepB-Hib, 10 doses/vial, Liquid associated injection safety material and related co-financing budget

Annex 2

10. Attachments

10.1 Documents required for NVS support

10.2 Attachments

Banking Form

# Executive Summary

1. Country Background

Timor Leste (population 1.06 million) was declared a new sovereign state in 2002. Since this period, the predominantly rural country has commenced to re develop its human resource capacity and institutions. The population is very young, with approximately half under the age of 15. The country is divided into 13 Districts, 65 sub Districts and 442 villages (sucos). 

2. Proposal Request

This proposal request is for GAVI funded support for the introduction of Pentavalent vaccine from January 2012. The duration of requested support is for the length of the current multiyear plan for immunization 2012 - 2015. The vaccine requested is pentavalent vaccine (DPT-Hep B-Hib) 10 dose liquid vial. Support is also requested for funds for associated introduction costs.

2. Baseline Data

The most recent JRF indicates that DTP3 rates are 72% for DTP3 and 66% for measles for 2010. The most recent administratively reported coverage data in 2010 provides coverage rates of 66% for DTP3 and 68% for measles. Overall coverage has improved in recent years. Between the last two DHS surveys in 2003 and 2009/10, DPT3 coverage improved by 15% and measles coverage by 28%. The main constraints to coverage are lack of accessibility to services due to geographic terrain and limitations in human resources numbers and capacity. Measles and neo natal tetanus cases have been reported consistently over the last two years, highlighting the need for Timor Leste to implement micro-planning and management strategies for improving access. In the next cMYP period, it is proposed to increase coverage to greater than 80% DPT3 in all districts by 2015. There is reasonable equity of immunization coverage in Timor Leste. DHS data from 2010 demonstrates that for DPT3 coverage, the lowest economic qunitile has a DPT3 coverage rate of 55% and the highest quintile 72.5% (and similar differences in relation to education status).

3. Country preparedness

3.1 Health System Preparedness

The redevelopment of the health sector is one of the major priorities of the Government of Timor Leste. The first health sector plan was developed for the period 2008 - 2012, with three main goals of improving accessibility for quality health services, strengthening management and support systems and strengthening coordination, planning and monitoring. A second health strategic plan (for the period 2011 - 2030) is currently near finalization. There are currently 6 hospitals and 65 community health centres in Timor Leste. A Basic Service Package has been devised for implementation by health facilities across the country, with immunization as one of the core components. Currently the national immunization program implements through community health centres and health posts and a community health strategy known as SISCa (refer to cMYP for details).

3.2 Program Preparedness

The current immunization schedule includes the standard seven routine EPI antigens, with the Government of Timor Leste financing the procurement of tetravalent vaccine which was introduced into the routine program in December 2007. 

The Ministry of Health with the technical support of WHO has recently established a Surveillance Unit at the Ministry of Health in 2011 with the initial focus of this unit being on strengthening systems for vaccine preventable surveillance including AEFI. The national EPI program through its implementing units at sub national level has systems in place for case based measles surveillance and AFP reporting. The Ministry of Health currently recognizes the need for strengthening of AEFI systems in particular. National Immunization Policy and middle level training programs are currently being revised and implemented that will have a major focus on introduction of AEFI and other surveillance concepts and processes. 

Cold Chain systems have been evaluated and updated over successive years since 2007. The vaccine cold chain system in Timor Leste extends from the Primary Central store in Dili to 13 District Stores to 65 CHCs. Since most facilities do not have 24 hr/day electricity, 75% of cold chain refrigeration equipment in the country is LP-Gas powered. In 2007, a consultant was engaged by UNICEF to develop a comprehensive cold chain inventory and a five-year cold chain rehabilitation plan (2008-2012). It was noted that some of the equipment was reaching its life-expectancy. As a consequence, over the period 2009-2010 UNICEF provided financial and technical assistance to purchase fifteen solar units and subsequently train district staff in the proper installation and maintenance of the new units. A comprehensive vaccine management assessment was conducted using the WHO/UNICEF Vaccine Management Assessment Tool in November 2007. At that time, the consultant found that cold chain capacity for DTP-HepB was adequate at primary and service delivery levels and the standard of equipment satisfactorily functional. A follow-up EVSM was conducted in 2009 and concluded that the primary vaccine store had more than sufficient capacity to accomodate all routine and campaign vaccines. The 2009 assessment further concluded that for routine EPI, none of the districts needed additional cold chain equipment. To best prepare for future new and underutilized vaccine introduction, efforts will continue on raising awareness and understanding among health staff -- particularly the newer work force expected over the next cMYP cycle – of vaccine temperature sensitivity, the importance of temperature monitoring and good vaccine handling, and proper record-keeping. As the transition from tetravalent to pentavalent vaccine will involve no significant shift in vaccine volume requirements, the current cold chain systems volumes are adequate for accommodating introduction of pentavalent vaccine (refer to cMYP for details).

In terms of introduction perparedness, important lessons learned from tetravalent introduction have included 4 main factors - these include (1) development of clear policy and guidelines on immunization (2) training of health staff (including vaccine management and AEFI) (3) improving coverage through RED micro-planning and (4) adequate dissemination of public information. These lessons learned have been taken up into the introduction plan which is annexed to this proposal. 

The nature of stakeholders participation in developing this proposal

In April 2010, at the Directors Meeting of the Ministry of Health represented by Directorate heads and development partners, the decision was undertaken to introduce Pentavalent vaccine in 2012. Subsequent meetings were undertaken with the National EPI Technical Working Group with the participation of the national program, WHO, UNICEF and NGOs to revise and update the multiyear plan and costing and to respond to critical issues in the development of this proposal to GAVI. The revised plan and costing and proposal were circulated to regional offices of WHO and UNICEF for additional inputs.

# Signatures

# Signatures of the Government and National Coordinating Bodies

# Government and the Inter-Agency Coordinating Committee for Immunisation

The Government of Timor-Leste (East Timor) would like to expand the existing partnership with the GAVI Alliance for the improvement of the infants routine immunisation programme of the country, and specifically hereby requests for GAVI support for DTP-HepB-Hib 10 doses/vial Liquid introduction.

The Government of Timor-Leste (East Timor) commits itself to developing national immunisation services on a sustainable basis in accordance with the Comprehensive Multi-Year Plan (cMYP) presented with this document. The Government requests that the GAVI Alliance and its partners contribute financial and technical assistance to support immunisation of children as outlined in this application.

Tables 6.(n).5. (where (n) depends on the vaccine) in the NVS section of this application shows the amount of support in either supply or cash that is required from the GAVI Alliance. Tables 6.(n).4. of this application shows the Government financial commitment for the procurement of this new vaccine (NVS support only).

Following the regulations of the internal budgeting and financing cycles the Government will annually release its portion of the co-financing funds in the month of January.

Please note that this application will not be reviewed or approved by the Independent Review Committee (IRC) without the signatures of both the Minister of Health & Minister of Finance or their delegated authority.

Enter the family name in capital letters.

| Minister of Health (or delegated authority) |  | Minister of Finance (or delegated authority) |  |
| --- | --- | --- | --- |
| Name | H.E Ms.Madalena F.M.H.C Soares, B.Ns, Vice-Minister of Health | Name | H.E Mr Rui Manuel Hanjam, Vice Minister, Ministry of Finance, RDTL |
| Date |  | Date |  |
| Signature |  | Signature |  |

This report has been compiled by

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Full name | Position | Telephone | Email | Action |
| --- | --- | --- | --- | --- |
| Mateus Cunha | National EPI Officer MOH | +670 7269219 | cunha_2001et@yahoo.com |  |

# National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation

We the members of the ICC, HSCC, or equivalent committee[1] met on the 03.05.2011 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

[1] Inter-agency Coordinating Committee or Health Sector Coordinating Committee, or equivalent committee which has the authority to endorse this application in the country in question.

The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: 4.

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Name/Title | Agency/Organisation | Signature | Action |
| --- | --- | --- | --- |
| Mrs.Isabel Maria GOMES | National Director of Community Health, Ministry of Health |  |  |
| Mr. Mateus CUNHA | National EPI Manager |  |  |
| Mr. Jose Antonio Oliveira LIMA | EPI Field Officer Ministry of Health |  |  |
| Dr.Erling LARSSON | Adviser of Health Policy WHO |  |  |
| Dr. Yuwono SIDHARTA | Epidemiologist WHO |  |  |
| Mr. Herminio LELAN | EPI Officer WHO |  |  |
| Dr Md Monjur HOSSAIN | Chief of Health and Nutrition UNICEF |  |  |
| Dr. Sherin VARKEY | Health Specialist UNICEF |  |  |
| Mr. Aderito Gregorio DO CARMO | Immunization Officer UNICEF |  |  |
| Ms Lauri WINTER | TAIS/USAID |  |  |
| Dr. Ruhul AMIN | Chief of Party MCC TPI (MCC/USAID) |  |  |

In case the GAVI Secretariat has queries on this submission, please contact

Enter the family name in capital letters.

| Name | Mateus Cunha | Title | EPI Officer |
| --- | --- | --- | --- |
| Tel no | +670 7269219 |  |  |
| Fax no | +670 3331176 | Address | Ministry of Health Dili Timor Leste |
| Email | cunha_2001et@yahoo.com |  |  |

# The Inter-Agency Coordinating Committee for Immunisation

Agencies and partners (including development partners and NGOs) supporting immunisation services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC, HSCC, or equivalent committee). The ICC, HSCC, or equivalent committee is responsible for coordinating and guiding the use of the GAVI NVS support. Please provide information about the ICC, HSCC, or equivalent committee in your country in the table below.

Profile of the ICC, HSCC, or equivalent committee

| Name of the committee | National EPI Technical Working Group |
| --- | --- |
| Year of constitution of the current committee | 2006 |
| Organisational structure (e.g., sub-committee, stand-alone) | Stand Alone Committee |
| Frequency of meetings | Once per quarter |

Composition

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Function | Title / Organisation | Name |  |
| --- | --- | --- | --- |
| Chair | National Director of Community Health, Ministry of Health | Mrs. Isabel Maria GOMES |  |
| Secretary | National EPI Manager Ministry of Health (Vice Chair) | Mr. Mateus CUNHA |  |
| Members | EPI Field Officer Ministry of Health (Secretary) | Mr. Jose Antonio Oliveira LIMA | Action |
|  | Adviser of Health Policy / WHO | Dr. Erling LARSSON |  |
|  | Epidemiologist /WHO | Dr. Yuwono SIDHARTA |  |
|  | EPI Officer WHO | Mr. Herminio LELAN |  |
|  | Chief of Health and Nutrition / UNICEF | Dr. Md. Monjur HOSSAIN |  |
|  | Health Specialist UNICEF | Dr Sherrin VARKEY |  |
|  | Immunization Officer UNICEF | Mr Aderito Gregorio DO CARMO |  |
|  | Country Director / TAIS - USAID | Ms. Lauri WINTER |  |
|  | Chief of Party MCC TPI MCC/USAID | Dr. Ruhul AMIN |  |

Major functions and responsibilities of the committee

1. To monitor immunization coverage and surveillance data and recommend improvements to immunization strategy. 2. To recommend to the Ministry of Health any changes to Immunization Policy 3. To provide technical recommendations to the Ministry of Health on new vaccine introductions 4. To oversee development of multi year planning and costing of national program 5. To coordinate resources both national and international for the financing of the national program 6. To coordinate resource mobilization and responses for immunization program 7. To report to the Ministry of Health on any other factors effecting the performance of the national EPI program

Three major strategies to enhance the committee's role and functions in the next 12 months

| 1. | Increase frequency of National EPI Technical Working Group to 6 times per year. |
| --- | --- |
| 2. | Every quarter, to request that one District Manager presents the situation of immunization services in that District |
| 3. | To request higher level MOH membership on the EPI TWG from time to time in order to link EPI policy issues closer to the health policy issues of the sector. |

# National Immunization Technical Advisory Group for Immunisation

(If it has been established in the country)

We the members of the NITAG met on the to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: .

In case the GAVI Secretariat has queries on this submission, please contact

Enter the family name in capital letters.

| Name |  | Title |  |
| --- | --- | --- | --- |
| Tel no |  |  |  |
| Fax no |  | Address |  |
| Email |  |  |  |

# The NITAG Group for Immunisation

Profile of the NITAG

| Name of the NITAG |  |
| --- | --- |
| Year of constitution of the current NITAG |  |
| Organisational structure (e.g., sub-committee, stand-alone) |  |
| Frequency of meetings |  |

Composition

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Function | Title / Organisation | Name |  |
| --- | --- | --- | --- |
| Chair |  |  |  |
| Secretary |  |  |  |
| Members |  |  | Action |

Major functions and responsibilities of the NITAG

Three major strategies to enhance the NITAG’s role and functions in the next 12 months

| 1. |  |
| --- | --- |
| 2. |  |
| 3. |  |

# Immunisation Programme Data

Please complete the tables below, using data from available sources. Please identify the source of the data, and the date. Where possible use the most recent data and attach the source document.

- Please refer to the Comprehensive Multi-Year Plan for Immunisation (cMYP) (or equivalent plan) and attach a complete copy (with an Executive Summary) as DOCUMENT NUMBER 5

- Please refer to the two most recent annual WHO/UNICEF Joint Reporting Forms (JRF) on Vaccine Preventable Diseases.

- Please refer to Health Sector Strategy documents, budgetary documents, and other reports, surveys etc, as appropriate.

# Basic facts

For the year 2010 (most recent; specify dates of data provided)

|  | Figure |  | Year | Source |
| --- | --- | --- | --- | --- |
| Total population | 1,066,582 |  | 2010 | Census 2010 with population Growth rate of 2.41% |
| Infant mortality rate (per 1000) | 45 |  | 2010 | DHS 2010 |
| Surviving Infants[1] | 45,253 |  | 2010 | Based on Live Births 47,385 from JRF and IMR of 45/1000 from 2010 DHS Survey |
| GNI per capita (US$) | 2,644 |  | 2010 | World Bank |
| Total Health Expenditure (THE) as a percentage of GDP | 12.30 | % | 2009 | NHA WHO Website 2010 |
| General government expenditure on health (GGHE) as % of General government expenditure | 9.80 | % | 2008 | NHA WHO Website 2010 |

[1] Surviving infants = Infants surviving the first 12 months of life

Please provide some additional information on the planning and budgeting context in your country; also indicate the name and date of the relevant planning document for health

There are three relevant documents for planning and budgeting in the country context. These are as follows:cMYP 2011 - 2015, Health Sector Plan 2007 - 2012 and Draft Health Sector Plan 2011 - 2030.Other important aspects of the national planning and budgeting cycle are as follows: District health teams under the Ministry’s direction implement health policy and strategies through annual action plans and have a designated role in ensuring appropriate local service delivery and effective utilisation of resources. At the sub national level, there are systems of annual district implementation plans and sub district implementation plans

Is the cMYP (or updated Multi-Year Plan) aligned with this document (timing, content, etc.)?

The time period of the cMYP is 2011 - 2015. This is aligned to the national health sector planning cycle. This proposal is aligned to the time period of 2011 - 2015

Please indicate the national planning budgeting cycle for health

The Health Strategic Plan is linked to a Medium Term Expenditure Framework. The annual budgeting cycle is based on the calendar year.Historically, the annual planning process at district level has been separate from the budget cycle. However, steps have been taken in recent times to more appropriately link planning and budgeting. There is a system of annual program review at the central level

Please indicate the national planning cycle for immunisation

Immunization forms part of the basic services package which is implemented nationally. All national programs are integrated at the sub district and district levels within annual district and sub district implementation plans.There is a line item in the national budget for immunization and the national government procures all vaccines and injection safety supplies.

Please indicate if sex disaggregated data (SDD) is used in immunisation routine reporting systems

Timor Leste conducted a DHS survey in 2010 which disaggraegtes data according to gender and education and income quintiles. In the cMYP, gender disaggregated data from the DHS data is presented for immunization coverage and other health and social indicators. Sex disaggregated data is also recorded on immunization tally sheets.

Please indicate if gender aspects relating to introduction of a new vaccine have been addressed in the introduction plan

The DHS 2010 survey demonstrates that infant mortality is slightly higher for boys than girls. Measles immunization coverage is slightly higher for boys (69%)than girls (66%). For DPT3, similarly the rate is 68.6% for boys compared to 64.1% for girls.

# Current vaccination schedule

Traditional, New Vaccines and Vitamin A supplement (refer to cMYP pages)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Vaccine (do not use trade name) | Ages of administration (by routine immunisation services) | Given in entire country | Comments | Action |
| --- | --- | --- | --- | --- |
| BCG | Birth to 1 Year | Yes |  |  |
| DTP-Hep B | 6 weeks or 1st contact after 6 weeks, + 1 month, + 1 month | Yes |  |  |
| Polio | 0-2 weeks, 6 weeks or 1st contact after 6 weeks, + 1 month, + 1 month | Yes |  |  |
| Measles | 9 months | Yes |  |  |
| TT | Pregnant women: 1st contact, + 1 month, + 6 months, + 1 year, + 1 year | Yes |  |  |
| Vitamin A | 2 doses 12-59 months. Post partum mothers | Yes |  |  |

# Trends of immunisation coverage and disease burden

(as per last two annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases)

| Trends of immunisation coverage (percentage) |  |  |  |  |  | Vaccine preventable disease burden |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine |  | Reported |  | Survey |  | Disease | Number of reported cases |  |
|  |  | 2009 | 2010 | 2009 | 2010 |  | 2009 | 2010 |
| BCG |  | 71 | 71 | 77 |  | Tuberculosis | 0 | 0 |
| DTP | DTP1 | 76 | 75 | 74 |  | Diphtheria | 0 | 0 |
|  | DTP3 | 72 | 72 | 64 |  | Pertussis | 0 | 0 |
| Polio 3 |  | 78 | 72 | 54 |  | Polio | 0 | 0 |
| Measles (first dose) |  | 70 | 66 | 60 |  | Measles | 10 | 50 |
| TT2+ (Pregnant women) |  | 39 | 33 | 76 |  | NN Tetanus | 2 | 7 |
| Hib3 |  |  |  |  |  | Hib[2] | 0 | 0 |
| Yellow Fever |  |  |  |  |  | Yellow fever |  |  |
| HepB3 |  | 72 | 72 | 63 |  | HepBsero-prevalence[1] |  |  |
| Vitamin A supplement Mothers (< 6 weeks post-delivery) |  |  | 39 | 55 |  |  |  |  |
| Vitamin A supplement Infants (>6 months) |  |  | 42 | 51 |  |  |  |  |

[1] If available

[2] Note: JRF asks for Hib meningitis

If survey data is included in the table above, please indicate the years the surveys were conducted, the full title and if available, the age groups the data refers to

A DHS Survey was conducted in Timor Leste 2009 and 2010 (Timor-Leste Demographic and Health Survey 2009-10 national Statistics Directorate Ministry of Finance). The Immunization data refers to children aged 12-23 months at time of survey. The TT coverage data refers to women aged 15-49 years who had a birth in the 5 years preceding the survey.

# Baseline and Annual Targets

(refer to cMYP pages)

Table 1: baseline figures

| Number | Base Year | Baseline and Targets |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2010 | 2012 | 2013 | 2014 | 2015 |  |  |
| Total births | 47,385 | 49,696 | 50,894 | 52,121 | 53,377 |  |  |
| Total infants' deaths | 2,132 | 2,236 | 2,290 | 2,345 | 2,402 |  |  |
| Total surviving infants | 45,253 | 47,460 | 48,604 | 49,776 | 50,975 |  |  |
| Total pregnant women | 51,650 | 54,170 | 55,475 | 56,812 | 58,181 |  |  |
| Number of infants vaccinated (to be vaccinated) with BCG | 29,770 | 41,248 | 45,805 | 48,472 | 51,242 |  |  |
| BCG coverage (%)[1] | 63% | 83% | 90% | 93% | 96% |  |  |
| Number of infants vaccinated (to be vaccinated) with OPV3 | 30,443 | 40,751 | 44,278 | 46,909 | 49,107 |  |  |
| OPV3 coverage (%)[2] | 67% | 86% | 91% | 94% | 96% |  |  |
| Number of infants vaccinated (or to be vaccinated) with DTP1[3] | 31,582 | 40,341 | 43,744 | 46,291 | 48,426 |  |  |
| Number of infants vaccinated (to be vaccinated) with DTP3[3] | 30,524 | 38,917 | 42,285 | 44,798 | 46,897 |  |  |
| DTP3 coverage (%)[2] | 67% | 82% | 87% | 90% | 92% |  |  |
| Wastage[1] rate in base-year and planned thereafter for DTP (%) | 50% | 50% | 40% | 30% | 20% |  |  |
| Wastage[1] factor in base-year and planned thereafter for DTP | 2 | 2 | 1.67 | 1.43 | 1.25 |  |  |
| Infants vaccinated (to be vaccinated) with 1st dose of HepB and/or Hib | 31,582 | 40,341 | 43,744 | 46,291 | 48,426 |  |  |
| Infants vaccinated (to be vaccinated) with 3rd dose of HepB and/or Hib | 30,524 | 38,917 | 42,285 | 44,798 | 46,897 |  |  |
| HepB and/or Hib 3rd dose coverage (%)[2] | 67% | 82% | 87% | 90% | 92% |  |  |
| Infants vaccinated (to be vaccinated) with 1st dose of Measles | 27,922 | 39,757 | 41,224 | 44,824 | 48,753 |  |  |
| Measles coverage (%)[2] | 62% | 84% | 85% | 90% | 96% |  |  |
| Pregnant women vaccinated with TT+ | 16,810 | 37,026 | 37,919 | 38,833 | 39,768 |  |  |
| TT+ coverage (%)[4] | 33% | 68% | 68% | 68% | 68% |  |  |
| Vit A supplement to mothers within 6 weeks from delivery |  |  |  |  |  |  |  |
| Vit A supplement to infants after 6 months |  |  |  |  |  |  |  |
| Annual DTP Drop-out rate[ ( DTP1 - DTP3 ) / DTP1 ] x 100[5] | 3% | 4% | 3% | 3% | 3% |  |  |

[1] Number of infants vaccinated out of total births

[2] Number of infants vaccinated out of total surviving infants

[3] Indicate total number of children vaccinated with either DTP alone or combined

[4] Number of pregnant women vaccinated with TT+ out of total pregnant women

[5] The formula to calculate a vaccine wastage rate (in percentage):[ ( A – B ) / A ] x 100. Whereby: A = the number of doses distributed for use according to the supply records with correction for stock balance at the end of the supply period; B = the number of vaccinations with the same vaccine in the same period.

# Summary of current and future immunisation budget

(or refer to cMYP pages)

|  | Estimated costs per annum in US$ (in thousand US$) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cost category | Base Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |  |
|  | 2010 | 2012 | 2013 | 2014 | 2015 |  |  |  |  |  |
| Routine Recurrent Cost |  |  |  |  |  |  |  |  |  |  |
| Vaccines (routine vaccines only) | 310,261 | 528,681 | 462,530 | 423,531 | 391,646 |  |  |  |  |  |
| Traditional vaccines | 135,148 | 99,618 | 102,191 | 96,051 | 90,941 |  |  |  |  |  |
| New and underused vaccines | 175,113 | 429,063 | 360,339 | 327,480 | 300,705 |  |  |  |  |  |
| Injection supplies | 33,381 | 27,665 | 27,104 | 28,397 | 29,658 |  |  |  |  |  |
| Personnel | 483,792 | 624,877 | 761,345 | 776,572 | 792,103 |  |  |  |  |  |
| Salaries of full-time NIP health workers (immunisation specific) | 455,352 | 589,108 | 718,557 | 732,928 | 747,586 |  |  |  |  |  |
| Per-diems for outreach vaccinators / mobile teams | 28,440 | 35,769 | 42,788 | 43,644 | 44,517 |  |  |  |  |  |
| Transportation | 12,144 | 14,694 | 16,164 | 17,780 | 19,558 |  |  |  |  |  |
| Maintenance and overheads | 169,097 | 211,786 | 233,894 | 237,209 | 266,260 |  |  |  |  |  |
| Training |  | 41,616 | 37,142 | 43,297 | 44,163 |  |  |  |  |  |
| Social mobilisation and IEC | 25,105 | 26,949 | 28,363 | 29,850 | 31,415 |  |  |  |  |  |
| Disease surveillance | 40,167 | 43,119 | 45,380 | 47,760 | 50,264 |  |  |  |  |  |
| Program management | 45,188 | 48,509 | 51,053 | 53,730 | 56,547 |  |  |  |  |  |
| Other | 269,000 | 306,538 | 95,400 | 96,000 | 99,000 |  |  |  |  |  |
| Subtotal Recurrent Costs | 1,388,135 | 1,874,434 | 1,758,375 | 1,754,126 | 1,780,614 |  |  |  |  |  |
| Routine Capital Costs |  |  |  |  |  |  |  |  |  |  |
| Vehicle |  | 67,626 | 68,979 | 70,358 | 71,765 |  |  |  |  |  |
| Cold chain equipment | 193,228 | 27,486 | 4,553 | 4,644 | 60,526 |  |  |  |  |  |
| Other capital equipment |  | 23,929 |  |  |  |  |  |  |  |  |
| Subtotal Capital Costs | 193,228 | 119,041 | 73,532 | 75,002 | 132,291 |  |  |  |  |  |
| Campaigns |  |  |  |  |  |  |  |  |  |  |
| Polio |  |  |  |  |  |  |  |  |  |  |
| Measles |  |  |  | 1,240,148 |  |  |  |  |  |  |
| Yellow Fever |  |  |  |  |  |  |  |  |  |  |
| MNT campaigns | 99,366 |  | 30,056 |  | 30,471 |  |  |  |  |  |
| Other campaigns |  |  |  |  |  |  |  |  |  |  |
| Subtotal Campaign Costs | 99,366 | 0 | 30,056 | 1,240,148 | 30,471 |  |  |  |  |  |
| GRAND TOTAL | 1,680,729 | 1,993,475 | 1,861,963 | 3,069,276 | 1,943,376 |  |  |  |  |  |

# Summary of current and future financing and sources of funds

Please list in the tables below the funding sources for each type of cost category (if known). Please try and indicate which immunisation program costs are covered from the Government budget, and which costs are covered by development partners (or the GAVI Alliance), and name the partners (or refer to cMYP).

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

|  |  | Estimated costs per annum in US$ (in thousand US$) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cost category | Funding source | Base Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |  |
|  |  | 2010 | 2012 | 2013 | 2014 | 2015 |  |  |  |  |  |
| Routine Recurrent Cost |  |  |  |  |  |  |  |  |  |  |  |
| Recurrent Costs | Government | 927,711 | 1,056,087 | 1,259,183 | 1,313,263 | 1,388,330 |  |  |  |  |  |
| Surveillance | WHO | 40,000 | 40,000 | 40,000 | 40,000 | 40,000 |  |  |  |  |  |
| Recurrent Costs | UNICEF | 147,594 | 200,000 | 200,000 | 200,000 | 200,000 |  |  |  |  |  |
| Recurrent Costs | USAID | 200,000 | 200,000 | 200,000 |  |  |  |  |  |  |  |
| Vaccines | GAVI | 0 | 418,400 | 284,000 | 182,000 | 83,000 |  |  |  |  |  |
|  | Other | 0 | 0 | 0 | 0 | 0 |  |  |  |  |  |
| Routine Capital Costs |  |  |  |  |  |  |  |  |  |  |  |
|  | Government |  |  |  |  |  |  |  |  |  |  |
|  | WHO |  |  |  |  |  |  |  |  |  |  |
| TT High Risk SIA | UNICEF |  |  |  |  |  |  |  |  |  |  |
|  | USAID |  |  |  |  |  |  |  |  |  |  |
|  | GAVI |  |  |  |  |  |  |  |  |  |  |
| Campaigns |  |  |  |  |  |  |  |  |  |  |  |
|  | Government |  |  |  |  |  |  |  |  |  |  |
|  | WHO |  |  |  |  |  |  |  |  |  |  |
|  | UNICEF | 99,366 |  |  |  |  |  |  |  |  |  |
|  | USAID |  |  |  |  |  |  |  |  |  |  |
|  | GAVI |  |  |  |  |  |  |  |  |  |  |
| GRAND TOTAL |  | 1,414,671 | 1,914,487 | 1,983,183 | 1,735,263 | 1,711,330 |  |  |  |  |  |

# New and Under-Used Vaccines (NVS)

Please summarise the cold chain capacity and readiness to accommodate new vaccines, stating how the cold chain expansion (if required) will be financed, and when it will be in place. Please indicate the additional cost, if capacity is not available and the source of funding to close the gap.

The introduction of DTP-HepB-Hib 10 dose vial (2.6 cm3/dose), which is only marginally bigger than the DTP-HepB 10 dose currently in use (2.1 cm3/dose) will be easily accomodated into the cold chain system and will not require purchase of new equipment. A vaccine management assessment conducted in 2007 with the WHO Vaccine Management Tool concluded that that storage capacity at primary and service delivery levels (except one sub-district) was adequate for the routine EPI vaccines, which included the supply of DTP-HepB vaccines, in 10 dose vial presentations. A comprehensive cold chain inventory (2008-2012) and gap analysis was also conducted. It was noted that 90% of equipment was in good working order and that a third of equipment was over six years old (life-expectancy at 10-12 years). As a consequence, over the period 2007-2010 UNICEF provided financial and technical assistance to purchase and install a total of 34 fridge/freezer units, 7 freezers, 16 ILRS and 15 solar units, and subsequently train district staff in the proper maintenance of the new equipment. The five-year cold chain rehabilitation plan will need to be updated and work must continue to develop an effective cold chain maintenance strategy. In preparation for a measles and tetanus campaign, a follow-up EVSM was conducted in 2009 and concluded that the primary vaccine store had more than sufficient capacity to accomodate all routine and campaign vaccines. Specifically 20,000 litre capacity available at +2-+8 degrees celsius versus 2,773 litres volume required (surplus 17,227 litres) and 10,000 litre capacity available at -15 to-25 degrees celsius versus 297 litres required (surplus 9,703 litres). The 2009 assessment further concluded that for routine EPI, none of the districts needed additional cold chain equipment. Prior to the introduction of DTP-HepB, knowledge about appropriate vaccine management handling was not well understood, and skills diminished from national to service delivery level. Since 2007,a Cold Chain and Vaccine Management (CCVM) training curricula was developed and 21 national and district staff were trained over a five-day course in mid 2009. The same staff then participated in a training skills course and vaccine management refresher training at the end of 2009 to then facilitate sub-national CCVM trainings. During 2009-2010 a series sub-national CCVM trainings were then conducted to train health workers, covering topics such as reading vaccine vial monitors, multi-dose vial policy, temperature monitoring, vaccine forecasting and calculating wastage. The CCVM trainings will continue as staff rotates and a new cadre of staff roll-in. Overall, vaccine management practices have improved at all levels in the past five years due to the investment in training and system improvements. The cold chain and logistics sytems is being established and stabilised and new technologies like digital freeze indicators have been widely introduced. To best prepare for future new vaccine introduction, efforts will continue on raising awareness and understanding among health staff -- particularly the newer work force expected over the next cMYP cycle – of vaccine temperature sensitivity, the importance of temperature monitoring and good vaccine handling, and proper record-keeping. One recent area of work that has been under-taken is vaccine wastage monitoring, as this is still not a concept that is well-understood or proactively managed. The last vaccne management assessments were conducted in the following years:WHO/UNICEF Vaccine Management Assessment Tool Oct-Nov 2007 WHO/UNICEF Effective Vaccine Store Management, March 2009, The next assessment is proposed for June-August 2011.

Please give a summary of the cMYP sections that refer to the introduction of new and under-used vaccines. Outline the key points that informed the decision-making process (data considered etc)

The WHO vaccine position paper (Nov 2006) recommends that Hib vaccine should be introduced into all routine infant immunization programmes. Furthermore, in 2009 WHO provided estimates of severe disease due to Hib, indicating a range of 2102 to 3780 cases per year in Timor Leste among children aged 1 month to 5 years and 33 deaths. This information, combined with technical information provided on global and regional Hib estimates, vaccine supply issues and co-financing projections were considered. Furthermore, lessons learned from the introduction of DTP-Hep B made apparent that Timor Leste is capable of introducing a new vaccine successfully. The Council of Directors therefore endorsed in April 2011 the proposition by the National Immunization Programme to introduce Hib vaccine.

# Capacity and cost (for positive storage)

|  |  | Formula | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| A | Annual positive volume requirement, including new vaccine (litres or m3) Litres | Sum-product of total vaccine doses multiplied by unit packed volume of the vaccine | 1,210 | 1,400 | 1,296 | 1,104 |  |  |  |  |
| B | Existing net positive cold chain capacity (litres or m3) Litres | # | 20,000 | 20,000 | 20,000 | 20,000 |  |  |  |  |
| C | Estimated minimum number of shipments per year required for the actual cold chain capacity | A / B | 1 | 1 | 1 | 1 |  |  |  |  |
| D | Number of consignments / shipments per year | Based on national vaccine shipment plan | 2 | 2 | 2 | 2 |  |  |  |  |
| E | Gap (if any) | ((A / D) - B) | -19,395 | -19,300 | -19,352 | -19,448 |  |  |  |  |
| F | Estimated additional cost of cold chain | US$ | 120,113 | 103,703 | 110,645 | 178,641 |  |  |  |  |

Please briefly describe how your country plans to move towards attaining financial sustainability for the new vaccines you intend to introduce, how the country will meet the co-financing payments, and any other issues regarding financial sustainability you have considered (refer to the cMYP)

The following issues, identified in the cMYP, and of direct relevance to the financial sustainability of ne wvaccine introduction. 1. Following introduction of tetravalent vaccine through AusAID support in 2007, the Government of Timor Leste assumed full resposibility for financing of the vaccine program from 2009. This demonstrates the committment and financial capacity of the Government of Timor Leste to finance the recurrent costs of the national immunization program. 2. Currently the MOH finances 79% of program costs. Wider developments in the health system in the coming years, including improvements to roads and communications, should result in improved demand for fixed facility services in the coming years. This will reduce somewhat in improved efficiency of the program. 3. Improving GNI will increase the capacity of the national government to direct financing to social sectors.

# Assessment of burden of relevant diseases (if available)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Disease | Title of the assessment | Date | Results |  |
| --- | --- | --- | --- | --- |
| Haemophilus Influenzae Type B Disease | Estimates of severe illness cases and deaths in children from one month to less than | 27 July 2009 | There is an annual estimate of 2321 pneumonia cases due to Hib. (Estimates range from 2102 to 3780 cases). The incidence rate for pneumonia is estimated at 1382/100,000. 45 meningitis cases are expected per year (incidence 28/100,000). The report is annexed to this application. |  |
| Broncho/Pneummonia and Meningitis/encephalitis | Health Management Information System Timor Leste | 2010 | There were 1292 reported cases of broncho-pneummonia/pneummonia in 2010 in under 5 children (63 deaths). There were 21 reported meningitis cases in 2010 in under 5 children (6 deaths). |  |

If new or under-used vaccines have already been introduced in your country, please give details of the lessons learned from storage capacity, protection from accidental freezing, staff training, cold chain, logistics, drop-out rate, wastage rate etc., and suggest action points to address them

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Lessons Learned | Action Points |  |
| --- | --- | --- |
| Important success factor included preparing an inventory of the cold chain plan and developing a rehabilitation plan. Introducing the RED approach (detailed micro-plan) was an important factor in improving coverage. Ensuring the development and dissemination of immunization policy to all managers and health providers was essential for updating on quality and standards for immunization services. Training of health staff in middle level management, side effects and refreshment of technical skills were all important factors for supporting the introduction of tetravalent vaccine. With the last vaccine introduction, public information was too focussed on the urban areas and communication effors should target a wider population | The next vaccine management assessment will be conducted in 2011. Ongoing efforts will be made to integrate cold and vaccine management into MLM and immunization in practice training. In 2011, a MLM program is being conducted with micro-planning being one of the main components. The Immunization Policy is being updated in 2011 and will be disseminated with immunization training for new vaccine introduction. Two main areas of focus for the immunization policy update will be surveillance and AEFI. For introduction planning for pentavalent, more emphasis in the communication strategy will be placed on strategies to communicate with more rural and remote populations. |  |

Please list the vaccines to be introduced with support from the GAVI Alliance (and presentation)

Pentavalent Vaccine (DPT-Heb B-Hib) 10 Dose liquid Vials

# 6.3.1. Requested vaccine ( DTP-HepB-Hib, 10 doses/vial, Liquid )

As reported in the cMYP, the country plans to introduce DTP-HepB-Hib, 10 doses/vial, Liquid vaccine.

# 6.3.2. Co-financing information

If you would like to co-finance higher amount than minimum, please overwrite information in the “Your co-financing” row.

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

| Country group | Graduating |
| --- | --- |

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Minimum co-financing | 0.37 | 0.74 | 1.11 | 1.48 |  |  |  |  |
| Your co-financing (please change if higher) | 0.37 | 0.74 | 1.11 | 1.48 |  |  |  |  |

# 6.3.3. Wastage factor

Please indicate wastage rate:

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Vaccine wastage rate in % | 25% | 25% | 25% | 20% |  |  |  |  |
| Equivalent wastage factor | 1.33 | 1.33 | 1.33 | 1.25 |  |  |  |  |

# 6.3.4. Specifications of vaccinations with new vaccine

|  | Data from |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 40,341 | 43,744 | 46,291 | 48,426 |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 38,917 | 42,285 | 44,798 | 46,897 |  |  |  |  |
| Immunisation coverage with the third dose | Table 1 | # | 82.00% | 87.00% | 90.00% | 92.00% |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[3] | # | 1.33 | 1.33 | 1.33 | 1.25 |  |  |  |  |
| Country co-financing per dose[2] | Table 6.(n).2[3] | $ | 0.37 | 0.74 | 1.11 | 1.48 |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Total price per-dose includes vaccine cost, plus freight, supplies, insurance, visa costs etc.

[3] Where (n) depends on the vaccine

# 6.3.5. Portion of supply to be procured by the country (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Number of vaccine doses | # | 28,500 | 53,600 | 96,400 | 136,200 |  |  |  |  |
| Number of AD syringes | # | 25,400 | 45,100 | 80,800 | 121,000 |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 300 | 500 | 900 | 1,350 |  |  |  |  |
| Total value to be co-financed by country | $ | 74,500 | 132,000 | 208,000 | 269,000 |  |  |  |  |

# 6.3.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Number of vaccine doses | # | 172,800 | 124,400 | 90,900 | 45,500 |  |  |  |  |
| Number of AD syringes | # | 153,700 | 104,500 | 76,200 | 40,400 |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 1,725 | 1,175 | 850 | 450 |  |  |  |  |
| Total value to be co-financed by GAVI | $ | 452,000 | 305,500 | 196,000 | 90,000 |  |  |  |  |

# 6.3.7. New and Under-Used Vaccine Introduction Grant

Please indicate in the tables below how the one-time Introduction Grant[1] will be used to support the costs of vaccine introduction and critical pre-introduction activities (refer to the cMYP).

Calculation of lump-sum for the DTP-HepB-Hib, 10 doses/vial, Liquid

If the total is lower than US$100,000, it is automatically rounded up to US$100,000

| Year of New Vaccine Introduction | Births (from Table 1) | Share per Birth in US$ | Total in US$ |
| --- | --- | --- | --- |
| 2012 | 49,696 | 0.30 | 100,000 |

[1] The Grant will be based on a maximum award of $0.30 per infant in the birth cohort with a minimum starting grant award of $100,000

Cost (and finance) to introduce the DTP-HepB-Hib, 10 doses/vial, Liquid (US$)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Cost Category | Full needs for new vaccine introduction in US$ | Funded with new vaccine introduction grant in US$ |  |
| --- | --- | --- | --- |
| Training | 39,000 | 39,000 |  |
| Social Mobilization, IEC and Advocacy | 42,000 | 42,000 |  |
| Cold Chain Equipment & Maintenance | 20,000 |  |  |
| Vehicles and Transportation | 10,000 | 10,000 |  |
| Programme Management | 5,000 | 5,000 |  |
| Surveillance and Monitoring | 4,000 | 4,000 |  |
| Human Resources |  |  |  |
| Waste Management |  |  |  |
| Technical assistance |  |  |  |
| Totals | 120,000 | 100,000 |  |

# Procurement and Management of New and Under-Used Vaccines

Note: The PCV vaccine must be procured through UNICEF

- Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that most countries will procure vaccine and injection supplies through UNICEF)

1. Introduction planning and implementation will be managed through the National EPI program at the Ministry of Health. 2. Major policy and technical decsions will be made through the Council of Directors at the Ministry of Health. 3. Introduction activities will be technical advised and coordinated by the EPI National Working Group that is represented by the EPI program, WHO, UNICEF and NGO partners. 4. Vaccines will be procured through UNICEF procurement mechanisms.

- If an alternative mechanism for procurement and delivery of supply (financed by the country or the GAVI Alliance) is requested, please document

- Other vaccines or immunisation commodities procured by the country and descriptions of the mechanism used.

- The functions of the National Regulatory Authority (as evaluated by WHO) to show they comply with WHO requirements for procurement of vaccines and supply of assured quality.

N/A

- Please describe the introduction of the vaccines (refer to cMYP)

The cMYP on page 26 describes the strategies for introduction of new vaccines and activity mapping is attached as Document 16: 1. The introduction plan describes how managers will undertake a review of sentinel surveillance systems in the region in preparation for establishment of such a system in Timor Leste. 2. The vaccine will be introduced as per MOH decision into the routine schedule from early 2012. The vaccine will be introduced nationwide. 3. IEC programs will be implemented nationwide through media, launching and training of volunteers and local authorities, especially in remote areas. 4. There will be important preparatory activities to prepare the EPI system for introduction. A follow up EVM assessment from the one conducted in 2009 will be conducted in June 2011. Also, WHO will provide technical assistance to develop country specfic AEFI guidelines in 2011. A feasibility assessment will also be conducted for establishment of a meningitis-encephaltis hospital sentinel site (AES guidelines are already available but the system is not yet functional). 5. Staff and managers will trained in new vaccine introduction, with a special empahsis on surveillance and AEFI. Training will be followed up by supervision and monitoring from Districts A costed activity plan is also appended which describes the new vaccine introduction plan which is summarized below according to the main components. (a)Preparatory Activities. These activities include conducting an updated EVM assessment and development of an EVM Plan. In preparation for introduction, many changes to documentation will be required, including updating of the immunization strategy and preparation of new EPI health information forms and IEC materials (including immunization cards for parents. Activities will also be under taken to ensure timly procurement and distribution of vaccines. (b)Immunization Safety and AEFI Surveillance. As outlined in the cMYP, there is currently a proposal to position an AEFI officer at the surveillance unit at the MOH. Upcoming MLM training programs for community health centre managers will have a component on AEFI surveillance. In other issues relating to surveillance, there was a agreement that a feasibility study should be organized in order to establish a sentinel surveillance system for meningitis and encephalitis. (c)Training and IEC. A substantial range of activities are proposed for training and IEC. In terms of training, in addition to the MLM program proposed this year, there will be a national workshop for central and District levels on Hib disease and vaccine introduction, followed by District workshops for CHJC managers and staff. The focus of the training will be on Hib disease, the new vaccine, as well as reinforcing of AEFI responses, cold chain management and Red strategy implementation. In terms of IEC there will be an official launching of the program, as well as an orientation of local authorities and PSF volunteers regarding the new vaccine and the EPI program. Finally, there will also be investments in media materials including radio and TV messages on the new vaccine and printed materials for community members. (d)Supervision and Monitoring. The cMYP details strategies and plans for improving supervision and monitoring through MLM programs (to be implemnted in 2011), development of supervision guidelines and strengthening the monitoring functions of the EPI technical working group. The annexed introduction plan includes plans for on site training and supervision by national and district supervisors and a post introduction evaluation in 2013.

- Please indicate how funds should be transferred by the GAVI Alliance (if applicable)

1. Introduction Grants funds should be channelled to the Government Bank Account as specified in this application (refer to attachment 8).

- Please indicate how the co-financing amounts will be paid (and who is responsible for this)

Government co financing amounts will be paid by the Directorate of Finance at the Ministry of Health. Following provision of the cost estimate from the Supply Division in UNICEF, the MOH will approve the cost estimate and transfer the funds to UNICEF Supply Division. The agency responsible for this function is the Directorate of Finance at the Ministry of Health in Timor Leste.

- Please outline how coverage of the new vaccine will be monitored and reported (refer to cMYP)

Objectives 1,2 and 3 in the cMYP (programme management, service delivery and routine immunization, )are the main areas outlining monitoring and reporting. In summary the main strategies are as follows: (a) Developing line list of high priority Community Health centres and Villages (b) Developing needs based mirco-plans that indentify areas with unreached children and describe the actions to reach them (c) Implementation of programs of supportive supervision, reinforced through Middle level management training in May/June 2011. (d) Use of immunization monitoring charts at facility level to track coverage and alert for immunization drop out. Integrated surveillance systems have been developed in Timor Leste for AFP, measles and MNTE but these systems will require strengthening, commencing with MLM capacity building in May/June 2011 and the extending to immunization in practice training in 2012. Surveillance topics will also be updated during introduction training. The Regional and Country Offices of WHO will provide technical support during the next cMYP plan cycle to develop sentinel surveillance systems for meningitis, encephalitis and pneummonia at a selection of the 6 Hospitals in Timor Leste. (cMYP page 25) Although MOH managers and staff are required to report adverse events, systems will require strengthening. In 2011, WHO will provide technical assistance to develop country specific AEFI guidelines. Reporting of AEFI will be reinforced duting MLM and vaccine introduction training in 2011 (see Page 26 CMYP)

# Vaccine Management (EVSM/EVM/VMA)

When was the last Effective Vaccine Store Management (EVSM) conducted? March  - 2009

When was the last Effective Vaccine Management (EVM) or Vaccine Management Assessment (VMA) conducted? May  - 2007

- If your country conducted either EVSM, EVM, or VMA in the past three years, please attach relevant reports. (Document N°13)

- A VMA report must be attached from those countries which have introduced a New and Underused Vaccine with GAVI support before 2008.

- Please note that EVSM and VMA tools have been replaced by an integrated Effective Vaccine Management (EVM) tool. The information on EVM tool can be found at http://www.who.int/immunization_delivery/systems_policy/logistics/en/index6.html

- For countries which conducted EVSM, VMA or EVM in the past, please report on activities carried out as part of either action plan or improvement plan prepared after the EVSM/VMA/EVM.

Improvements to Cold Chain and vaccine Management over recent years are detailed in the cMYP on pages 15 and 16. In summary, the main points are as follows: 1. CAPITAL EQUIPMENT A vaccine management assessment in 2007 observed that 90% of equipment was in good working order and that a third of equipment was over six years old (life-expectancy at 10-12 years). As a consequence over the period 2007-2010 UNICEF provided financial and technical assistance to purchase and install a total of 34 fridge/freezer units, 7 freezers, 16 ILRS and 15 solar units, and subsequently train district staff in the proper maintenance of the new equipment. 2. TRAINING A Cold Chain and Vaccine Management (CCVM) training curricula was developed and 21 national and district staff were trained over a five-day course in mid 2009. During 2009-2010 a series sub-national CCVM trainings were then conducted to train health workers, covering topics such as reading vaccine vial monitors, multi-dose vial policy, temperature monitoring, vaccine forecasting and calculating wastage. As illustrated in Table 2.5 below, while weaknesses in the central store management persist, there have been notable improvements to the system, particularly in the areas of vaccine arrival and handing, monitoring of temperatures and stock management. While cold chain capacity for all routine and campaign doses of tetanus and measles was deemed quite sufficient, it was noted the vaccine storekeeper needed further training on volume capacity analysis, hence the lowered score. 3. TECHNOLOGIES Overall, vaccine management practices have improved at all levels in the past five years due to the investment in training and system improvements. The cold chain and logistics systems is being established and stabilised and new technologies like digital freeze indicators have been widely introduced. To best prepare for future new vaccine introduction, efforts will continue on raising awareness and understanding among health staff -- particularly the newer work force expected over the next cMYP cycle – of vaccine temperature sensitivity, the importance of temperature monitoring and good vaccine handling, and proper record-keeping.

- When is the next Effective Vaccine Management (EVM) Assessment planned? June  - 2011

- Under new guidelines, it will be mandatory for the countries to conduct an EVM prior to an application for introduction of new vaccine.

# Additional Comments and Recommendations

Comments and Recommendations from the National Coordinating Body (ICC/HSCC)

WASTAGE: Due to the fact the EPI program is in an early stage of development and due to in accessibility of many remote areas due to communication, geographic and transport barriers, reducing vaccine wastage is a major challenge for the EPI program. The cMYP (see pages 25 cMYP) details strategies by which vaccine wastage will be monitored and reduced. At this stage it is not feasible that vaccine wastage can be reduced from 50% to 25% in 1 or 2 years. The plan in the cMYP is to reduce wastage from 50% to 20% over 4 years. This being the case, it is requested that GAVI take this plan into consideration when considering this vaccine proposal request. That is, the country is requesting vaccine supply based on a wastage rate of 50% in 2012. This will prevent the risk of stock out and interruption to the program. POPULATION: The population reported in the JRF for 2010 (total births) is 47,385. The 2010 has identified a new infant mortality rate of 45 per 1000 live births as identified in the 2010 DHS Survey. For this reason, the surviviving infants for 2010 and subsequent years has been readjusted to take into account this new figure.

# Annexes

# Annex 1

# Annex 1.1 – DTP-HepB-Hib, 10 doses/vial, Liquid

Table 1.1 A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

| Required supply item |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # | 28,500 | 53,600 | 96,400 | 136,200 |  |  |  |  |
| Number of AD syringes | # | 25,400 | 45,100 | 80,800 | 121,000 |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 300 | 500 | 900 | 1,350 |  |  |  |  |
| Total value to be co-financed by the country | $ | 74,500 | 132,000 | 208,000 | 269,000 |  |  |  |  |

Table 1.1  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

| Required supply item |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # | 172,800 | 124,400 | 90,900 | 45,500 |  |  |  |  |
| Number of AD syringes | # | 153,700 | 104,500 | 76,200 | 40,400 |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 1,725 | 1,175 | 850 | 450 |  |  |  |  |
| Total value to be co-financed by the country | $ | 452,000 | 305,500 | 196,000 | 90,000 |  |  |  |  |

Table 1.1  C - Summary table for DTP-HepB-Hib, 10 doses/vial, Liquid

|  | Data from |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of Surviving infants | Table 1 | # | 47,460 | 48,604 | 49,776 | 50,975 |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 38,917 | 42,285 | 44,798 | 46,897 |  |  |  |  |
| Immunisation coverage with the last dose | Table 1 | # | 82.00% | 87.00% | 90.00% | 92.00% |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 40,341 | 43,744 | 46,291 | 48,426 |  |  |  |  |
| Number of doses per child |  | # | 3 | 3 | 3 | 3 |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[2] | # | 1.33 | 1.33 | 1.33 | 1.25 |  |  |  |  |
| Number of doses per vial |  | # | 10 | 10 | 10 | 10 |  |  |  |  |
| AD syringes required |  | # | Yes | Yes | Yes | Yes |  |  |  |  |
| Reconstitution syringes required |  | # | No | No | No | No |  |  |  |  |
| Safety boxes required |  | # | Yes | Yes | Yes | Yes |  |  |  |  |
| Vaccine price per dose |  | $ | 2.470 | 2.320 | 2.030 | 1.850 |  |  |  |  |
| Country co-financing per dose | Table 6.(n).2[2] | $ | 0.37 | 0.74 | 1.11 | 1.48 |  |  |  |  |
| AD syringe price per unit |  | $ | 0.053 | 0.053 | 0.053 | 0.053 |  |  |  |  |
| Reconstitution syringe price per unit |  | $ |  |  |  |  |  |  |  |  |
| Safety box price per unit |  | $ | 0.640 | 0.640 | 0.640 | 0.640 |  |  |  |  |
| Freight cost as % of vaccines value |  | % | 3.50 | 3.50 | 3.50 | 3.50 |  |  |  |  |
| Freight cost as % of devices value |  | % | 10.00 | 10.00 | 10.00 | 10.00 |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.1 D - Estimated number of doses for DTP-HepB-Hib, 10 doses/vial, Liquid associated injection safety material and related co-financing budget (page 1)

|  |  | Formula | 2012 |  |  | 2013 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 14.15% |  |  | 30.12% |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 40,341 | 5,708 | 34,633 | 43,744 | 13,177 | 30,567 |
| C | Number of doses per child | Vaccine parameter | 3 | 3 | 3 | 3 | 3 | 3 |
| D | Number of doses needed | B * C | 121,023 | 17,122 | 103,901 | 131,232 | 39,529 | 91,703 |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 | 1.33 |
| F | Number of doses needed including wastage | D * E | 160,961 | 22,773 | 138,188 | 174,539 | 52,574 | 121,965 |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 40,241 | 5,694 | 34,547 | 3,395 | 1,023 | 2,372 |
| I | Total vaccine doses needed | F + G | 201,202 | 28,466 | 172,736 | 177,934 | 53,597 | 124,337 |
| J | Number of doses per vial | Vaccine parameter | 10 | 10 | 10 | 10 | 10 | 10 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 | 179,004 | 25,325 | 153,679 | 149,436 | 45,013 | 104,423 |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | (K + L) / 100 x 1.11 | 1,987 | 282 | 1,705 | 1,659 | 500 | 1,159 |
| N | Cost of vaccines needed | I * vaccine price per dose | 496,969 | 70,310 | 426,659 | 412,807 | 124,344 | 288,463 |
| O | Cost of AD syringes needed | K * AD syringe price per unit | 9,488 | 1,343 | 8,145 | 7,921 | 2,386 | 5,535 |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 1,272 | 180 | 1,092 | 1,062 | 320 | 742 |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 17,394 | 2,461 | 14,933 | 14,449 | 4,353 | 10,096 |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 1,076 | 153 | 923 | 899 | 271 | 628 |
| T | Total fund needed | (N + O + P + Q + R + S) | 526,199 | 74,445 | 451,754 | 437,138 | 131,672 | 305,466 |
| U | Total country co-financing | I * country co-financing per dose | 74,445 |  |  | 131,672 |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 14.15% |  |  | 30.12% |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.1 D - Estimated number of doses for DTP-HepB-Hib, 10 doses/vial, Liquid associated injection safety material and related co-financing budget (page 2)

|  |  | Formula | 2014 |  |  | 2015 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 51.47% |  |  | 74.99% |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 46,291 | 23,828 | 22,463 | 48,426 | 36,318 | 12,108 |
| C | Number of doses per child | Vaccine parameter (schedule) | 3 | 3 | 3 | 3 | 3 | 3 |
| D | Number of doses needed | B * C | 138,873 | 71,482 | 67,391 | 145,278 | 108,952 | 36,326 |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.33 | 1.33 | 1.33 | 1.25 | 1.25 | 1.25 |
| F | Number of doses needed including wastage | D * E | 184,702 | 95,071 | 89,631 | 181,598 | 136,190 | 45,408 |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 2,541 | 1,308 | 1,233 | 0 | 0 | 0 |
| I | Total vaccine doses needed | F + G | 187,243 | 96,379 | 90,864 | 181,598 | 136,190 | 45,408 |
| J | Number of doses per vial | Vaccine parameter | 10 | 10 | 10 | 10 | 10 | 10 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 | 156,970 | 80,797 | 76,173 | 161,259 | 120,937 | 40,322 |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | (K + L) / 100 x 1.11 | 1,743 | 898 | 845 | 1,790 | 1,343 | 447 |
| N | Cost of vaccines needed | I * vaccine price per dose | 380,104 | 195,650 | 184,454 | 335,957 | 251,951 | 84,006 |
| O | Cost of AD syringes needed | K * AD syringe price per unit | 8,320 | 4,283 | 4,037 | 8,547 | 6,410 | 2,137 |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 1,116 | 575 | 541 | 1,146 | 860 | 286 |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 13,304 | 6,848 | 6,456 | 11,759 | 8,819 | 2,940 |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 944 | 486 | 458 | 970 | 728 | 242 |
| T | Total fund needed | (N + O + P + Q + R + S) | 403,788 | 207,840 | 195,948 | 358,379 | 268,766 | 89,613 |
| U | Total country co-financing | I * country co-financing per dose | 207,840 |  |  | 268,766 |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 51.47% |  |  | 74.99% |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Annex 2

Estimated prices of supply and related freight cost: 2011 from UNICEF Supply Division; 2012 onwards: GAVI Secretariat

Table A - Commodities Cost

| Vaccine | Presentation | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AD syringe | 0 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 |
| DTP-HepB | 2 | 1.600 |  |  |  |  |  |  |
| DTP-HepB | 10 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-Hib | 10 | 3.400 | 3.400 | 3.400 | 3.400 | 3.400 | 3.200 | 3.200 |
| HepB monoval | 1 |  |  |  |  |  |  |  |
| HepB monoval | 2 |  |  |  |  |  |  |  |
| Hib monoval | 1 | 3.400 |  |  |  |  |  |  |
| Measles | 10 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 |
| Pneumococcal(PCV10) | 2 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 |
| Pneumococcal(PCV13) | 1 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 |
| Reconstit syringe for Pentaval (2ml) | 0 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 |
| Reconstit syringe for YF | 0 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 |
| Rotavirus 2-dose schedule | 1 | 7.500 | 6.000 | 5.000 | 4.000 | 3.600 | 3.600 | 3.600 |
| Rotavirus 3-dose schedule | 1 | 5.500 | 4.000 | 3.333 | 2.667 | 2.400 | 2.400 | 2.400 |
| Safety box | 0 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 |
| Yellow Fever | WAP | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 |
| Yellow Fever | WAP | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 |

Note: WAP - weighted average price (to be used for any presentation: For DTP-HepB-Hib, it applies to 1 dose liquid, 2 dose lyophilised and 10 dose liquid. For Yellow Fever, it applies to 5 dose lyophilised and 10 dose lyophilised)

Table B - Commodities Freight Cost

| Vaccines | Group | No Threshold | 200’000 $ |  | 250’000 $ |  | 2’000’000 $ |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | <= | > | <= | > | <= | > |
| Yellow Fever | Yellow Fever |  | 20% |  |  |  | 10% | 5% |
| DTP+HepB | HepB and or Hib | 2% |  |  |  |  |  |  |
| DTP-HepB-Hib | HepB and or Hib |  |  |  | 15% | 3,50% |  |  |
| Pneumococcal vaccine (PCV10) | Pneumococcal | 5% |  |  |  |  |  |  |
| Pneumococcal vaccine (PCV13) | Pneumococcal | 5% |  |  |  |  |  |  |
| Rotavirus | Rotavirus | 5% |  |  |  |  |  |  |
| Measles | Measles | 10% |  |  |  |  |  |  |

Table C - Graduating - Minimum country's co-payment per dose of co-financed vaccine.

| vaccine | 2012 | 2013 | 2014 | 2015 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| DTP-HepB-Hib, 10 doses/vial, Liquid | 0.37 | 0.74 | 1.11 | 1.48 |  |  |  |

Table D - Wastage rates and factors

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2 | 2.22 | 2.5 |

WHO International shipping guidelines: maximum packed volumes of vaccines

Table E - Vaccine maximum packed volumes

| Vaccine product | Designation | Vaccine formulation | Admin route | No. Of doses in the schedule | Presentation (doses/vial, prefilled) | Packed volume vaccine (cm3/dose) | Packed volume diluents (cm3/dose) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| BCG | BCG | lyophilized | ID | 1 | 20 | 1.2 | 0.7 |
| Diphtheria-Tetanus-Pertussis | DTP | liquid | IM | 3 | 20 | 2.5 |  |
| Diphtheria-Tetanus-Pertussis | DTP | liquid | IM | 3 | 10 | 3.0 |  |
| Diphtheria-Tetanus | DT | liquid | IM | 3 | 10 | 3.0 |  |
| Tetanus-Diphtheria | Td | liquid | IM | 2 | 10 | 3.0 |  |
| Tetanus Toxoid | TT | liquid | IM | 2 | 10 | 3.0 |  |
| Tetanus Toxoid | TT | liquid | IM | 2 | 20 | 2.5 |  |
| Tetanus Toxoid UniJect | TT | liquid | IM | 2 | Uniject | 12.0 |  |
| Measles | Measles | lyophilized | SC | 1 | 1 | 26.1 | 20.0 |
| Measles | Measles | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles | Measles | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles | Measles | lyophilized | SC | 1 | 10 | 3.5 | 4.0 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 1 | 26.1 | 26.1 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 1 | 26.1 | 26.1 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 10 | 3.0 | 4.0 |
| Polio | OPV | liquid | Oral | 4 | 10 | 2.0 |  |
| Polio | OPV | liquid | Oral | 4 | 20 | 1.0 |  |
| Yellow fever | YF | lyophilized | SC | 1 | 5 | 6.5 | 7.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 10 | 2.5 | 3.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 20 | 1.5 | 2.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 50 | 0.7 | 1.0 |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 1 | 9.7 |  |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 2 | 6.0 |  |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 10 | 3.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 1 | 18.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 2 | 13.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 6 | 4.5 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 10 | 4.0 |  |
| Hepatitis B UniJect | HepB | liquid | IM | 3 | Uniject | 12.0 |  |
| Hib liquid | Hib_liq | liquid | IM | 3 | 1 | 15.0 |  |
| Hib liquid | Hib_liq | liquid | IM | 3 | 10 | 2.5 |  |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 1 | 13.0 | 35.0 |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 2 | 6.0 |  |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 10 | 2.5 | 3.0 |
| DTP liquid + Hib freeze-dried | DTP+Hib | liquid+lyop. | IM | 3 | 1 | 45.0 |  |
| DTP-Hib combined liquid | DTP+Hib | liquid+lyop. | IM | 3 | 10 | 12.0 |  |
| DTP-Hib combined liquid | DTP-Hib | liquid | IM | 3 | 1 | 32.3 |  |
| DTP-HepB liquid + Hib freeze-dried | DTP-Hib | liquid | IM | 3 | 10 | 2.5 |  |
| DTP-HepB liquid + Hib freeze-dried | DTP-HepB+Hib | liquid+lyop. | IM | 3 | 1 | 22.0 |  |
| DTP-HepB-Hib liquid | DTP-HepB+Hib | liquid+lyop. | IM | 3 | 2 | 11.0 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 10 | 4.4 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 2 | 13.1 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 1 | 19.2 |  |
| Meningitis A/C | MV_A/C | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis A/C | MV_A/C | lyophilized | SC | 1 | 50 | 1.5 | 3.0 |
| Meningococcal A/C/W/ | MV_A/C/W | lyophilized | SC | 1 | 50 | 1.5 | 3.0 |
| Meningococcal A/C/W/Y | MV_A/C/W/Y | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis W135 | MV_W135 | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis A conjugate | Men_A | lyophilized | SC | 2 | 10 | 2.6 | 4.0 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 10 | 15.0 |  |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 10 | 8.1 | 8.1 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 5 | 2.5 | 2.9 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 1 | 12.6 | 11.5 |
| Japanese Encephalitis | JE_liq | liquid | SC | 3 | 10 | 3.4 |  |
| Rota vaccine | Rota_lyo | lyophilized | Oral | 2 | 1 | 156.0 |  |
| Rota vaccine | Rota_liq | liquid | Oral | 2 | 1 | 17.1 |  |
| Rota vaccine | Rota_liq | liquid | Oral | 3 | 1 | 45.9 |  |
| Pneumo. conjugate vaccine 7-valent | PCV-7 | liquid | IM | 3 | PFS | 55.9 |  |
| Pneumo. conjugate vaccine 7-valent | PCV-7 | liquid | IM | 3 | 1 | 21.0 |  |
| Pneumo. conjugate vaccine 10-valent | PCV-10 | liquid | IM | 3 | 1 | 11.5 |  |
| Pneumo. conjugate vaccine 10-valent | PCV-10 | liquid | IM | 3 | 2 | 4.8 |  |
| Pneumo. conjugate vaccine 13-valent | PCV-13 | liquid | IM | 3 | 1 | 12.0 |  |
| Polio inactivated | IPV | liquid | IM | 3 | PFS | 107.4 |  |
| Polio inactivated | IPV | liquid | IM | 3 | 10 | 2.5 |  |
| Polio inactivated | IPV | liquid | IM | 3 | 1 | 15.7 |  |
| Human Papilomavirus vaccine | HPV | liquid | IM | 3 | 1 | 15.0 |  |
| Human Papilomavirus vaccine | HPV | liquid | IM | 3 | 2 | 5.7 |  |
| Monovalent OPV-1 | mOPV1 | liquid | Oral |  | 20 | 1.5 |  |
| Monovalent OPV-3 | mOPV3 | liquid | Oral |  | 20 | 1.5 |  |

# Attachments

# List of Supporting Documents Attached to this Proposal

| Document | Section | Document Number | Mandatory[1] |
| --- | --- | --- | --- |
| MoH Signature (or delegated authority) of Proposal |  | 1 | Yes |
| MoF Signature (or delegated authority) of Proposal |  | 2 | Yes |
| Signatures of ICC or HSCC or equivalent in Proposal |  | 3 | Yes |
| Minutes of ICC/HSCC meeting endorsing Proposal |  | 4 | Yes |
| comprehensive Multi Year Plan - cMYP |  | 14 | Yes |
| cMYP Costing tool for financial analysis |  | 15 | Yes |
| Minutes of last three ICC/HSCC meetings |  | 13 | Yes |
| Improvement plan based on EVM |  | 9 | Yes |
| WHO/UNICEF Joint Reporting Form (JRF) |  | 6 |  |
| ICC/HSCC workplan for forthcoming 12 months |  | 7 |  |
| National policy on injection safety |  | 8 |  |
| Action plans for improving injection safety |  |  |  |
| Plan for NVS introduction (if not part of cMYP) |  | 16 |  |
| Banking details |  | 5 |  |

[1] Please indicate the duration of the plan / assessment / document where appropriate

# Attachments

List of all the mandatory and optional documents attached to this form

Note: Use the Upload file arrow icon to upload the document. Use the Delete item icon to delete a line. To add new lines click on the New item icon in the Action column.

| ID | File type | File name |  | New file | Actions |
| --- | --- | --- | --- | --- | --- |
|  | Description | Date and Time | Size |  |  |
| 1 | File Type: MoH Signature (or delegated authority) of Proposal * File Desc: | File name: DOC 1 Signature MOH.pdf Date/Time: 09.05.2011 21:01:14 Size: 635 KB |  |  |  |
| 2 | File Type: MoF Signature (or delegated authority) of Proposal * File Desc: | File name: DOC 2 Signature MOF.pdf Date/Time: 09.05.2011 21:02:12 Size: 635 KB |  |  |  |
| 3 | File Type: Signatures of ICC or HSCC or equivalent in Proposal * File Desc: | File name: DOC 3 Signature ICC.pdf Date/Time: 09.05.2011 21:02:12 Size: 619 KB |  |  |  |
| 4 | File Type: Minutes of ICC/HSCC meeting endorsing Proposal * File Desc: | File name: DOC 4 Minutes Endorsing proposal May 3 2011.doc.docx Date/Time: 03.05.2011 02:47:58 Size: 17 KB |  |  |  |
| 5 | File Type: Banking details File Desc: | File name: DOC 9 Banking Form.pdf Date/Time: 09.05.2011 20:58:05 Size: 1 MB |  |  |  |
| 6 | File Type: WHO/UNICEF Joint Reporting Form (JRF) File Desc: | File name: DOC 10 updated_TLS_JRF_2010_SEARO_11_APRIL_2011.xls Date/Time: 02.05.2011 02:40:17 Size: 277 KB |  |  |  |
| 7 | File Type: ICC/HSCC workplan for forthcoming 12 months File Desc: | File name: DOC 11 Work Plan for National EPI Technical Working Group 2011 Timor Leste.docx Date/Time: 02.05.2011 02:40:17 Size: 19 KB |  |  |  |
| 8 | File Type: National policy on injection safety File Desc: National Immunization Strategy | File name: DOC 12 EPIStrategy07_Es[1].pdf Date/Time: 02.05.2011 02:39:10 Size: 298 KB |  |  |  |
| 9 | File Type: Improvement plan based on EVM * File Desc: EVM | File name: DOC 13 Annex_Exec_summa_mission_TL_07.doc Date/Time: 02.05.2011 02:39:10 Size: 171 KB |  |  |  |
| 10 | File Type: other File Desc: EVSM | File name: DOC 14 Annex_EVSM2009.pdf Date/Time: 02.05.2011 02:38:21 Size: 131 KB |  |  |  |
| 11 | File Type: other File Desc: DHS Coverage Survey | File name: DOC 15 Timor-Leste_DHS_2009-10_Complete_Final_11-18-2010.zip Date/Time: 02.05.2011 02:26:34 Size: 3 MB |  |  |  |
| 12 | File Type: other File Desc: Preliminary Census Report 2010 | File name: DOC 16 Preliminary Census Results 2010 TL.pdf Date/Time: 03.05.2011 20:51:10 Size: 3 MB |  |  |  |
| 13 | File Type: Minutes of last three ICC/HSCC meetings * File Desc: | File name: DOC 7 Minutes,_EPI_NWG 2011.docx Date/Time:09.05.2011 20:49:41 Size: 68 KB |  |  |  |
| 14 | File Type: comprehensive Multi Year Plan - cMYP * File Desc: | File name: DOC 5 MYP-TLS_2011-2015 updated may 17.doc Date/Time: 19.05.2011 03:16:44 Size: 2 MB |  |  |  |
| 15 | File Type: cMYP Costing tool for financial analysis * File Desc: | File name: DOC 6 TL cMYP Costing 2011-2015 updated may 17.xls Date/Time: 19.05.2011 03:18:25 Size: 3 MB |  |  |  |
| 16 | File Type: Plan for NVS introduction (if not part of cMYP) File Desc: | File name: DOC 8 Hib_IntroPlan_Timor May 19.xlsx Date/Time: 19.05.2011 03:27:32 Size: 15 KB |  |  |  |