|  |  |  |  |  | [V2.7]. |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| GAVI Alliance. |  |  |  |  |  |  |  |
| Application Form for Country Proposals. |  |  |  |  |  |  |  |
| For Support to:. |  |  |  |  |  |  |  |
| Routine New Vaccines Support. Preventive Campaign Support. |  |  |  |  |  |  |  |
| Submitted by. |  |  |  |  |  |  |  |
| The Government of. |  |  |  |  |  |  |  |
| Gambia. |  |  |  |  |  |  |  |
| Date of submission: 8/30/2012. |  |  |  |  |  |  |  |
| Deadline for submission: 8/31/2012. |  |  |  |  |  |  |  |
| Select Start and End Year of your Comprehensive Multi-Year Plan (cMYP). |  |  |  |  |  |  |  |
| Start Year. | 2012. |  |  |  |  |  |  |
|  |  |  | End Year. | 2016. |  |  |  |
| Form revised in 2012. |  |  |  |  |  |  |  |
| (To be used with Guidelines of September 2012). |  |  |  |  |  |  |  |
| Please submit the Proposal using the online platform. https://AppsPortal.gavialliance.org/PDExtranet. |  |  |  |  |  |  |  |
| Enquiries to: proposals@gavialliance.org or representatives of a GAVI partner agency. The documents can be shared with GAVI partners, collaborators and general public. The Proposal and attachments must be submitted in English, French, Spanish, or Russian.. Note: Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline.. The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents will be shared with the GAVI Alliance partners and the general public.. |  |  |  |  |  |  |  |

GAVI ALLIANCE GRANT TERMS AND CONDITIONS. FUNDING USED SOLELY FOR APPROVED PROGRAMMES. The applicant country ("Country") confirms that all funding provided by the GAVI Alliance will be used and applied for the sole purpose of fulfilling the programme(s) described in the Country's application. Any significant change from the approved programme(s) must be reviewed and approved in advance by the GAVI Alliance. All funding decisions for the application are made at the discretion of the GAVI Alliance Board and are subject to IRC processes and the availability of funds.. AMENDMENT TO THE APPLICATION. The Country will notify the GAVI Alliance in its Annual Progress Report if it wishes to propose any change to the programme(s) description in its application.The GAVI Alliance will document any change approved by the GAVI Alliance, and the Country's application will be amended.. RETURN OF FUNDS. The Country agrees to reimburse to the GAVI Alliance all funding amounts that are not used for the programme(s) described in its application. The country's reimbursement must be in US dollars and be provided, unless otherwise decided by the GAVI Alliance, within sixty (60) days after the Country receives the GAVI Alliance's request for a reimbursement and be paid to the account or accounts as directed by the GAVI Alliance.. SUSPENSION/ TERMINATION. The GAVI Alliance may suspend all or part of its funding to the Country if it has reason to suspect that funds have been used for purpose other than for the programmes described in the Country's application, or any GAVI Alliance-approved amendment to the application.The GAVI Alliance retains the right to terminate its support to the Country for the programmes described in its application if a misuse of GAVI Alliance funds is confirmed.. ANTICORRUPTION. The Country confirms that funds provided by the GAVI Alliance shall not be offered by the Country to any third person, nor will the Country seek in connection with its application any gift, payment or benefit directly or indirectly that could be construed as an illegal or corrupt practice.. AUDITS AND RECORDS. The Country will conduct annual financial audits, and share these with the GAVI Alliance, as requested. The GAVI Alliance reserves the right, on its own or through an agent, to perform audits or other financial management assessment to ensure the accountability of funds disbursed to the Country.. The Country will maintain accurate accounting records documenting how GAVI Alliance funds are used. The Country will maintain its accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of GAVI Alliance funds. If there is any claims of misuse of funds, Country will maintain such records until the audit findings are final. The Country agrees not to assert any documentary privilege against the GAVI Alliance in connection with any audit.. CONFIRMATION OF LEGAL VALIDITY. The Country and the signatories for the Country confirm that its application, and Annual Progress Report, are accurate and correct and form legally binding obligations on the Country, under the Country's law, to perform the programmes described in its application, as amended, if applicable, in the APR.. CONFIRMATION OF COMPLIANCE WITH THE GAVI ALLIANCE TRANSPARANCY AND ACCOUNTABILITY POLICY. The Country confirms that it is familiar with the GAVI Alliance Transparency and Accountability Policy (TAP) and complies with the requirements therein.. USE OF COMMERCIAL BANK ACCOUNTS. The Country is responsible for undertaking the necessary due diligence on all commercial banks used to manage GAVI cash-based support. The Country confirms that it will take all responsibility for replenishing GAVI cash support lost due to bank insolvency, fraud or any other unforeseen event.. ARBITRATION. Any dispute between the Country and the GAVI Alliance arising out of or relating to its application that is not settled amicably within a reasonable period of time, will be submitted to arbitration at the request of either the GAVI Alliance or the Country. The arbitration will be conducted in accordance with the then-current UNCITRAL Arbitration Rules. The parties agree to be bound by the arbitration award, as the final adjudication of any such dispute. The place of arbitration will be Geneva, Switzerland. . The languages of the arbitration will be English or French.. For any dispute for which the amount at issue is US$ 100,000 or less, there will be one arbitrator appointed by the GAVI Alliance. For any dispute for which the amount at issue is greater than US $100,000 there will be three arbitrators appointed as follows: The GAVI Alliance and the Country will each appoint one arbitrator, and the two arbitrators so appointed will jointly appoint a third arbitrator who shall be the chairperson.. The GAVI Alliance will not be liable to the country for any claim or loss relating to the programmes described in the application, including without limitation, any financial loss, reliance claims, any harm to property, or personal injury or death. Country is solely responsible for all aspects of managing and implementing the programmes described in its application..

1. Application Specification Please specify for which type of GAVI support you would like to apply to..

Type of Support; Vaccine; Start Year; End Year; Preferred second presentation[1]. Routine New Vaccines Support; Rotavirus, 3 -dose schedule; 2013; 2016. Preventive Campaign Support; Meningogoccal, 10 dose(s) per vial, LIQUID; 2013; 2013.

[1] This "Preferred second presentation" will be used in case there is no supply available for the preferred presentation of the selected vaccine ("Vaccine" column). If left blank, it will be assumed that the country will prefer waiting until the selected vaccine becomes available..

2. Table of Contents.

1. Application Specification. 2. Table of Contents. 3. Executive Summary. 4. Signatures. 4.1. Signatures of the Government and National Coordinating Bodies. 4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation. 4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation. 4.1.3. The Inter-Agency Coordinating Committee for Immunisation. 4.2. National Immunization Technical Advisory Group for Immunisation. 4.2.1. The NITAG Group for Immunisation. 5. Immunisation Programme Data. 5.1. Basic facts. 5.2. Baseline and Annual Targets (NVS Routine Support). 5.3. Baseline and Annual Targets for Preventive Campaign(s). 5.3.1 Baseline and annual targets (Meningogoccal campaign). 6. New and Under-Used Vaccines (NVS Routine). 6.1. Assessment of burden of relevant diseases (if available). 6.2 Requested vaccine (Rotavirus, 3 -dose schedule). 6.2.1 Co-financing information. 6.2.2 Specifications of vaccinations with new vaccine. 6.2.3 Portion of supply to be procured by the country (and cost estimate, US$). 6.2.4 Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$). 6.2.5 New and Under-Used Vaccine Introduction Grant. 7. NVS Preventive Campains. 7.1. Assessment of burden of relevant diseases related to campaigns (if available). 7.2 Requested for Meningogoccal, 10 dose(s) per vial, LIQUID campaign support. 7.2.1 Summary for Meningogoccal campaign support. 7.2.2 Grant Support for Operational Costs of the Meningogoccal Campaign. 8. Procurement and Management. 8.1. Procurement and Management of New and Under-Used Vaccines Routine. 8.2. Procurement and Management for NVS Preventive Campaign(s). 8.2.1 Procurement and Management for Meningogoccal, 10 dose(s) per vial, LIQUID campaign. 8.3. Vaccine Management (EVSM/EVM/VMA). 9. Additional Comments and Recommendations from the National Coordinating Body (ICC/HSCC). 10. Attachments. 11. Annexes. Annex 1 - NVS Routine Support. Annex 1.1 Rotavirus, 3 -dose schedule. Table Annex 1.1 A Rounded up portion of supply that is procured by the country and estimate of relative costs in US$. Table Annex 1.1 B Rounded up portion of supply that is procured by GAVI and estimate of relative costs in US$. Table Annex 1.1 C Summary table for vaccine Rotavirus, 3 -dose schedule. Table Annex 1.1 D Estimated numbers for Rotavirus, 3 -dose schedule, associated injection safety material and related co-financing budget (page 1). Annex 2 - NVS Routine – Preferred Second Presentation. Annex 3 - NVS Preventive campaign(s). Table Annex 3.1 C Summary table for vaccine Meningogoccal, 10 dose(s) per vial, LIQUID. Table Annex 3.1 D Estimated numbers for Meningogoccal, 10 dose(s) per vial, LIQUID, associated injection safety material and related co-financing budget (page 1). Annex 4. Table Annex 4A: Commodities Cost. Table Annex 4B: Freight cost as percentage of value. Table Annex 4C: Low - Minimum country's co-payment per dose of co-financed vaccine.. Table Annex 4D: Wastage rates and factors. Table Annex 4E: Vaccine maximum packed volumes. 12. Banking Form.

3. Executive Summary.

Please provide a summary of your country's proposal, including the following the information:. l; For each specific request, NVS routine support or NVS campaign :. ¡; The duration of support. ¡; The total amount of funds. ¡; Details of the vaccine(s), if applicable. l; Relevant baseline data, including:. ¡; DTP3 and Measles coverage data (as reported on the WHO/UNICEF Joint Reporting Form). ¡; Birth cohort, targets and immunisation coverage by vaccines. l; Country preparedness. ¡; Summary of EVM assessment. l; The nature of stakeholders' participation in developing this proposal. ¡; Inter-Agency Coordinating Committee. EXECUTIVE SUMMARY FOR ROTA VIRUS VACCINE In The Gambia, a hospital-based rota virus surveillance was conducted at Royal Victoria Teaching Hospital (RVTH) in children under five years of age with diarrhoea within 48 hours of admission. Of the 536 admissions, 187 (34.9%) had acute diarrhoea, out of which 148 (79.1%) had their stools tested. Among those tested, 111 (75%) were positive for rota virus and 90 (81%) were twelve months and below. There were 14 diarrhoeal deaths ; Case Fatality of 7.5% and 7 deaths were positive for Rota virus. In addition, a population-based surveillance has been conducted in the South Bank of Upper River Region (URR) between December 2007 and Mid 2010. This population based study used the passive surveillance system to identify moderate to severe diarrhoea in children aged 0-59 months at 6 health centers across the South Bank of URR using the WHO criteria. A total of 29, 583 under five children sought care at different health centers in 2008, 33,116 in 2009 and 31,608 in 2010. In 2008, 10.6% (3159/29583) of presentations were due to diarrhoea, 7.1 % (2377/33116) in 2009, and 6.5% (2065/31,608) in 2010. Rota virus was the most common cause of moderate to severe diarrhoea (35%) with a peak in the dry cool months of December to February. Rota virus caused 43% of diarrhoea in those aged 0-11 months, 34% in those aged 12-23 months, and 25% in those aged 24-59 months. The objective of introducing Rota virus vaccine is to vaccinate 94% of children aged 2-11 months by the end of 2016. The preferred vial presentation is one-dose vial fully liquid. The total birth cohort for the first year is 75,775 with coverage of 92%. The country had attained 97% and 91% coverage rates for Penta 3 and Measles in 2011 respectively. Key among these achievements include the continuous availability of vaccines and other supplies at all levels, geographical access and committed staff to deliver immunization services. Compared to other countries within the sub region, The Gambia has a good track record of high immunization coverage due mainly to increased access with about 95% of the population living within a radius of 5-8kms and service utilization. Furthermore,The Gambia has added Hepatitis B (1990), Haemophillus Influenzae type b (1997), Pneumoccocal conjugate vaccine (2009) and Measles Second Dose (2012) to the traditional vaccines. It is therefore evident that introducing new vaccines is not a new concept in the country. The Post Introduction Evaluation (PIE) conducted in 2010 showed that lessons and experiences exist in the country to serve as a guide in future introductions. Though experiences from the past exist, the country will adequately plan in order to successfully introduce any new vaccines. Adequate preparations will be made for the introduction of this new vaccine. The findings of the Effective Vaccine Management (EVM) revealed that The Gambia has adequate storage capacity at national and in some of the regions. There is a national cold room that houses vaccines at central level, whereas the regions are equipped with freezers and ice lined refrigerators. As part of the EVM recommendations, UNICEF procured cold chain equipment to expand the vaccine storage capacity in these areas. Like other new vaccines, the government will pay US$0.132 per dose of the vaccine as its co-financing contribution. This proposal was developed by a technical team comprising of members from MoH&SW and partners. This was then presented to ICC for review and endorsement. EXECUTIVE SUMMARY FOR PREVENTIVE MEN.A. CAMPAIGN Meningoccocal Meningitis/cerebro-spinal meningitis is a contagious bacterial infection occurring sporadically throughout the world. Several different bacteria can cause the disease; Neisseria meningitidis is the one with potential to cause large epidemics. Twelve sero types have been identified, six of which (A.B,C, W135, X and Y) cause major epidemics in the Meningitis belt. In The Gambia, epidemics records have shown sero type A as the predominant type responsible for epidemics. However, of recent W135 has been responsible for epidemics ,for example, as of August 2012, this strain cause 175 cases and 9 deaths. In 1996/97 epidemic seasons, The Gambia experienced the worst epidemics causing 1685 cases and 222 deaths with a Case Fatality Rate (CFR) of 13.1%. During these seasons, the Upper River Region (URR), one of the high risk regions recorded 1390 cases and 168 deaths with a CFR of 12%. Furthermore, from November 2000 to March 2001, 137 cases including 21 deaths were recorded. Increased prevalence over the years, epidemiological shift, high susceptible populations coupled with globalization are major concerns. In addition, inadequate capacity of the health care system in relation to timely detection, diagnosis, management and treatment of cases as well as high poverty levels in The Gambia continue to hamper efforts in the control and prevention of Meningitis. In this regard, effective surveillance and mass vaccination campaigns remain to be the most cost effective strategies to eliminate Meningitis epidemic in The Gambia. The objective of conducting this campaign (Meningoccocal A conjugate) is to reduce the occurrence of Meningitis epidemic that occasionally hits The Gambia which stretches from Ethiopia in the East to Senegal and Gambia in the West. The preferred vial presentation is 10-dose vial fully liquid. The campaign will target the age group 1-29 years. Evidence from the Meningitis A Vaccine Trial indicates that the conjugate vaccine induces a higher and more lasting immunity in this age group. A total of 1,253,546 (70%) people out of a total population of 1.7 million (projected from the 2003 Pop. census) country wide have been targeted for the campaign.. The campaign is scheduled to take place in November 2013. The country had attained 97% and 91% coverage rates for Penta 3 and Measles in 2011 respectively. Key among these achievements include the continuous availability of vaccines and other supplies at all levels, geographical access and committed health staff to deliver immunization services. Compared to other countries within the sub region, The Gambia has a good track record of high immunization coverage due mainly to improved access with about 95% of the population living within the radius of 5-8kms and service utilization. Furthermore, The Gambia has added Hepatitis B (1990), Heamophillus Influenzea Type b (1997), Pneumo (2009) and Measles Second Dose (2012) to the traditional vaccines. It is therefore evident that introducing new vaccines is not a new concept in the country. The Post Introduction Evaluation conducted in 2010 showed that lessons and experiences exist in the country to serve as a guide in future introductions. Though experiences from the past exist, the country will prepare adequately in order to successfully introduce any new vaccine including the mass vaccination campaign. The findings of the Effective Vaccine Management (EVM) assessment revealed that The Gambia has adequate storage capacity at national and in some of the regions. There is a national cold room that houses vaccines at central level, whereas the regions are equipped with freezers and ice-lined refrigerators. As part of the EVM recommendations, UNICEF procured cold chain equipment to expand the vaccine storage capacity in these areas. A total amount of US$674,416.23 will be required for the meningitis campaign. GAVI will provide 50% of the operational cost whilst the other part will be mobilized by government and other partners. The cost per person for the operation is US$0.55. This proposal was developed by a technical team comprising members from the Ministry of Health & Social Welfare and partners. This was then forwarded to the ICC for review and endorsement..

| 4. Signatures. |  |  |
| --- | --- | --- |
| 4.1. Signatures of the Government and National Coordinating Bodies. |  |  |
| 4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation. |  |  |
| The Government of Gambia would like to expand the existing partnership with the GAVI Alliance for the improvement of the infants routine immunisation programme of the country, and specifically hereby requests for GAVI support for. |  |  |
|  | Rotavirus, 1 dose(s) per vial, ORAL routine introduction. Meningogoccal, 10 dose(s) per vial, LIQUID preventive campaigns. |  |
| The Government of Gambia commits itself to developing national immunisation services on a sustainable basis in accordance with the Comprehensive Multi-Year Plan presented with this document. The Government requests that the GAVI Alliance and its partners contribute financial and technical assistance to support immunisation of children as outlined in this application.. |  |  |
| Table(s) 6.2.4 in the NVS Routine section of this application shows the amount of support in either supply or cash that is required from the GAVI Alliance. Table(s) 6.2.3 of this application shows the Government financial commitment for the procurement of this new vaccine (NVS support only).. |  |  |
| Following the regulations of the internal budgeting and financing cycles the Government will annually release its portion of the co-financing funds in the month of January.. |  |  |
| The payment for the first year of co-financed support will be around October 2013 for Meningogoccal, 10 dose(s) per vial, LIQUID, Rotavirus, 1 dose(s) per vial, ORAL.. |  |  |
| Please note that this application will not be reviewed or approved by the Independent Review Committee (IRC) without the signatures of both the Minister of Health and Minister of Finance or their delegated authority.. |  |  |
| Minister of Health (or delegated authority); Minister of Finance (or delegated authority). Name; Mrs. Fatim Badgie; Name; Mr. Abdou Kolley. Date; Date. Signature; Signature. |  |  |
| This report has been compiled by (these persons may be contacted in case the GAVI Secretatiat has queries on this document):. |  |  |
| Full name; Position; Telephone; Email. Mrs. Yamundow Lowe- Jallow; EPI Manager; (220) 9917719; ylowe_jallow@hotmail.com. |  |  |
| 4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation. |  |  |
| We the members of the ICC, HSCC, or equivalent committee [1] met on the 22/08/2012 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.. |  |  |
| [1] Inter-agency Coordinating Committee or Health Sector Coordinating Committee, or equivalent committee which has the authority to endorse this application in the country in question.. |  |  |
| The endorsed minutes of this meeting are attached as document number 4.. |  |  |
| Name/Title*; Agency/Organisation*; Signature. Dr. Adama Demba, Ag. Director of Health Services; Ministry of Health & Social Welfare. Dr. Kujay Manneh, Country Director; Action Aid-The Gambia. Dr. Makie Taal, Permanent Secretary; Ministry of Health & Social Welfare. Dr. Thomas Sukwa, Country Representative; WHO Country Office. Mr. Bai Cham, Secretray General; Gambia Red Cross Society. Mr. Eustace Cassell, Country Director; Child Fund. Mr. Sanna Jawara, Chief Public Health Officer; Ministry of Health & Social Welfare. Mrs. Aichatou Diawara-Flambert, Country Representative; UNICEF Country Office. Mrs.Oumou Tall, Chairperson-Polioplus; Rotary International. Prof. Tumani Corrah, Unit Director; Medical Research Council. |  |  |
| 4.1.3. The Inter-Agency Coordinating Committee for Immunisation. |  |  |
| Agencies and partners (including development partners and NGOs) supporting immunisation services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC, HSCC, or equivalent committee). The ICC, HSCC, or equivalent committee is responsible for coordinating and guiding the use of the GAVI NVS routine support and/or campaign support. Please provide information about the ICC, HSCC, or equivalent committee in your country in the table below.. |  |  |
| Profile of the ICC, HSCC, or equivalent committee. |  |  |
| Name of the committee; Inter agency Cordinating Committee. Year of constitution of the current committee; 1997. Organisational structure (e.g., sub-committee, stand-alone); STAND ALONE. Frequency of meetings; QUARTERLY. |  |  |
| Composition. |  |  |
| Function; Title / Organisation; Name. Chair; Hon. Minister of Health, Ministry of Health & Social Welfare; Ms. Fatim BADJIE. Secretary; The EPI Manager, EPI Unit; Mrs. Yamundow LOWE-JALLOW. Members; Permanent Secretary, MoH&SW; Dr. Makie TAAL. Ag. Director, MoH&SW; Dr. Adama DEMBA. Country Representative, WHO Country Office; Dr. Thomas SUKWA. Country Representative, UNICEF Country Office; Mrs. Aichatou DIAWARA-FLAMBERT. Country Director, Action Aid; Dr. Kujay MANNEH. Country Director, Child Fund; Mr. Eustace CASSELL. Secretray General, Gambia Red Cross Society; Mr. Bai CHAM. Unit Director, MRC; Prof. Tumani CORRAH. Chairperson, Polio Plus, Rotary International; Mrs. Oumou TALL. Chief Public Health Officer, MoH&SW; Mr. Sanna JAWARA. |  |  |
| Major functions and responsibilities of the ICC/HSCC:. |  |  |
| i) Mobilize resources for the EPI programme ii) Review and support work plans such as NIDs, EPI annual plans, cMYP etc iii) Review and endorse the use of GAVI funds at regular intervals iv) Ensure that the EPI Programme receives the required technical and political support for effective immunization service delivery v) Address technical issues as and when they arise such as introduction of new vaccines, strengthening immunization services etc. |  |  |
| Three major strategies to enhance the committee's role and functions in the next 12 months. |  |  |
| 1.; Conducting quarterly meetings with a view to mobilizing resources for the EPI programme. 2.; Reviewing the EPI operational plans as well as conducting supportive supervisory visits to the facilities annually. 3.; Organizing refresher orientation on their terms of reference and responsibilities. |  |  |
| 4.2. National Immunization Technical Advisory Group for Immunisation. |  |  |
| (If it has been established in the country). |  |  |
| We the members of the NITAG met on the to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.. |  |  |
| The endorsed minutes of this meeting are attached as document number 4.. |  |  |

4.2.1. The NITAG Group for Immunisation.

Profile of the NITAG.

Name of the NITAG; Not Applicable. Year of constitution of the current NITAG. Organisational structure (e.g., sub-committee, stand-alone); Not Applicable. Frequency of meetings; Not Applicable.

Composition.

Function; Title / Organisation; Name. Chair; Not Applicable; Not applicable. Secretary; Not Applicable; Not Applicable. Members; Not Applicable; Not Applicable.

Major functions and responsibilities of the NITAG.

Not Applicable.

Three major strategies to enhance the NITAG's role and functions in the next 12 months.

1.; Not Applicable. 2.; Not Applicable. 3.; Not Applicable.

5. Immunisation Programme Data.

5.1. Basic facts.

Please complete the tables below, using data from available sources. Please identify the source of the data, and the date. Where possible use the most recent data and attach the source document..

▪; Please refer to the Comprehensive Multi-Year Plan for Immunisation (cMYP) (or equivalent plan) and attach a complete copy (with an Executive Summary) as DOCUMENT NUMBER : 6. ▪; Please attach relevant Vaccine Introduction Plans as DOCUMENT NUMBER : 7. ▪; Please refer to the two most recent annual WHO/UNICEF Joint Reporting Forms (JRF) on Vaccine Preventable Diseases. ▪; Please refer to Health Sector Strategy documents, budgetary documents, and other reports, surveys etc, as appropriate..

For the year 2011 (most recent; specify dates of data provided).

Figure; Year; Source. Total population; 1,734,278; 2012; Projected from 2003 Census figures. Infant mortality rate (per 1000); 75; 2011; 2003 Census. Surviving infants[1]; 73,782; 2012; cMYP 2012-2016. GNI per capita (US$); 740; 2009; WB Report for 2010. Total Health Expenditure (THE) as a percentage of GDP; 8; %; 2010; 2010 Government Budget Estimates. General government expenditure on health (GGHE) as % of General government expenditure; 50; %; 2010; Extrapolated from 2005 NHA.

[1] Surviving infants = Infants surviving the first 12 months of life.

Please provide some additional information on the planning and budgeting context in your country. The planning cycle for the government is from January to December every year. Annual plans are sent to the Ministry of Finance for funding.. Please indicate the name and date of the relevant planning document for health. The relevant planning documents for the Health Ministry are the Health Policy and the strategic plan, 2012 -2016. Is the CMYP (or updated Multi-Year Plan) aligned with the document (timing, content, etc.). Yes.. Please indicate the national planning budgeting cycle for health. January to December every year. Please indicate the national planning cycle for immunisation. January to December every year. Please indicate if sex disaggregated data (SDD) is used in immunisation routine reporting systems. No. However, the routine immunization data collection tools have just been reviewed to capture sex disagregated data. Please indicate if gender aspects relating to introduction of a new vaccine have been addressed in the introduction plan. In The Gambia, there is no gender related barriers to immunization services. Please describe any recent evidence of socio-economic and/or gender barriers to the immunisation programme through studies or surveys?. No study or survey had revealed socio-economic and gender-related barriers to immunization services. Country should provide an outline of all preparatory activities for vaccine(s) introduction. The pre-implementation activities for the introduction of the Rota Virus vaccine will include the followings: i) Advocacy & Communication: Advocacy and communication play a key role in involving and sensitizing the Gambian Population particularly decision/policy makers and women in the delivery and utilization of immunization services. In this regard, the social mobilization activities will begin with the sensitization of regional and district authorities as well as Technical Advisory Committees (TACs) members, who will in turn sensitize their respective communities. During these regional meetings, the critical role for community sensitization will be emphasized and governors will be encouraged to help in mobilizing other resources including vehicles in their respective regions. Furthermore, meetings will be organized for christian and muslim religious leaders. Radio and television programmes will also be organized in different radio stations in different languages across the country. Communication materials will be produced and distributed to the communities. Finally, series of ICC meetings will be conducted to brief and request for support from members. ii) Data Management: The data collection tools such as tally books, registers, clinic cards and monthly returns would be reviewed and finalized to include the Rota vaccine in consultation with stakeholders at regional and health facility levels. The existing routine data collection and reporting system will be used. In addition, the Comprehensive Multi year Plan and the immunization policy will be reviewed and finalised to include Rota vaccine iii) Cold Chain & Logistics: The EPI Programme has a good network of the cold chain system. The cold chain technicians will carry out preventive maintenance of the cold chain equipment country wide before the introduction of the Rota vaccine. vi) Waste Management: There are incinerators built in 2010 (one in each region) for the management of immunization wastes. These incinerators will be fully utilized during the introduction of the vaccine. However, some of these incinerators are in a state of disrepair and would be rehabilitated before the introduction of the vaccine. v) Central Level Monitoring: The central EPI team will conduct a country wide supervisory visit to assess the state of preparedness at regional and health facility levels. vi) Regional Level Monitoring: Each region will carry out regular supervisory visit to the health facilities to assess the state of preparedness. vii) Training: Training of trainers will be conducted at central level including health training institutions followed by cascade trainings at service delivery level. viii) Launching: There would be launching ceremonies at central and regional levels. These would be graced by authorities at national and regional levels. The pre implementation activities for the Men.A. preventive campaign will include the followings: i) Advocacy and Communication: Advocacy and communication play a key role in involving and sensitizing the Gambian population particularly decision/policy makers and community members on the importance of the campaign. In this regard, the social mobilization activities will begin with sensitization of regional and district authorities as well as the Technical Advisory Committee (TAC) members, who will in turn sensitize their respective communities. During these regional meetings, the critical role for community sensitization will be emphasized and governors will be encouraged to help in mobilizing other resources including vehicles in their respective regions. Furthermore, meetings will be organized for christian and muslim leaders. Radio and television programmes will also be organized in different radio stations in different languages across the country. Communication materials would be produced and distributed to the communities. Finally, series of ICC meetings would be conducted to brief and request for support from members. ii) Data Management: The data collection tool will be reviewed and finalized in consultation with stakeholders at regional and health facility levels. During the campaign, the district data will be collected and send by supervisor to the regional level for onward transmission to the central level.The central level will then analyze the data collected and sent to WHO sub-regional office in Burkina Faso daily. iii) Micro planning: The Regional Health Teams will conduct micro planning sessions with basic health facilities at regional level. This exercise would identify the target populations, vehicles, motor bikes, cold chain requirements and all other needed resources for effective and efficient mas vaccination campaign. These regional plans would then be finalized with the regional staff at central level before implementation. iv) Cold Chain: The EPI Programme has in place a good network of cold chain equipment. The cold chain technicians will carry out preventive maintenance of he equipment country wide before the campaign. v) Waste Management: There are incinerators built (one in each region) for the management of immunization waste. These incinerators will be fully utilized for the campaign. vi)Central Level Monitoring: The central EPI team will conduct a country wide supervisory visit to assess the state of preparedness at regional and health facility levels. The team will also visit the regions during the training of personel for the campaign. vii) Regional Level Monitoring: Each region will carry out regular supervisory visit to the health facilities to assess the state of preparedness. viii) Training: Training of trainers (ToT) for central level supervisors will be conducted a week before the campaign; who will conduct cascade trainings for supervisors and vaccinators at regional and district levels. viiii) Launching: There would be launching ceremonies at central and regional levels.These would graced by authorities at national and regional levels..

5.2. Baseline and Annual Targets (NVS Routine Support)

Please refer to cMYP pages to assist in filling-in this section..

Number; Base Year; Baseline and Targets; Baseline and Targets; Baseline and Targets; Baseline and Targets. 2012; 2013; 2014; 2015; 2016. Total births; 79,678; 81,830; 84,039; 86,308; 88,639. Total infants’ deaths; 5,896; 6,055; 6,219; 6,387; 6,648. Total surviving infants; 73,782; 75,775; 77,820; 79,921; 81,991. Total pregnant women; 73,782; 75,772; 77,820; 79,921; 82,080. Target population vaccinated with BCG; 75,695; 78,557; 80,678; 84,582; 87,753. BCG coverage; 95 %; 96 %; 96 %; 98 %; 99 %. Target population vaccinated with OPV3. OPV3 coverage; 98 %; 98 %; 99 %; 99 %; 99 %. Number of infants vaccinated (to be vaccinated) with DTP1; 73,045; 75,017; 77,821; 79,122; 81,171. Number of infants vaccinated (to be vaccinated) with DTP3; 72,307; 74,259; 77,042; 79,122; 81,171. DTP3 coverage; 98 %; 98 %; 99 %; 99 %; 99 %. Wastage[1] rate in base-year and planned thereafter (%) for DTP; 15; 15; 15; 10; 10. Wastage[1] factor in base-year and planned thereafter for DTP; 1.18; 1.18; 1.18; 1.11; 1.11. Rotavirus coverage; 0 %; 90 %; 91 %; 92 %; 94 %. First Presentation: Rotavirus, 3-dose schedule. Wastage[1] rate in base-year and planned thereafter (%); 0; 5; 5; 5; 5. Wastage[1] factor in base-year and planned thereafter (%); 1.00; 1.05; 1.05; 1.05; 1.05. Maximum wastage rate value for Rotavirus, 3-dose schedule; 5 %; 5 %; 5 %; 5 %; 5 %. Target population vaccinated with 1st dose of Measles; 67,880; 70,471; 73,152; 75,926; 77,072. Measles coverage; 92 %; 93 %; 94 %; 95 %; 94 %. Number of infants vaccinated (to be vaccinated) with 1st dose of TT+; 56,813; 59,104; 61,478; 63,937; 69,692. TT+ coverage; 77 %; 78 %; 79 %; 80 %; 85 %. Annual DTP Drop out rate [ ( DTP1 – DTP3 ) / DTP1 ] x 100; 1 %; 1 %; 1 %; 0 %; 0 %.. [1] Number of infants vaccinated out of total births. [2] Number of infants vaccinated out of total surviving infants. [3] Indicate total number of children vaccinated with either DTP alone or combined. [4] Number of pregnant women vaccinated with TT+ out of total pregnant women. [5] The formula to calculate a vaccine wastage rate (in percentage): [ ( A - B ) / A ] x 100. Whereby: A = the number of doses distributed for use according to the supply records with correction for stock balance at the end of the supply period; B = the number of vaccinations with the same vaccine in the same period...

| 5.3. Baseline and Annual Targets for Preventive Campaign(s).. |  |
| --- | --- |
| 5.3.1 Baseline and annual targets (Meningogoccal campaign). Cohort for Meningogoccal is population 1-29 years old.. Table 5.3.1 Baseline NVS preventive campaign figures for Meningogoccal.. Number; Base Year; Baseline and Targets. 2012; 2013. Total births; 79,678; 81,830. Total population 1-29 years old; 1,210,566; 1,243,251. Target population vaccinated with Meningococcal; 0; 1,118,926. Meningococcal (campaign) coverage (%) [1]; 0.00 %; 90.00 %. Wastage rate in base year and thereafter (%) for Meningococcal (campaign); 0; 10. Wastage factor in base year and thereafter for Meningococcal; 1; 1.11.. [1] Number of persons vaccinated out of total births... |  |

6. New and Under-Used Vaccines (NVS Routine)

6.1. Assessment of burden of relevant diseases (if available).

Disease; Title of the assessment; Date; Results.

If new or under-used vaccines have already been introduced in your country, please give details of the lessons learned from previous introduction(s) specifically for: storage capacity, protection from accidental freezing, staff training, cold chain, logistics, coverage and drop-out rates, wastage rate, etc., and suggest action points to address them..

Lessons Learned; Action Points. Community Sensitization - Sufficient sensitization provided adequate awareness of the new vaccines that were introduced -Posters, leaflets and banners were important tools for awareness creation; -Community sensitization activities planned and implemented prior to the vaccine introduction. Staff orientation - Training manuals and guidelines on the new vaccines were very useful in orienting staff on the vaccines that were introduced; - Guidelines and manuals reviewed, finalised, printed and distributed to staff before the introduction of the new vaccines. Data Collection Tools -The revision of existing data collection tools proved helpful; -Data collection tools were reviewed and finalised ahead of the introduction of the new vaccines. Cold Chain There was sufficient storage capacity at all levels to accomodate the new vaccines; -Cold chain assessment conducted before the new vaccine introduction. Political Support -Strong political support led to the successful introduction of the new vaccines -Government fulfilled its co-financing obligations; -Advocacy meeting for political support were organised well before the new vaccines were introduced. Committed Staff Strong staff commitment at all levels contributed to the successful introduction of new vaccines; -Staff were provided with incentives to boost morale. Surveillance strengthened surveillance system to include the new vaccines and AEFI monitoring and reporting has been critical; The surveillance system was strengthened prior to the introduction of new vaccine. Waste Management Improved waste management system was key to the introduction of new vaccines; New incinerators were built to replace the old ones. Monitoring regular monitoring and supervision ensured smooth new vaccine introduction; monitoring and supervisory check lists were available at all levels.

Please list the vaccines to be introduced with support from the GAVI Alliance (and presentation).

The vaccine to be introduced is rota virus vaccine in one dose vial fully liquid.

6.2. Requested vaccine (Rotavirus, 3 -dose schedule) As reported in the cMYP, the country plans to introduce Rotavirus, using Rotavirus, 3 -dose schedule.. 6.2.1. Co-financing information. If you would like to co-finance higher amount than minimum, please overwrite information in the Your co-financing row... Country group; Low.. Year 1; Year 2; Year 3; Year 4. 2013; 2014; 2015; 2016. Minimum co-financing; 0.13; 0.13; 0.13; 0.13. Your co-financing (please change if higher); 0.13; 0.13; 0.13; 0.13.. 6.2.2. Specifications of vaccinations with new vaccine.. Data from; Year 1; Year 2; Year 3; Year 4. 2013; 2014; 2015; 2016. Number of children to be vaccinated with the first dose; Table 5.2; #; 69,713; 72,373; 75,126; 78,711. Number of children to be vaccinated with the third dose; Table 5.2; #; 68,198; 70,816; 73,527; 77,072. Immunisation coverage with the third dose; Table 5.2; #; 90.00 %; 91.00 %; 92.00 %; 94.00 %. Country co-financing per dose [1]; Table 6.2.1; $; 0.132; 0.132; 0.132; 0.132.. [1] Total price per-dose includes vaccine cost, plus insurance, etc....

6.2.3. Portion of supply to be procured by the country (and cost estimate, US$)... 2013; 2014; 2015; 2016. Number of vaccine doses; #; 9,900; 8,300; 8,600; 9,100. Number of AD syringes; #; 0; 0; 0; 0. Number of re-constitution syringes; #; 0; 0; 0; 0. Total value to be co-financed by country; $; 36,500; 30,500; 32,000; 33,500... 6.2.4. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$).. 2013; 2014; 2015; 2016. Number of vaccine doses; #; 264,700; 221,900; 230,300; 241,800. Number of AD syringes; #; 0; 0; 0; 0. Number of re-constitution syringes; #; 0; 0; 0; 0. Total value to be co-financed by country; $; 973,000; 815,500; 846,500; 888,500....

6.2.5. New and Under-Used Vaccine Introduction Grant.. Please indicate in the tables below the full costs/needs and how the one-time Introduction Grant [1] will be used to support the costs of vaccine introduction and critical pre-introduction activities (refer to the cMYP). GAVI’s support may not be enough to cover the full needs so please indicate in the table below how much and who will be complementing the funds needed.. Calculation of lump-sum for the Rotavirus, 3 -dose schedule.. Year of New Vaccine Introduction; Births (from Table 5.2); Share per Birth in US$; Total in US$. 2013; 81,830; 0.80; 100,000.. [1] The Grant will be based on a maximum award of $0.80 per infant in the birth cohort with a minimum starting grant award of $100,000.. Cost (and finance) to introduce the Rotavirus, 3 -dose schedule US$.. Cost Category Full needs for new vaccine introduction in US$; Funded with GAVI introduction grant in US$. Training; 18,500; 18,500. Social Mobilization, IEC and advocacy; 15,500; 15,500. Cold Chain Equipment & Maintenance; 20,000; 20,000. Vehicles and Transportation; 10,000; 10,000. Programme Management; 3,579; 3,579. Surveillance and Monitoring; 22,421; 22,421. Human Resources; 0; 0. Waste Management; 10,000; 10,000. Technical Assistance; 0; 0. Other (please specify). 0; 0. Total; 100,000; 100,000..... Please describe others sources of funding if available to cover your full needs.. If there are financial gaps during the introduction of the vaccine, these would be provided by government and other partners...

7. NVS Preventive Campains

7.1. Assessment of burden of relevant diseases related to campaigns (if available).

Disease; Title of the assessment; Date; Results. Meningitis; No assessment was conducted.

If Meningogoccal vaccines have already been introduced in your country during campaigns, please give details of the lessons learned from previous introduction(s) specifically for: storage capacity, protection from accidental freezing, staff training, cold chain, logistics, coverage and drop-out rates, wastage rate, etc., and suggest action points to address them..

Lessons Learned; Action Points. Community Sensitization - Sufficient sensitization provided adequate public awareness on the campaign -Leaflets, banners and posters were important tools for campaign awareness creation; Community sensitization activities planned and implemented prior to the campaigns. Training -Standardised training materials proved very helpful in the preparation of health workers for the campaign; -Guidelines prepared, printed and distributed before the campaign -Adequate training of staff (vaccine administration, injection safety, data management, AEFI, Cold chain) conducted. Data Management -The revision of the existing data collection tools proved very positive; -All data collection tools were revised before the campaign. Cold Chain -There was sufficient storage capacity at national and regional levels to handle the vaccine; -Cold chain assessment conducted before the campaign. Political Support -Strong political support led to a successful implementation of the campaign -Political leaders used multiple public fora to create awareness of the campaign; -Advocacy meetings for political support were organized well before the campaign. Committed Staff -Strong national, regional and health facility staff commitment contributed to the high success of the campaign; - Staff were provided with incentives to boost morale. Surveillance -Strong surveillance system with lab component facilitated the effective monitoring of AEFI during and after the campaign; -The surveillance system was strengthened prior to the campaign to measure disease burden and impact - AEFI focal persons identified at all levels. Waste Management The waste management system was strengthened to accomodate the waste generated from the campaign.; -Incinerators were built before the campaign. -A national focal person and incinerator attendants were identified. Monitoring -regular monitoring and supervision ensured quality campaigns; -Plans to monitor and supervise all levels were in place prior to the campaign.

7.2.Requested for Meningogoccal, 10 dose(s) per vial, LIQUID campaign support 7.2.1. Summary for Meningogoccal campaign support. Please give a summary of the cMYP and/or the Meningogoccal, 10 dose(s) per vial, LIQUID campaign introduction plan sections that refer to the introduction of Meningogoccal, 10 dose(s) per vial, LIQUID campaign. Outline the key points that informed the decision-making process (data considered etc):. Meningoccocal Meningitis/cerebro-spinal meningitis is a contagious bacterial infection occurring sporadically throughout the world. In Africa, major epidemics have been occurring over the past hundred years. Most of them have been attributed to sero type A within the belt. However, the largest burden of the disease is due to cyclic epidemic in the African Meninigitis belt, which streches from Ethiopia in the East to Senegal and the Gambia in the West. From 1996 to 1997, the largest epidemics in history swept across causing 250,000 cases with an estimated 25,000 deaths and disability in 50,000 people. Several different bacteria can cause the disease; Neisseria Meningitidis is the one with the potential to cause large epidemics. Twelve sero types have been identified, six of which (A,B,C,W135,X and Y) have been responsible for epidemics. In The Gambia, epidemic records have shown sero type A as the predominant type responsible for epidemics. For example as of August 2012, this strain caused 175 cases and 9 deaths. In 1996/7 epidemic seasons, The Gambia experienced the worst epidemics causing 1685 cases and 222 deaths with a case fatality rate (CFR) of 13.1%. During this season, the Upper River Region; one of the high risk regions recorded 1390 cases and 168 deaths with a case fatality rate of 12%. Furthermore, from November 2000 to March 2001, 137 cases including 21 deaths were recorded. Increased prevalence over the years, epidemiological shift, high susceptible populations coupled with globalization are major concerns. In addition, inadequate capacity of the health care system in relation to timely detection, diagnosis, management and treatment of cases as well as high poverty levels in The Gambia continue to hamper efforts in the control and prevention of Meningitis. In this regard, effective surveillance and mass vaccination campaigns remain to be the most effective strategies to eliminate meningitis epidemics in The Gambia. The aforementioned evidence coupled with the existence of a strong national immunization programme as well as availability of safe Man. A Vaccine, led to the WHO recommending the conduct of Meningoccocal mass vaccination campaign targeting those aged 1-29 years before its inclusion into the national immunization schedule of member countries; hence the Gambia's application for the conduct of the Meningoccocal mass vaccination campaign in November 2013.. Please summarise (1) the waste management plan and (2) the cold chain capacity and readiness to accommodate new vaccines, stating how the cold chain expansion (if required) will be financed, and when it will be in place.Please indicate if the supplies for the campaign will have any impact in the shipment plans for your routine vaccines and how it will be handled:. Injection Safety: This is assured by the use of AD Syringes. Bundling will continue to be implemented at all levels. The quality of vaccines to be used will continue to be a key priority and as such UNICEF procurement system would be used. Waste Management: New improved waste disposal units were constructed in all the six health regions (one in each region) in the country for the management of wastes. Sharps are initially disposed off in safety boxes at the injection site and are later transported to the incineration sites by the respective health facility staff and in some instances by the regional health teams during supervision. There are incinerator attendants in each region for the management of the sharps under the supervision of the regional health teams. Cold Chain Capacity: The current cold chain capacity in the country is adequate to support the Meningitis campaign. There is a walk-in cold room at the central level with a gross capacity of 25,000 litres and is adequate to take vaccines for the campaign and this is supported with additional freezers and ice-lined refrigerators. There are regional vaccine stores in five of the six regions that are equipped with refrigerators and freezers adequate enough to handle vaccines for the campaign. In addition, there is walk-in cold room in CRR that will be able to accomodate vaccines for the two regions (CRR and URR). Two of the smaller regions (NBRE & NBRW) have just been provided with solar refrigerators (TCW 2000 DC) for vaccine storage. All the public health facilities have been solarized for the storing of vaccines. In a bid to ensure quality mass vaccination campaign, additional freezers would be required at regional level for ice pack production. Therefore, part of the introduction grant would be used for the purchase of ten freezers to be distributed to the regions. In addition, 500 vaccine carriers and 1000 small ice packs would be needed for the campaign... 7.2.2. Grant Support for Operational Costs of the Meningogoccal Campaign.. Please indicate in the tables below how the support Grant [1] will be used to support the operational costs of the campaign and other critical pre-introduction activities. GAVI's support may not be enough to cover the full needs so please indicate in the table below how much and who will be complementing the funds needed (refer to the cMYP and the Meningogoccal, 10 dose(s) per vial, LIQUID campaign introduction plan)... Table 7.2.2: calculation of grant to support the operational costs of the campaigns.. Year of Meningogoccal support; Target population vaccinated (from Table 5.3); Share per population 1-29 years old in US$; Total in US$. 2013; 1,118,926; 0.65; 727,302.. [1] The Grant will be based on a maximum award of $0.65$ per cohort population.. Cost (and finance) of the Meningogoccal, 10 dose(s) per vial, LIQUID campaign US$.. Cost Category Full needs for new vaccine introduction in US$; Funded with GAVI introduction grant in US$. 2013; 2013. Training; 68,140; 48,140. Social Mobilization, IEC and advocacy; 85,321; 35,321. Cold Chain Equipment & Maintenance; 20,000; 20,000. Vehicles and Transportation; 75,215; 20,000. Programme Management; 5,000; 0. Surveillance and Monitoring; 10,000; 0. Human Resources; 234,368; 220,368. Waste Management; 13,589; 0. Technical Assistance; 10,000; 10,000. Planning; 22,783; 0. Volunteer incentives; 100,000; 0. Other (please specify). Imprest; 30,000; 0. Total; 674,416; 353,829..... Please describe others sources of funding if available to cover your full needs.. Government and other partners will mobilize the remaining part of the operational cost in-country....

8. Procurement and Management.

8.1. Procurement and Management of New and Under-Used Vaccines Routine.

Note: The PCV vaccine must be procured through UNICEF to be able to access the price awarded by the Advance Market Commitment (AMC)..

a) Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that most countries will procure vaccine and injection supplies through UNICEF):. Currently, vaccines and other EPI supplies are procured through UNICEF and the same mechanism will be utilized for the Rota vaccine.. b) If an alternative mechanism for procurement and delivery of vaccine supply (financed by the country or the GAVI Alliance) is requested, please document. l; Other vaccines or immunisation commodities procured by the country and descriptions of the mechanism used.. l; The functions of the National Regulatory Authority (as evaluated by WHO) to show they comply with WHO requirements for procurement of vaccines and supply of assured quality.. No alternative mechanism. c) Please describe the introduction of the vaccines (refer to cMYP). The Gambia had and will continue to introduce new vaccines, in pursuance of implementing Strategic Area Number of GIVS (i.e. introducing new vaccines and technologies). Compared to other contris within the sub region, The Gambia has a wealth of experience in new vaccine introduction, for instance, Hepatitis B (1990) Heamophillus Influenzae type B 91997), Pneumo (2009) and Measles Second Dose (2012) were added to the traditional vaccines. it is therefore evident that introducing new vaccines is not a new concept in the country. This is indicated in the Post Introduction Evaluation (PIE) conducted in 2010. Though experiences from the past exist, the country will adequately plan in order to successfully introduce any new vaccine. Adequate preparations will be made for the introduction of Rota virus vaccine. Furthermore, the country will conduct Men. A campaign in November 2013 as well as introduce Rota virus vaccine into routine immunization services in the second quarter of 2013.. d) Please indicate how funds should be transferred by the GAVI Alliance (if applicable). Already, there is an established system with a GAVI account at the Central Bank of The Gambia managed by the Ministries of Finance and Health. The funds from GAVI should be channeled through this account.. e) Please indicate how the co-financing amounts will be paid (and who is responsible for this). The government co-financing payments as required for other vaccines has been disbursed by the Ministry of Finance and deposited into the EPI account managed by UNICEF Supply Division in Copenhagen. This mechanism has been successfully utilized over the years for the procurement and co-financing of traditional and new vaccines respectively. The same mechanism will be used for the payment of co-financing of Rota virus vaccine.. f) Please outline how coverage of the new vaccine will be monitored and reported (refer to cMYP). There is already an existing mechanism for monitoring and reporting of routine administrative data. The same system would be used for Rota virus coverage after updating the data collection tools. the following systems are also in place: - monitoring the coverage using the monthly reports and monitoring charts at service delivery level. -Bi monthly meetings will be conducted at central level where routine data (feedback) is being reviewed and similar meetings are held at regional level monthly. -Supportive supervisory visits will be conducted by the central level to all the regions and health facilities, whilst regional health teams visit each health facility monthly. - Biennial survey will be conducted using standard WHO EPI survey tools to validate the routine administrative data. -Annual GAVI Progress Reports and joint reporting form will be submitted The current system of monthly, bi monthly, quarterly, annual reporting and feedback will continue at all levels.

8.2. Procurement and Management for NVS Preventive Campaign(s).

8.2.1. Procurement and Management for Meningogoccal, 10 dose(s) per vial, LIQUID campaign. a) Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that countries will procure vaccine and injection supplies through UNICEF):. Currently, vaccines and other EPI supplies are procured through UNICEF and the same mechanism will continue to be utilized for this campaign.. b) Please indicate when you are planning to conduct the campaign (month and year) and how the campaign is going to be rolled out (e.g. in different phases or one time).. The campaign will be conducted in November 2013 country wide targeting those aged 1-29 years.. c) Please outline how coverage of the new vaccine will be monitored and reported (refer to the cMYP and/or the Meningogoccal, 10 dose(s) per vial, LIQUID campaign introduction plan). During the campaign, daily reporting of data will be instituted at all levels (national, regional and health facility). In this system, the district data will be collected and sent by supervisors to the regional level for onward transmission to the central level. The central level will then analysed the data collected and send to WHO Sub Regional Office in Burkina Faso daily..

8.3. Vaccine Management (EVSM/EVM/VMA).

Did the country have Effective Vaccine Management Assessment (VMA) in the past? No. Did the country have Effective Vaccine Store Management (EVSM) in the past? No. Did the country have Effective Vaccine Management (EVM) in the past? Yes. When was the EVM conducted? June 2011. If your country conducted either EVSM or VMA in the past two years, please attach relevant reports. (Document N°13). A VMA report must be attached from those countries which have introduced a New and Underused Vaccine with GAVI support before 2008.. Please note that Effective Vaccine Store Management (EVSM) and Vaccine Management Assessment(VMA) tools have been replaced by an integrated Effective Vaccine Management (EVM) tool. The information on EVM tool can be found at http://www.who.int/immunization_delivery/systems_policy/logistics/en/index6.html. For countries which conducted EVSM, VMA or EVM in the past, please report on activities carried out as part of either action plan or improvement plan prepared after the EVSM/VMA/EVM.. After the Effective Vaccine Management (EVM) assessment, the following activities were carried out: i) The EPI Unit conducted training of trainers (ToT) at national level for central ad regional supervisors on immunization service delivery. Similar trainings were conducted at regional level for basic health facility staff offering immunization services. ii) Fridge tags were procured and distributed to all the health facilities country wide. iii) Ten (10) sets of refrigerators were procured and installed at regional and health facility level. iv) Monitoring and supervision at all levels have been strengthened v) Routine monitoring and maintenance of the cold chain system was carried out country wide and this will continue on regular basis. vi) Multi-loggers and other cold chain accessories have been procured and would be installed in the fourth quarter of 2012.. Does the country plan to conduct an Effective Vaccine Management (EVM) Assessment in the future? No.

9. Additional Comments and Recommendations from the National Coordinating Body (ICC/HSCC).

Comments and Recommendations from the National Coordinating Body (ICC/HSCC).

10. Attachments.

10.1. List of documents attached to this proposal.

Document Number; Document; Section; Mandatory; File. MoH & MoF Signatures _Men. A.pdf. 1; MoH Signature (or delegated authority) of Proposal; File desc:. Date/time: 8/28/2012 10:01:44 AM. Size: 333374. MoH & MoF Signatures _Men. A.pdf. 2; MoF Signature (or delegated authority) of Proposal; File desc:. Date/time: 8/28/2012 10:02:18 AM. Size: 333374. ICC SIGNATURES_ Men.A.pdf. 3; Signatures of ICC or HSCC or equivalent in Proposal; File desc:. Date/time: 8/28/2012 10:06:06 AM. Size: 546811. ICC_MINUTES_MAY_2012.doc. 4; Minutes of ICC/HSCC meeting endorsing Proposal; File desc:. Date/time: 8/28/2012 10:07:56 AM. Size: 320512. THE GAMBIA cMYP FOR 2012-2016.doc. 5; comprehensive Multi Year Plan - cMYP; File desc:. Date/time: 8/28/2012 10:12:43 AM. Size: 4911104. NITAG.doc. 5; Minutes of NITAG meeting endorsing proposal; 4.2; File desc:. Date/time: 8/29/2012 6:50:47 AM. Size: 26112. The Gambia_cMYP_Costing_Tool_2012-2016.xls. 6; cMYP Costing tool for financial analysis; File desc:. Date/time: 8/26/2012 9:41:17 AM. Size: 3523584. Final Introduction Plan for Rota Virus 2013-2016_21_08_2012 LATEST.doc. 7; Plan for NVS introduction (if not part of cMYP); 5.1; File desc:. Date/time: 8/30/2012 5:01:38 AM. Size: 251392. EVM Improvement Plan Gambia.xls. 8; Improvement plan based on EVM; File desc:. Date/time: 8/26/2012 9:44:01 AM. Size: 55808. HPV PROJECT.doc. 9; HPV summary of the evaluation methodology; 5.1.1; File desc:. Date/time: 8/29/2012 6:42:44 AM. Size: 26112. HPV PROJECT.doc. 10; HPV roadmap or strategy; 6.1.1; File desc:. Date/time: 8/29/2012 6:43:29 AM. Size: 26112. RCV.doc. 11; Evidence of introduction of RCV in routine programme; 7.c.3; File desc:. Date/time: 8/29/2012 6:47:05 AM. Size: 26112. RCV.doc. 12; Plan Of Action for RCV introduction; 7.c.4; File desc:. Date/time: 8/29/2012 6:46:05 AM. Size: 26112.

11. Annexes... Annex 1 - NVS Routine Support

Annex 1.1 - NVS Routine Support (Rotavirus, 3 -dose schedule). Table Annex 1.1 A: Rounded up portion of supply that is procured by the country and estimate of relative costs in US$.. 2013; 2014; 2015; 2016. Number of vaccine doses; #; 9,900; 8,300; 8,600; 9,100. Number of AD syringes; #; 0; 0; 0; 0. Number of re-constitution syringes; #; 0; 0; 0; 0. Total value to be co-financed by country; $; 36,500; 30,500; 32,000; 33,500... Table Annex 1.1 B: Rounded up portion of supply that is procured by GAVI and estimate of relative costs in US$.. 2013; 2014; 2015; 2016. Number of vaccine doses; #; 264,700; 221,900; 230,300; 241,800. Number of AD syringes; #; 0; 0; 0; 0. Number of re-constitution syringes; #; 0; 0; 0; 0. Total value to be co-financed by country; $; 973,000; 815,500; 846,500; 888,500....

Table Annex 1.1 C: Summary table for vaccine Rotavirus, 3 -dose schedule. ID Data from; 2013; 2014; 2015; 2016. Number of surviving infants; Table 5.2; #; 75,775; 77,820; 79,921; 81,991. Number of children to be vaccinated with the first dose; Table 5.2; #; 69,713; 72,373; 75,126; 78,711. Number of children to be vaccinated with the third dose; Table 5.2; #; 68,198; 70,816; 73,527; 77,072. Immunisation coverage with the third dose; Table 5.2; %; 90.00 %; 91.00 %; 92.00 %; 94.00 %. Number of doses per child; Parameter; #; 3; 3; 3; 3. Estimated vaccine wastage factor; Table 5.2; #; 1.05; 1.05; 1.05; 1.05. Number of doses per vial; Parameter; #; 1; 1; 1; 1. AD syringes required; Parameter; #; No; No; No; No. Reconstitution syringes required; Parameter; #; No; No; No; No. Safety boxes required; Parameter; #; No; No; No; No. g; Vaccine price per dose; Table Annexes 4A; $; 3.5; 3.5; 3.5; 3.5. cc; Country co-financing per dose; Table 6.4.1; $; 0.13; 0.13; 0.13; 0.13. ca; AD syringe price per unit; Table Annexes 4A; $; 0.0465; 0.0465; 0.0465; 0.0465. cr; Reconstitution syringe price per unit; Table Annexes 4A; $; 0; 0; 0; 0. cs; Safety box price per unit; Table Annexes 4A; $; 0.0058; 0.0058; 0.0058; 0.0058. fv; Freight cost as % of vaccines value; Table Annexes 4B; %; 5.00 %; 5.00 %; 5.00 %; 5.00 %. fd; Freight cost as % of devices value; Parameter; %; 10.00 %; 10.00 %; 10.00 %; 10.00 %....

Table Annex 1.1 D: Estimated numbers for Rotavirus, 3 -dose schedule, associated injection safety material and related co-financing budget (page 1) Formula; 2013. Total; Government; GAVI. A; Country co-finance; 3.59 %. B; Number of children to be vaccinated with the first dose; Table 1; 69,713; 2,505; 67,208. C; Number of doses per child; Vaccine parameter (schedule); 3.00. D; Number of doses needed; B x C; 209,139; 7,513; 201,626. E; Estimated vaccine wastage factor; Wastage factor table; 1.05. F; Number of doses needed including wastage; D x E; 219,596; 7,888; 211,708. G; Vaccines buffer stock; (F – F of previous year) * 0.25; 54,899; 1,972; 52,927. I; Total vaccine doses needed; F + G; 274,495; 9,860; 264,635. J; Number of doses per vial; Vaccine parameter; 1.00. K; Number of AD syringes (+ 10% wastage) needed; (D + G) x 1.11; 0; 0; 0. L; Reconstitution syringes (+ 10% wastage) needed; I / J * 1.11; 0; 0; 0. N; Cost of vaccines needed; I x g; 960,733; 34,509; 926,224. O; Cost of AD syringes needed; K x ca; 0; 0; 0. P; Cost of reconstitution syringes needed; L x cr; 0; 0; 0. Q; Cost of safety boxes needed; M x cs; 0.00; 0; 0. R; Freight cost for vaccines needed; N x fv; 48,037; 1,726; 46,311. S; Freight cost for devices needed; (O+P+Q) x fd; 0; 0; 0. T; Total fund needed; (N+O+P+Q+R+S); 1,008,770; 36,234; 972,536. U; Total country co-financing; I 3 cc; 36,234. V; Country co-financing % of GAVI supported proportion; U / T; 3.59 %... Table Annex 1.1 D: Estimated numbers for Rotavirus, 3 -dose schedule, associated injection safety material and related co-financing budget (page 2). Formula; 2014. Total; Government; GAVI. A; Country co-finance; 3.59 %. B; Number of children to be vaccinated with the first dose; Table 1; 72,373; 2,600; 69,773. C; Number of doses per child; Vaccine parameter (schedule); 3.00. D; Number of doses needed; B x C; 217,119; 7,799; 209,320. E; Estimated vaccine wastage factor; Wastage factor table; 1.05. F; Number of doses needed including wastage; D x E; 227,975; 8,189; 219,786. G; Vaccines buffer stock; (F – F of previous year) * 0.25; 2,095; 76; 2,019. I; Total vaccine doses needed; F + G; 230,070; 8,264; 221,806. J; Number of doses per vial; Vaccine parameter; 1.00. K; Number of AD syringes (+ 10% wastage) needed; (D + G) x 1.11; 0; 0; 0. L; Reconstitution syringes (+ 10% wastage) needed; I / J * 1.11; 0; 0; 0. N; Cost of vaccines needed; I x g; 805,245; 28,924; 776,321. O; Cost of AD syringes needed; K x ca; 0; 0; 0. P; Cost of reconstitution syringes needed; L x cr; 0; 0; 0. Q; Cost of safety boxes needed; M x cs; 0.00; 0; 0. R; Freight cost for vaccines needed; N x fv; 40,263; 1,447; 38,816. S; Freight cost for devices needed; (O+P+Q) x fd; 0; 0; 0. T; Total fund needed; (N+O+P+Q+R+S); 845,508; 30,370; 815,138. U; Total country co-financing; I 3 cc; 30,370. V; Country co-financing % of GAVI supported proportion; U / T; 3.59 %... Table Annex 1.1 D: Estimated numbers for Rotavirus, 3 -dose schedule, associated injection safety material and related co-financing budget (page 3). Formula; 2015. Total; Government; GAVI. A; Country co-finance; 3.59 %. B; Number of children to be vaccinated with the first dose; Table 1; 75,126; 2,699; 72,427. C; Number of doses per child; Vaccine parameter (schedule); 3.00. D; Number of doses needed; B x C; 225,378; 8,096; 217,282. E; Estimated vaccine wastage factor; Wastage factor table; 1.05. F; Number of doses needed including wastage; D x E; 236,647; 8,501; 228,146. G; Vaccines buffer stock; (F – F of previous year) * 0.25; 2,168; 78; 2,090. I; Total vaccine doses needed; F + G; 238,815; 8,578; 230,237. J; Number of doses per vial; Vaccine parameter; 1.00. K; Number of AD syringes (+ 10% wastage) needed; (D + G) x 1.11; 0; 0; 0. L; Reconstitution syringes (+ 10% wastage) needed; I / J * 1.11; 0; 0; 0. N; Cost of vaccines needed; I x g; 835,853; 30,023; 805,830. O; Cost of AD syringes needed; K x ca; 0; 0; 0. P; Cost of reconstitution syringes needed; L x cr; 0; 0; 0. Q; Cost of safety boxes needed; M x cs; 0.00; 0; 0. R; Freight cost for vaccines needed; N x fv; 41,793; 1,502; 40,291. S; Freight cost for devices needed; (O+P+Q) x fd; 0; 0; 0. T; Total fund needed; (N+O+P+Q+R+S); 877,646; 31,524; 846,122. U; Total country co-financing; I 3 cc; 31,524. V; Country co-financing % of GAVI supported proportion; U / T; 3.59 %... Table Annex 1.1 D: Estimated numbers for Rotavirus, 3 -dose schedule, associated injection safety material and related co-financing budget (page 4). Formula; 2016. Total; Government; GAVI. A; Country co-finance; 3.59 %. B; Number of children to be vaccinated with the first dose; Table 1; 78,711; 2,828; 75,883. C; Number of doses per child; Vaccine parameter (schedule); 3.00. D; Number of doses needed; B x C; 236,133; 8,482; 227,651. E; Estimated vaccine wastage factor; Wastage factor table; 1.05. F; Number of doses needed including wastage; D x E; 247,940; 8,906; 239,034. G; Vaccines buffer stock; (F – F of previous year) * 0.25; 2,824; 102; 2,722. I; Total vaccine doses needed; F + G; 250,764; 9,008; 241,756. J; Number of doses per vial; Vaccine parameter; 1.00. K; Number of AD syringes (+ 10% wastage) needed; (D + G) x 1.11; 0; 0; 0. L; Reconstitution syringes (+ 10% wastage) needed; I / J * 1.11; 0; 0; 0. N; Cost of vaccines needed; I x g; 877,674; 31,525; 846,149. O; Cost of AD syringes needed; K x ca; 0; 0; 0. P; Cost of reconstitution syringes needed; L x cr; 0; 0; 0. Q; Cost of safety boxes needed; M x cs; 0.00; 0; 0. R; Freight cost for vaccines needed; N x fv; 43,884; 1,577; 42,307. S; Freight cost for devices needed; (O+P+Q) x fd; 0; 0; 0. T; Total fund needed; (N+O+P+Q+R+S); 921,558; 33,101; 888,457. U; Total country co-financing; I 3 cc; 33,101. V; Country co-financing % of GAVI supported proportion; U / T; 3.59 %......

Annex 2 - NVS Routine – Preferred Second Presentation.

No NVS Routine – Preferred Second Presentation requested this year.

Annex 3 - NVS Preventive campaign(s)... Annex 3.1 - NVS Preventive campaign(s) (Meningogoccal, 10 dose(s) per vial, LIQUID). Table Annex 3.1 C: Summary table for CAMPAIGN Meningogoccal, 10 dose(s) per vial, LIQUID.. Data from; 2013. Total campaign population; Table 5.3.1; #; 1,243,251. Immunization coverage; Table 5.3.1; %; 90.00 %. Number of persons to be vaccinated; Table 5.3.1; #; 1,118,926. Number of doses per persons; Parameter; #; 1. Estimated vaccine wastage factor; Table 5.3.1; #; 1.11. Number of doses per vial; Parameter; #; 10. AD syringes required; Parameter; #; Yes. Reconstitution syringes required; Parameter; #; No. Safety boxes required; Parameter; #; No. Vaccine price per dose; Table Annexes 4A; $; 0.52. AD syringe price per unit; Table Annexes 4A; $; 0.0465. Reconstitution syringe price per unit; Table Annexes 4A; $; 0. Safety box price per unit; Table Annexes 4A; $; 0.0058. Freight cost as % of vaccines value; Table Annexes 4B; %; 10.00 %. Freight cost as % of devices value; Parameter; %; 0...

Table Annex 3.1 D: Estimated number of Meningogoccal, 10 dose(s) per vial, LIQUID associated injection safety material and related co-financing budget (page 1). Formula; GAVI. 2013. B; Number of persons to be vaccinated with the first dose; 1,118,926. C; Number of doses per persons; 1. D; Number of doses needed; B x C; 1,118,926. E; Estimated vaccine wastage factor; Wastage factor table; 1.11. F; Number of doses needed including wastage; D x E; 1,242,008. G; Vaccines buffer stock; (F – F of previous year) * 0.25; 310,502. I; Total vaccine doses needed; F + G; 1,552,510. J; Number of doses per vial; Vaccine parameter; 10. K; Number of AD syringes (+ 10% wastage) needed; (D + G) x 1.11; 1,586,666. L; Reconstitution syringes (+ 10% wastage) needed; I / J * 1.11; 0. N; Cost of vaccines needed; I x g; 0.52. O; Cost of AD syringes needed; K x ca; 73,779.969. P; Cost of reconstitution syringes needed; L x cr; 0. Q; Cost of safety boxes needed; M x cs; 0. R; Freight cost for vaccines needed; N x fv; 0. S; Freight cost for devices needed; (O+P+Q) x fd; 0. T; Total fund needed; (N+O+P+Q+R+S); 881,085.969... Note: There is no cofinancing for NVS preventive campaigns...

| Annex 4. |  |
| --- | --- |
| Table Annex 4A: Commodities Cost. |  |
| Vaccine; Presentation; 2013; 2014; 2015; 2016. DTP-HepB, 10 dose(s) per vial, LIQUID; 10. DTP-HepB-Hib, 1 dose(s) per vial, LIQUID; 1; 2.017; 1.986; 1.933; 1.927. DTP-HepB-Hib, 10 dose(s) per vial, LIQUID; 10; 2.017; 1.986; 1.933; 1.927. DTP-HepB-Hib, 2 dose(s) per vial, LYOPHILISED; 2; 2.017; 1.986; 1.933; 1.927. HPV bivalent, 2 dose(s) per vial, LIQUID; 2; 5.000; 5.000; 5.000; 5.000. HPV quadrivalent, 1 dose(s) per vial, LIQUID; 1; 5.000; 5.000; 5.000; 5.000. Measles, 10 dose(s) per vial, LYOPHILISED; 10; 0.242; 0.242; 0.242; 0.242. Meningogoccal, 10 dose(s) per vial, LIQUID; 10; 0.520; 0.520; 0.520; 0.520. MR, 10 dose(s) per vial, LYOPHILISED; 10; 0.494; 0.494; 0.494; 0.494. Pneumococcal (PCV10), 2 dose(s) per vial, LIQUID; 2; 3.500; 3.500; 3.500; 3.500. Pneumococcal (PCV13), 1 dose(s) per vial, LIQUID; 1; 3.500; 3.500; 3.500; 3.500. Rotavirus, 2-dose schedule; 1; 2.550; 2.550; 2.550; 2.550. Rotavirus, 3-dose schedule; 1; 3.500; 3.500; 3.500; 3.500. Yellow Fever, 10 dose(s) per vial, LYOPHILISED; 10; 0.900; 0.900; 0.900; 0.900. Yellow Fever, 5 dose(s) per vial, LYOPHILISED; 5; 0.900; 0.900; 0.900; 0.900. |  |
| Note for HPV and MR: These prices are indicative only as GAVI has not procured HPV and MR vaccines for GAVI countries yet. Prices will be finalised through tender processes in Q3. GAVI will only fund HPV vaccines if an acceptable price reduction is secured from the current price indicated. The MR price is based on the current price to UNICEF. |  |
| Supply; Form; 2013; 2014; 2015; 2016. AD-SYRINGE; SYRINGE; 0.047; 0.047; 0.047; 0.047. RECONSTIT-SYRINGE-PENTAVAL; SYRINGE; 0.047; 0.047; 0.047; 0.047. RECONSTIT-SYRINGE-YF; SYRINGE; 0.004; 0.004; 0.004; 0.004. SAFETY-BOX; SAFETYBOX; 0.006; 0.006; 0.006; 0.006. |  |
| Note: WAP - weighted average price (to be used for any presentation: For DTP-HepB-Hib, it applies to 1 dose liquid, 2 dose lyophilised and 10 dose liquid. For Yellow Fever, it applies to 5 dose lyophilised and 10 dose lyophilised). |  |
| Table Annex 4B: Freight cost as percentage of value. |  |
| Vaccine Antigen; Vaccine Type; No Threshold; 500,000$. <=; >. DTP-HepB; HEPBHIB; 2.00 %. DTP-HepB-Hib; HEPBHIB; 23.80 %; 6.00 %. HPV bivalent; HPV; 3.50 %. HPV quadrivalent; HPV; 3.50 %. Measles; MEASLES; 14.00 %. Meningogoccal; MENINACONJUGATE; 10.20 %. MR; MR; 13.20 %. Pneumococcal (PCV10); PNEUMO; 3.00 %. Pneumococcal (PCV13); PNEUMO; 6.00 %. Rotavirus; ROTA; 5.00 %. Yellow Fever; YF; 7.80 %. |  |
| Table Annex 4C: Low - Minimum country's co-payment per dose of co-financed vaccine.. |  |
| Vaccine; 2013; 2014; 2015; 2016. Rotavirus, 1 dose(s) per vial, ORAL; 0.132; 0.132; 0.132; 0.132. |  |
| Table Annex 4D: Wastage rates and factors. |  |
| Countries are expected to plan for a maximal wastage rate of:. |  |
| • 50% - for a lyophilised vaccine in 10 or 20-dose vial,. |  |
| • 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,. |  |
| • 10% - for a lyophilised/liquid vaccine in 2-dose vial, and. |  |
| • 5% - for a liquid vaccine in 1-dose vial. |  |
| Vaccine wastage rate; 5%; 10%; 15%; 20%; 25%; 30%; 35%; 40%; 45%; 50%; 55%; 60%. Equivalent wastage factor; 1.05; 1.11; 1.18; 1.25; 1.33; 1.43; 1.54; 1.67; 1.82; 2; 2.22; 2.5. |  |
| Vaccine; Vaccine wastage rate; VaccineWastageFactor. Meningogoccal, 10 dose(s) per vial, LIQUID; 0%; 1. |  |
| Table Annex 4E: Vaccine maximum packed volumes. |  |
| Vaccine product; Designation; Vaccine formulation; Admin route; No. Of doses in the schedule; Presentation (doses/vial, prefilled); Packed volume vaccine (cm3/dose); Packed volume diluents (cm3/dose). BCG; BCG; lyophilized; ID; 1; 20; 1.2; 0.7. Diphtheria-Tetanus-Pertussis; DTP; liquid; IM; 3; 20; 2.5. Diphtheria-Tetanus-Pertussis; DTP; liquid; IM; 3; 10; 3. Diphtheria-Tetanus; DT; liquid; IM; 3; 10; 3. Tetanus-Diphtheria; Td; liquid; IM; 2; 10; 3. Tetanus Toxoid; TT; liquid; IM; 2; 10; 3. Tetanus Toxoid; TT; liquid; IM; 2; 20; 2.5. Tetanus Toxoid UniJect; TT; liquid; IM; 2; Uniject; 12. Measles; Measles; lyophilized; SC; 1; 1; 26.1; 20. Measles; Measles; lyophilized; SC; 1; 2; 13.1; 13.1. Measles; Measles; lyophilized; SC; 1; 5; 5.2; 7. Measles; Measles; lyophilized; SC; 1; 10; 3.5; 4. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 1; 26.1; 26.1. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 2; 13.1; 13.1. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 5; 5.2; 7. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 10; 2.5; 4. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 1; 26.1; 26.1. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 2; 13.1; 13.1. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 5; 5.2; 7. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 10; 3; 4. Polio; OPV; liquid; Oral; 4; 10; 2. Polio; OPV; liquid; Oral; 4; 20; 1. Yellow fever; YF; lyophilized; SC; 1; 5; 6.5; 7. Yellow fever; YF; lyophilized; SC; 1; 10; 2.5; 3. Yellow fever; YF; lyophilized; SC; 1; 20; 1.5; 2. Yellow fever; YF; lyophilized; SC; 1; 50; 0.7; 1. DTP-HepB combined; DTP-HepB; liquid; IM; 3; 1; 9.7. DTP-HepB combined; DTP-HepB; liquid; IM; 3; 2; 6. DTP-HepB combined; DTP-HepB; liquid; IM; 3; 10; 3. Hepatitis B; HepB; liquid; IM; 3; 1; 18. Hepatitis B; HepB; liquid; IM; 3; 2; 13. Hepatitis B; HepB; liquid; IM; 3; 6; 4.5. Hepatitis B; HepB; liquid; IM; 3; 10; 4. Hepatitis B UniJect; HepB; liquid; IM; 3; Uniject; 12. Hib liquid; Hib_liq; liquid; IM; 3; 1; 15. Hib liquid; Hib_liq; liquid; IM; 3; 10; 2.5. Hib freeze-dried; Hib_lyo; lyophilized; IM; 3; 1; 13; 35. Hib freeze-dried; Hib_lyo; lyophilized; IM; 3; 2; 6. Hib freeze-dried; Hib_lyo; lyophilized; IM; 3; 10; 2.5; 3. DTP liquid + Hib freeze-dried; DTP+Hib; liquid+lyop.; IM; 3; 1; 45. DTP-Hib combined liquid; DTP+Hib; liquid+lyop.; IM; 3; 10; 12. DTP-Hib combined liquid; DTP-Hib; liquid; IM; 3; 1; 32.3. DTP-HepB liquid + Hib freeze-dried; DTP-Hib; liquid; IM; 3; 10; 2.5. DTP-HepB liquid + Hib freeze-dried; DTP-HepB+Hib; liquid+lyop.; IM; 3; 1; 22. DTP-HepB-Hib liquid; DTP-HepB+Hib; liquid+lyop.; IM; 3; 2; 11. DTP-HepB-Hib liquid; DTP-HepB-Hib; liquid; IM; 3; 10; 4.4. DTP-HepB-Hib liquid; DTP-HepB-Hib; liquid; IM; 3; 2; 13.1. DTP-HepB-Hib liquid; DTP-HepB-Hib; liquid; IM; 3; 1; 19.2. Meningitis A/C; MV_A/C; lyophilized; SC; 1; 10; 2.5; 4. Meningitis A/C; MV_A/C; lyophilized; SC; 1; 50; 1.5; 3. Meningococcal A/C/W/; MV_A/C/W; lyophilized; SC; 1; 50; 1.5; 3. Meningococcal A/C/W/Y; MV_A/C/W/Y; lyophilized; SC; 1; 10; 2.5; 4. Meningitis W135; MV_W135; lyophilized; SC; 1; 10; 2.5; 4. Meningitis A conjugate; Men_A; lyophilized; SC; 2; 10; 2.6; 4. Japanese Encephalitis; JE_lyo; lyophilized; SC; 3; 10; 15. Japanese Encephalitis; JE_lyo; lyophilized; SC; 3; 10; 8.1; 8.1. Japanese Encephalitis; JE_lyo; lyophilized; SC; 3; 5; 2.5; 2.9. Japanese Encephalitis; JE_lyo; lyophilized; SC; 3; 1; 12.6; 11.5. Japanese Encephalitis; JE_liq; liquid; SC; 3; 10; 3.4. Rota vaccine; Rota_lyo; lyophilized; Oral; 2; 1; 156. Rota vaccine; Rota_liq; liquid; Oral; 2; 1; 17.1. Rota vaccine; Rota_liq; liquid; Oral; 3; 1; 45.9. Pneumo. conjugate vaccine 7-valent; PCV-7; liquid; IM; 3; PFS; 55.9. Pneumo. conjugate vaccine 7-valent; PCV-7; liquid; IM; 3; 1; 21. Pneumo. conjugate vaccine 10-valent; PCV-10; liquid; IM; 3; 1; 11.5. Pneumo. conjugate vaccine 10-valent; PCV-10; liquid; IM; 3; 2; 4.8. Pneumo. conjugate vaccine 13-valent; PCV-13; liquid; IM; 3; 1; 12. Polio inactivated; IPV; liquid; IM; 3; PFS; 107.4. Polio inactivated; IPV; liquid; IM; 3; 10; 2.5. Polio inactivated; IPV; liquid; IM; 3; 1; 15.7. Human Papilomavirus vaccine; HPV; liquid; IM; 3; 1; 15. Human Papilomavirus vaccine; HPV; liquid; IM; 3; 2; 5.7. Monovalent OPV-1; mOPV1; liquid; Oral; 20; 1.5. Monovalent OPV-3; mOPV3; liquid; Oral; 20; 1.5. |  |

| 12. Banking Form |  |
| --- | --- |
| In accordance with the decision on financial support made by the GAVI Alliance, the Government of Gambia hereby requests that a payment be made via electronic bank transfer as detailed below:. Name of Institution (Account Holder):. Address:. City Country:. Telephone no.:; Fax no.:. Currency of the bank account:. For credit to:. Bank account's title:. Bank account no.:. Bank's name:. |  |
| Is the bank account exclusively to be used by this program?. |  |
| By who is the account audited?. |  |
| Signature of Government's authorizing official. |  |
| Seal. Name:. Title:. Signature:. Date:. |  |
| FINANCIAL INSTITUTION. Bank Name:. Branch Name:. Address:. City Country:. Swift Code:. Sort Code:. ABA No.:. Telephone No.:. FAX No.:. | CORRESPONDENT BANK. (In the United States). |
| I certify that the account No is held by at this banking institution. The account is to be signed jointly by at least (number of signatories) of the following authorized signatories:. 1; Name:. Title:. 2; Name:. Title:. 3; Name:. Title:. |  |
| Name of bank's authorizing official. Signature:. Date:. Seal:. |  |