GAVI Alliance

Application Form for Country Proposals

For Support to New and Under-Used Vaccines (NVS)

Submitted by

The Government of

Burundi

Date of submission: 29.05.2011 09:01:25

Deadline for submission: 1 Jun 2011

Select Start and End Year of your Comprehensive Multi-Year Plan (cMYP)

| Start Year | 2011 | End Year | 2015 |
| --- | --- | --- | --- |

Revised in January 2011

(To be used with Guidelines of December 2010)

Please submit the Proposal using the online platform https://AppsPortal.gavialliance.org/PDExtranet.

Enquiries to: proposals@gavialliance.org or representatives of a GAVI partner agency. The documents can be shared with GAVI partners, collaborators and general public. The Proposal and attachments must be submitted in English, French, Spanish, or Russian.

Note: Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline.

The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents will be shared with the GAVI Alliance partners and the general public.

GAVI ALLIANCE GRANT TERMS AND CONDITIONS FUNDING USED SOLELY FOR APPROVED PROGRAMMES The applicant country (“Country”) confirms that all funding provided by the GAVI Alliance will be used and applied for the sole purpose of fulfilling the programme(s) described in the Country’s application. Any significant change from the approved programme(s) must be reviewed and approved in advance by the GAVI Alliance. All funding decisions for the application are made at the discretion of the GAVI Alliance Board and are subject to IRC processes and the availability of funds. AMENDMENT TO THE APPLICATION The Country will notify the GAVI Alliance in its Annual Progress Report if it wishes to propose any change to the programme(s) description in its application. The GAVI Alliance will document any change approved by the GAVI Alliance, and the Country’s application will be amended. RETURN OF FUNDS The Country agrees to reimburse to the GAVI Alliance all funding amounts that are not used for the programme(s) described in its application. The country’s reimbursement must be in US dollars and be provided, unless otherwise decided by the GAVI Alliance, within sixty (60) days after the Country receives the GAVI Alliance’s request for a reimbursement and be paid to the account or accounts as directed by the GAVI Alliance. SUSPENSION/ TERMINATION The GAVI Alliance may suspend all or part of its funding to the Country if it has reason to suspect that funds have been used for purpose other than for the programmes described in the Country’s application, or any GAVI Alliance-approved amendment to the application. The GAVI Alliance retains the right to terminate its support to the Country for the programmes described in its application if a misuse of GAVI Alliance funds is confirmed. ANTICORRUPTION The Country confirms that funds provided by the GAVI Alliance shall not be offered by the Country to any third person, nor will the Country seek in connection with its application any gift, payment or benefit directly or indirectly that could be construed as an illegal or corrupt practice. AUDITS AND RECORDS The Country will conduct annual financial audits, and share these with the GAVI Alliance, as requested. The GAVI Alliance reserves the right, on its own or through an agent, to perform audits or other financial management assessment to ensure the accountability of funds disbursed to the Country. The Country will maintain accurate accounting records documenting how GAVI Alliance funds are used. The Country will maintain its accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of GAVI Alliance funds. If there is any claims of misuse of funds, Country will maintain such records until the audit findings are final. The Country agrees not to assert any documentary privilege against the GAVI Alliance in connection with any audit. CONFIRMATION OF LEGAL VALIDITY The Country and the signatories for the Country confirm that its application, and Annual Progress Report, are accurate and correct and form legally binding obligations on the Country, under the Country’s law, to perform the programmes described in its application, as amended, if applicable, in the APR. CONFIRMATION OF COMPLIANCE WITH THE GAVI ALLIANCE TRANSPARANCY AND ACCOUNTABILITY POLICY The Country confirms that it is familiar with the GAVI Alliance Transparency and Accountability Policy (TAP) and complies with the requirements therein. USE OF COMMERCIAL BANK ACCOUNTS The Country is responsible for undertaking the necessary due diligence on all commercial banks used to manage GAVI cash-based support. The Country confirms that it will take all responsibility for replenishing GAVI cash support lost due to bank insolvency, fraud or any other unforeseen event. ARBITRATION Any dispute between the Country and the GAVI Alliance arising out of or relating to its application that is not settled amicably within a reasonable period of time, will be submitted to arbitration at the request of either the GAVI Alliance or the Country. The arbitration will be conducted in accordance with the then-current UNCITRAL Arbitration Rules. The parties agree to be bound by the arbitration award, as the final adjudication of any such dispute. The place of arbitration will be Geneva, Switzerland. The language of the arbitration will be English. For any dispute for which the amount at issue is US$ 100,000 or less, there will be one arbitrator appointed by the GAVI Alliance. For any dispute for which the amount at issue is greater than US $100,000 there will be three arbitrators appointed as follows: The GAVI Alliance and the Country will each appoint one arbitrator, and the two arbitrators so appointed will jointly appoint a third arbitrator who shall be the chairperson. The GAVI Alliance will not be liable to the country for any claim or loss relating to the programmes described in the application, including without limitation, any financial loss, reliance claims, any harm to property, or personal injury or death. Country is solely responsible for all aspects of managing and implementing the programmes described in its application.

# Application Specification

Please specify for which type of GAVI support you would like to apply to.

Important note: To enable proper functioning of the form, please first select the cMYP years on the previous page.

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Type of Support | Vaccine | Start Year | End Year | Preferred second presentation[1] | Action |
| --- | --- | --- | --- | --- | --- |
| New Vaccines Support | Measles, 10 doses/vial, Lyophilised | 2012 | 2015 |  |  |
| New Vaccines Support | Rotavirus 2-dose schedule | 2013 | 2015 | Rotavirus 3-dose schedule |  |

[1] This "Preferred second presentation" will be used in case there is no supply available for the preferred presentation of the selected vaccine ("Vaccine" column). If left blank, it will be assumed that the country will prefer waiting until the selected vaccine becomes available.

# Table of Contents

Sections

Main

Cover Page

GAVI Alliance Grants Terms and Conditions

1. Application Specification

2. Table of Contents

3. Executive Summary

4. Signatures

4.1. Signatures of the Government and National Coordinating Bodies

4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation

4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation

4.1.3. The Inter-Agency Coordinating Committee for Immunisation

4.2. National Immunization Technical Advisory Group for Immunisation

4.2.1. The NITAG Group for Immunisation

5. Immunisation Programme Data

5.1. Basic facts

5.2. Current vaccination schedule

5.3. Trends of immunisation coverage and disease burden

5.4. Baseline and Annual Targets

Table 1: baseline figures

5.5. Summary of current and future immunisation budget

5.6. Summary of current and future financing and sources of funds

6. NVS

6.1. Capacity and cost (for positive storage)

6.2. Assessment of burden of relevant diseases (if available)

6.3.1. Requested vaccine ( Measles, 10 doses/vial, Lyophilised )

6.3.2. Co-financing information

6.3.3. Wastage factor

6.3.4. Specifications of vaccinations with new vaccine

6.3.5. Portion of supply to be procured by the country (and cost estimate, US$)

6.3.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

6.3.7. New and Under-Used Vaccine Introduction Grant

6.4.1. Requested vaccine ( Rotavirus 2-dose schedule )

6.4.2. Co-financing information

6.4.3. Wastage factor

6.4.4. Specifications of vaccinations with new vaccine

6.4.5. Portion of supply to be procured by the country (and cost estimate, US$)

6.4.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

6.4.7. New and Under-Used Vaccine Introduction Grant

7. Procurement and Management of New and Under-Used Vaccines

7.1. Vaccine management (EVSM/EVM/VMA)

8. Additional Comments and Recommendations

9. Annexes

Annex 1

Annex 1.1 - Measles, 10 doses/vial, Lyophilised

Table 1.1  A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

Table 1.1  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

Table 1.1  C - Summary table for vaccine Measles, 10 doses/vial, Lyophilised

Table 1.1  D - Estimated number of doses for vaccine Measles, 10 doses/vial, Lyophilised associated injection safety material and related co-financing budget

Annex 1.2 - Rotavirus 2-dose schedule

Table 1.2  A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

Table 1.2  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

Table 1.2  C - Summary table for vaccine Rotavirus 2-dose schedule

Table 1.2  D - Estimated number of doses for vaccine Rotavirus 2-dose schedule associated injection safety material and related co-financing budget

Annex 2

10. Attachments

10.1 Documents required for NVS support

10.2 Attachments

Banking Form

# Executive Summary

Burundi started its program in 1980 with vaccines against diphtheria, tuberculosis, whooping cough measles, polio and tetanos. This program proved highly successful at the country level such that in less than ten years, the country had coverage of over 80% for all those antigens. In 2004,two new vaccines were introduced, i.e. the vaccine against viral hepatitis B and type b haemophilus influenzae in two injections. During 2005, this form was replaced by the Pentavalent that is given in a single injection combining liquid DTC-Hep B and freeze-dried Hib. The pentavalent 3 coverage rate was 96% in 2010, and the measles coverage rate estimated by the WHO and UNICEF was 69% in 2007, 84% in 2008, 91% in 2009 and 92 % in 2010
The main factors that led to improved vaccine coverage are listed below:

-	Th e existence of major health centers (an average of 80% of the population lives within a five-kilometer radius of the Health Centers [CDS].) 
-	The existence of a major network of accessible roads that facilitates access by the people to heathcare facilities. This also makes it easier to provide supervision and supplies to the health centers. 
-	More than 90% of the country’s healthcare facilities provide routine vaccination services;
-	The proper use of healthcare services 
-	Free vaccinations for children and care for pregnant women 
-	Mother and Child Week held every six months since 2003 
-	EPI activities incorporated into the other programs (vit A, MII, deworming, etc.…)
-	Existence of a community network (grassroots administration and ASC [community health agents])
-	Functional cold chain at all levels.
-	Involvement of civil society in immunization services 

The major challenges facing the EPI are listed below:
-	Controlling outbreaks of measles epidemics in districts with low vaccine coverage 
-	Controlling overall drop-out rates nationally (9% in 2008);

-	Poor ability to forecast and estimate EPI needs at the intermediate and outreach levels, resulting in frequent vaccine inventory shortages, causing many missed opportunities.
-	Low Pentavalent III vaccine coverage (less than 80%) in four healthcare districts out of 45 in 2010;
-	Low rates of measles vaccine coverage (less than 80%) in ten healthcare districts in 2010;
-	Rates of non-polio AFP fewer than 2/100,000 children below the age of 15 in 26 districts in 2010
-	Frequent oil inventory shortfalls: two in 2010;
-	The lack of a national waste management policy (in the en cours d’élaboration);
-	The lack of a monitoring and evaluation plan.
Since the introduction of vaccines against viral hepatitis B and haemofilus enfluenzae in 2004, Burundi has cofinanced these vaccines with a 20% contribution every year. Despite its meager income, the Government has always honored its contribution as agreed with GAVIALLIANCE. 
The comprehensive multi-year EPI plan for 2011-2015 proposes ways and means of dealing with these challenges around the following objectives:
1.	Improve the effectiveness of program coordination and management 
2.	Improve planning and including within it micro-planning in the decentralized facilities 
3.	By 2015 increase the Government’s contribution to at least 35% of the EPI budget 
4.	Reach a DTC3 VC rate of at least 80% in 100% of the health districts 
5.	By 2015, reach a total drop-out rate of less than 10% in 100% of the HD 
6.	Reach vaccine coverage for three doses of 13-valent pneumococcal vaccine of 40% at the end of 2011 and 80% in 2012
7.	In 2012 introduce the second dose of measles vaccine 
8.	In 2013, introduce the rotavirus vaccine
9.	By 2015, equip all the HD with computer equipment and vaccine management software 
10.	By 2015, 100% of the district healthcare offices report correct data on AEFI
11.	By 2015, 100% of the district health offices [BDS] provide effective vaccine management
12.	By 2015, cold chain operational at all levels 
13.	By 2015, 100% of the districts equipped with efficient incinerators
14.	Maintain surveillance indicators for target EPI diseases above regional standards

The cMYP refers to the 2006-2015 Global Immunization Vision and Strategy (GIVS) and is aimed at helping officials to plan their vaccination program. The document was created by a multi-disciplinary team consisting of focal points from the Ministry of Finance, the Ministry of Plannng and Development, EPI partners like UNICEF and the WHO, from civil society and officials from the Ministry of Health in collaboration with the Inter-Agency Coordinating Committee (ICC/PFHD).It was revised to introduce the second dose of the measles vaccine in 2012 and to introduce the rotavirus vaccine in 2013.
This submission meets objectives 7 and 8 of our cMYP. Burundi was eligible to introduce the second doses of MCV for 18-month olds in the routine vaccination. The purpose of the MCV dose is to reduce the morbidity and mortality attributable to measles. In fact, despite the fine performance observed in terms of coverage, (MCV coverage rate above 90% since 2007 at the national level), measles epidemics still occur in some districts with low routine vaccination coverage. That being the case, it has been noted that children who have received two doses of MCV have less of a tendency to catch the disease compared to children who have received only one dose. 
In Burundi, the epidemiological situation with regard to diarrhetic diseases due to rotaviruses does not differ from that of other developing countries. In fact, in those countries, 75% of children experience an initial episode of rotavirus diarrhea before the age of 12 months, while in developed countries, often the first episode does not occur before the age of two to five years. Hence this is a major public health problem, especially since every year diarrhetic diseases often occur at the same time as bronchitis or flu epidemices, which can cause problems for pediatric healthcare systems. The revised cMYP took into account the introduction of the rotavirus vaccine and the second dose of the measles vaccine. Thanks to immunization, the developed countries have succeeded in reducing very significantly the number of case of diarrhetic diseases due to rotaviruses. Given the extent and the seriousness of rotavirus-induced diarrhetic diseases, Burumdi plans to introduce the rotavirus vaccine starting in 2013. 
The plans for introducing these vaccines attached to this submission give more details on the activities related to their introduction.

# Signatures

# Signatures of the Government and National Coordinating Bodies

# Government and the Inter-Agency Coordinating Committee for Immunisation

The Government of Burundi would like to expand the existing partnership with the GAVI Alliance for the improvement of the infants routine immunisation programme of the country, and specifically hereby requests for GAVI support for Measles 10 doses/vial Lyophilised , Rotavirus 2-dose schedule introduction.

The Government of Burundi commits itself to developing national immunisation services on a sustainable basis in accordance with the Comprehensive Multi-Year Plan (cMYP) presented with this document. The Government requests that the GAVI Alliance and its partners contribute financial and technical assistance to support immunisation of children as outlined in this application.

Tables 6.(n).5. (where (n) depends on the vaccine) in the NVS section of this application shows the amount of support in either supply or cash that is required from the GAVI Alliance. Tables 6.(n).4. of this application shows the Government financial commitment for the procurement of this new vaccine (NVS support only).

Following the regulations of the internal budgeting and financing cycles the Government will annually release its portion of the co-financing funds in the month of May.

Please note that this application will not be reviewed or approved by the Independent Review Committee (IRC) without the signatures of both the Minister of Health & Minister of Finance or their delegated authority.

Enter the family name in capital letters.

| Minister of Health (or delegated authority) |  | Minister of Finance (or delegated authority) |  |
| --- | --- | --- | --- |
| Name | Hon Dr NTAKARUTIMANA Sabine | Name | Hon Clotilde NIZIGAMA |
| Date |  | Date |  |
| Signature |  | Signature |  |

This report has been compiled by

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Full name | Position | Telephone | Email | Action |
| --- | --- | --- | --- | --- |
| Dr NTAKIRUTIMANA Dorothée | EPI Director | 00257 22223736/ 00257 78860945 | ntakirutimana.dorothee@yahoo.fr |  |
| Dr MARONKO Boniface | Assistant EPI Director | 00257 22223736/ 00257 79928514 | bonymaronko@yahoo.fr |  |
| Dr NDUWIMANA Rose M. Magnifique | EPI/WHO focal point | 00257 79735106 | nduwimanar@bi.afro.who.int |  |
| Dr MANIRAKIZA Déo | EPI/UNICEF focal point | 0257 77733771 | dmanirakiza@unicef.org |  |
| Dr NGIRIGI Liboire | Director General of Public Health | 00257 79735897 | ngirigi@yahoo.fr |  |
| Dr NINTERETSE Hilaire | Director of Health Services and Programs | 00257 79961315 | hilnintere@yahoo.fr |  |
| Dr BAZOMBANZA Pierre Claver | National IMCI focal point | 00257 77736819 | clabazombanza@yahoo.fr |  |
| Dr NIZIGIYIMANA Dionis | MPHAC/EPISTAT | 00257 77788788 | nizigi@hotmail.com |  |
| Mr MANANGA Méschack | Main Inspector | 00257 79988496 | mameschak@yahoo.fr |  |
| Mr SINDAYIKENGERA Isidore | Adviser in the Ministry of Plan and Community Development | 00257 78870070 | bampore006@yahoo.fr |  |
| Mme KAMIKAZI Josiane | Technical adviser at the Ministry of Finance | 00257 77714277 | kajos3@yahoo.fr |  |
| Mr NKINDIYABARIMAKURINDA Sublime | Planning unit | 00257 78368992 | ndisub@yahoo.fr |  |
| Mr NTACONAYIGIZE Bonaventure | Information officer at Center for Cooperation and Development – CARITAS BURUNDI |  | ntacobonauda@yahoo.fr |  |

# National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation

We the members of the ICC, HSCC, or equivalent committee[1] met on the 11.05.2011 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

[1] Inter-agency Coordinating Committee or Health Sector Coordinating Committee, or equivalent committee which has the authority to endorse this application in the country in question.

The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: 11.

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Name/Title | Agency/Organisation | Signature | Action |
| --- | --- | --- | --- |
| Dr NGIRIGI Liboire | Director General of the Ministry of Public Health and AIDS Control |  |  |
| Dr GASHUBIJE Longin | Executive Secretary of the PFHD |  |  |
| Mme MUHORANE Carmen | Adviser, Ministry of Public Health and AIDS Control |  |  |
| Mr NKINDIYABARIMAKURINDA Sublime | Adviser, Ministry of Public Health and AIDS Control |  |  |
| Dr FATIMAHA Moussa | Expert Consultant Public Health Services |  |  |
| Mr NIMPAYE Emile | Database Support Officer -MPHAC |  |  |
| Mr MANIRAKIZA Raphael | Expert Consultant in coordination support Embassy of Belgium |  |  |
| Mr MANIRAMBONA Richard | Research Director -National Institute of Public Health |  |  |
| Dr NIYONGABO Enock | Medical Coordinator – Community of Burundi Pentecostal Churches |  |  |
| Mr NTUNZWENIMANA Fidèle | Admnistrative and Financial Director – Burundi Drug Buying Group |  |  |
| Mme MITASHITA AKIKA | Coordinator - JICA |  |  |
| Mr KIMARARUNGU Alphonse | Consultant - JICA |  |  |
| Dr COUDRAY Michel | Health Plus Evaluation Consultant – European Union |  |  |
| Dr MOREELS Réginald | Adviser - MSPLS/APIMS |  |  |
| DR BOSSUYT Michel | Medical Coordinator - CORDAID |  |  |
| Mme KANYONGA Florence | Administrative and Financial Director - National Institute of Public Health |  |  |
| Dr KAMWENUBUSA Gaudef | Director of the Integrated national program fighting chronic and non-transmissible diseases/MPHAC |  |  |
| Mme KAMIKAZI Josiane | Technical Adviser Ministry of Finance |  |  |
| Mme BALENG Marie Louise | Resident representative/PSI Burundi |  |  |
| Mr NSHIMAYEZU Maximilien | Director General SOUSCOM-TERIMBERE |  |  |
| Dr CREPIN Pascal | Health Project Officer – European Union |  |  |
| Mme MONSEUR Sophie | Program Manager / European Union |  |  |
| Mr NDAYIRAGIJE Innocent | Researcher – Norwegian Refugee Council |  |  |
| Dr NDUWIMANA Rose Marie Magnifique | EPI/WHO focal point - WHO |  |  |
| Dr CIZA Alphonse | NMP/WHO |  |  |
| Mr SWALENSJean Michel | Cultural Attaché - Embassy of Belgium |  |  |
| DR CABORE Joseph | WHO representative |  |  |
| Mr MAMADOU N'DIAYE | Program Coordinator /IMC |  |  |
| Mr HICUBURUNDI Sostène | Director General of Resources - MPHAC |  |  |
| Mme Hedy Ip | UNICEF |  |  |
| Dr NINTERETSE Hilaire | Director of Health Services and Programs |  |  |
| Dr NINTUNZE Jacqueline | Secretary General of the Assocation for Malaria Control |  |  |
| Mr NDIKUMANA Désiré | HSS-GAVI Coordinator |  |  |
| Dr NTAKARUTIMANA Dorothée | Director of the EPI |  |  |
| Mr BARIGENZA Louis | Administrative assistant HSS GAVI |  |  |
| Dr SIBOMANA Célestin | Deputy Director National Blood Transfusion Center |  |  |
| Mme KANYANA Annonciate | EPI Data Manager |  |  |
| Mr MANIRABARUTA Jean Claude | EPI Logistician |  |  |
| Dr NIVYINDIKA Léocadie | Inspector General of Public Health |  |  |
| Mr BUSAGO André | ABS |  |  |

In case the GAVI Secretariat has queries on this submission, please contact

Enter the family name in capital letters.

| Name | Dr NTAKIRUTIMANA Dorothée | Title | Director of the EPI |
| --- | --- | --- | --- |
| Tel no | 00257 22223736/ 00257 78860945 |  |  |
| Fax no |  | Address | PEV Burundi Avenue de l'Hôpital BP:160 Bujumbura Burundi |
| Email | ntakirutimana.dorothee@yahoo.fr |  |  |

# The Inter-Agency Coordinating Committee for Immunisation

Agencies and partners (including development partners and NGOs) supporting immunisation services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC, HSCC, or equivalent committee). The ICC, HSCC, or equivalent committee is responsible for coordinating and guiding the use of the GAVI NVS support. Please provide information about the ICC, HSCC, or equivalent committee in your country in the table below.

Profile of the ICC, HSCC, or equivalent committee

| Name of the committee | Partnership Framework for Health and Development (PFHD) |
| --- | --- |
| Year of constitution of the current committee | 2006 |
| Organisational structure (e.g., sub-committee, stand-alone) |  |
| Frequency of meetings | The last Friday of the month |

Composition

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Function | Title / Organisation | Name |  |
| --- | --- | --- | --- |
| Chair | Ministry of Public Health and AIDS Control | Hon Dr NTAKARUTIMANA Sabine |  |
| Secretary | Director General of Public Health/ WHO | Dr NGIRIGI Liboire /Dr CIZA Alphonse |  |
| Members | Minister of Finance | Hon NIZIGAMA Clotilde | Action |
|  | WHO Representative | Dr CABORE Joseph |  |
|  | UNICEF Representative | Mr DIABATE Souleyman |  |
|  | World Bank Representative | Mme TEMDON Mercy |  |
|  | European Union Representative | Mr STEPHANE de Loecker |  |
|  | UNFPA Representative | Mr MBENGUE Ismaila |  |
|  | DFID Representative | Mr Dave BEER |  |
|  | Swiss Technical Cooperation Representative | Mr TOGNOLA Claudio |  |
|  | CORDAID Chief of Mission | Mr BOSSUYT Michel |  |
|  | Resident Representative of PSI | Mme BALENG Marie Louise |  |
|  | IMC Representative | Mr MAMADOU NDIAYE |  |
|  | AHA Project Manager Representative | Mme Askale BINEGA |  |
|  | Resident Representative of Belgian Technical Cooperation | Mr VAN IMPE Paul |  |
|  | Chief of French Cooperation | Mr Laurent ARNAUX |  |

Major functions and responsibilities of the committee

- Developing/adopting a common vision for developing the healthcare sector and for making the necessary reforms in the sector; - Helping the Government to analyze the situation with regard to the healthcare sector ,proposing appropriate strategies for accelerating healthcare development and reaching the Millenium Development and poverty reduction goals; - Pleading at the highest levels to have major healthcare problems treated adequately at macroeconomic and sectoral levels by attaching special importance to the effective use of the resources in the sector; - Reflecting about possible effective ways to make the health policies in Burundi part of the peace consolidation process; - Supporting the creation of socio-healthcare databanks based on a set of appropriate indicators accepted by all the parties concerned serving as a frame of reference for monitoring and evaluating progress; - Creating operational technical groups if needed to examine in depth some thoughts on certain specific subjects. - Seeing to it that information Is exchanged in order to guarantee excellent communication among the different partners.

Three major strategies to enhance the committee's role and functions in the next 12 months

| 1. |  |
| --- | --- |
| 2. |  |
| 3. |  |

# National Immunization Technical Advisory Group for Immunisation

(If it has been established in the country)

We the members of the NITAG met on the to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: .

In case the GAVI Secretariat has queries on this submission, please contact

Enter the family name in capital letters.

| Name |  | Title |  |
| --- | --- | --- | --- |
| Tel no |  |  |  |
| Fax no |  | Address |  |
| Email |  |  |  |

# The NITAG Group for Immunisation

Profile of the NITAG

| Name of the NITAG |  |
| --- | --- |
| Year of constitution of the current NITAG |  |
| Organisational structure (e.g., sub-committee, stand-alone) |  |
| Frequency of meetings |  |

Composition

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Function | Title / Organisation | Name |  |
| --- | --- | --- | --- |
| Chair |  |  |  |
| Secretary |  |  |  |
| Members |  |  | Action |

Major functions and responsibilities of the NITAG

Three major strategies to enhance the NITAG’s role and functions in the next 12 months

| 1. |  |
| --- | --- |
| 2. |  |
| 3. |  |

# Immunisation Programme Data

Please complete the tables below, using data from available sources. Please identify the source of the data, and the date. Where possible use the most recent data and attach the source document.

- Please refer to the Comprehensive Multi-Year Plan for Immunisation (cMYP) (or equivalent plan) and attach a complete copy (with an Executive Summary) as DOCUMENT NUMBER 4

- Please refer to the two most recent annual WHO/UNICEF Joint Reporting Forms (JRF) on Vaccine Preventable Diseases.

- Please refer to Health Sector Strategy documents, budgetary documents, and other reports, surveys etc, as appropriate.

# Basic facts

For the year 2010 (most recent; specify dates of data provided)

|  | Figure |  | Year | Source |
| --- | --- | --- | --- | --- |
| Total population | 8,444,784 |  | 2010 | GPHC 2008 |
| Infant mortality rate (per 1000) | 101 |  | 2010 | State of the World’s Children UNICEF 2009 |
| Surviving Infants[1] | 312,457 |  | 2010 | GPHC 2008 |
| GNI per capita (US$) | 140 |  | 2010 | State of the World’s Children UNICEF 2010 |
| Total Health Expenditure (THE) as a percentage of GDP | 14.00 | % | 2007 | National Health accounts 2007 |
| General government expenditure on health (GGHE) as % of General government expenditure | 7.40 | % | 2010 | 2010 Public Finance Act |

[1] Surviving infants = Infants surviving the first 12 months of life

Please provide some additional information on the planning and budgeting context in your country; also indicate the name and date of the relevant planning document for health

The Government has drafted and implemented a Poverty Reduction Strategic Framework (PRSF 2007-2010) in which health is taken as a priority and immunization in particular (third focus related to the development of human capital. In taking steps to control poverty, the Government is now drafting a new PRSF for 2011-2015 in which health remains a priority. Immunization is also part of the National Health Policy (2005-2015), and the National Health Development Plan (NHDP) now being finalized; specifically, it is part of its third goal, which stresses reducing maternal and child mortality.. It is the 2011-2015 NHDP that is the reference document for the health planning in effect for that period as well as the 2011-2015 MTEF of the healthcare sector

Is the cMYP (or updated Multi-Year Plan) aligned with this document (timing, content, etc.)?

The cMYP is aligned with the 2011-2015 NHDP for achieving goal 3 concerning the reduction in maternal and child mortality.

Please indicate the national planning budgeting cycle for health

The national planning and budgeting cycle for health is part of the country’s planning and budgeting cycle. It starts with the circular from the Minister of Finance sent out in June of every year inviting the technical ministries, including the ministry of health, to develop estimated expenditures, following the budget conferences that end with the parliamentary session for approval of the finance laws. The execution of the budget begins on 1 January of the following year and ends on 31 December of the same year.

Please indicate the national planning cycle for immunisation

The national planning cycle follows the planning cycle of the Ministry of Public Health. The EPI designs the comprehensive multi-year plan and submits it for approval by the PFHD. At the beginning of each year, an action plan related to the cMYP is designed by the EPI and also submitted for approval by the PFHD. The EPI staff handles the implentation, monitoring and evaluation of the plan. With regard to financial management procedures, the request for funding of the activities contained in the annual action plan is prepared by the EPI, which submits it for approval successively to the Director of Health Services and Programs, the Director General of Health, the Director General of Resources and finally to the Office of the Minister. This process is too long and burdensome for a Program that is sometimes called on to carry out urgent activities, especially in terms of cold chain maintenance. Based on the objectives assigned to the EPI in the NHDP, projects aimed at improving the indicators related to the different EPI operations are identified and further developed at different levels of the healthcare system.

Please indicate if sex disaggregated data (SDD) is used in immunisation routine reporting systems

The immunization data reported are not broken down by sex. With vaccine coverage above 90%, gender disparities in terms of immunization disappear. A recent survey (MPS) in 2009 did not show any significant differences between vaccine coverage for boys (91%) and for girls (90%) for routine EPI.

Please indicate if gender aspects relating to introduction of a new vaccine have been addressed in the introduction plan

No because all the children targeted by the routine EPI, both sexes combined, are taken into account in lans to introduce new vaccines.

# Current vaccination schedule

Traditional, New Vaccines and Vitamin A supplement (refer to cMYP pages)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Vaccine (do not use trade name) | Ages of administration (by routine immunisation services) | Given in entire country | Comments | Action |
| --- | --- | --- | --- | --- |
| BCG | At birth | Yes | Respected |  |
| Polio | At birth, 6, 10, 14 weeks | Yes | respected |  |
| Penta | 6,10 and 14 weeks | Yes | respected |  |
| Measles vaccine | 9 months | Yes | Respected |  |
| TT | Pregnant women TT 1 1st contact, TT 2 after 1 month, TT 3 after 6 months, TT 4 after 1 year, TT 5 after 1 to 3 years | Yes | Respected |  |
| Vitamin A | At 9 months, and then every 6 months until the age of 5 years | Yes | Respected |  |

# Trends of immunisation coverage and disease burden

(as per last two annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases)

| Trends of immunisation coverage (percentage) |  |  |  |  |  | Vaccine preventable disease burden |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine |  | Reported |  | Survey |  | Disease | Number of reported cases |  |
|  |  | 2009 | 2010 | 2009 |  |  | 2009 | 2010 |
| BCG |  | 98 | 93 |  |  | Tuberculosis |  | 321 |
| DTP | DTP1 | 104 | 99 |  |  | Diphtheria | 0 | 0 |
|  | DTP3 | 101 | 96 |  |  | Pertussis | 0 | 0 |
| Polio 3 |  | 96 | 94 |  |  | Polio | 2 | 0 |
| Measles (first dose) |  | 91 | 92 |  |  | Measles | 20 | 495 |
| TT2+ (Pregnant women) |  | 88 | 94 |  |  | NN Tetanus | 11 | 2 |
| Hib3 |  | 101 | 96 |  |  | Hib[2] | 0 | 0 |
| Yellow Fever |  |  |  |  |  | Yellow fever | 0 | 0 |
| HepB3 |  | 101 | 96 |  |  | HepBsero-prevalence[1] |  |  |
| Vitamin A supplement Mothers (< 6 weeks post-delivery) |  |  |  | 49 |  |  |  |  |
| Vitamin A supplement Infants (>6 months) |  | 89 | 99 |  |  |  |  |  |

[1] If available

[2] Note: JRF asks for Hib meningitis

If survey data is included in the table above, please indicate the years the surveys were conducted, the full title and if available, the age groups the data refers to

Basic household survey for monitoring and evaluation of the impact of support to the reimbursement system of the Minimum Package of Health Services (2009 MPS)

# Baseline and Annual Targets

(refer to cMYP pages)

Table 1: baseline figures

| Number | Base Year | Baseline and Targets |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2010 | 2012 | 2013 | 2014 | 2015 |  |  |
| Total births | 366,000 | 416,185 | 426,173 | 436,402 | 446,875 |  |  |
| Total infants' deaths | 30,642 | 88,550 | 90,675 | 92,852 | 95,080 |  |  |
| Total surviving infants | 335,358 | 327,635 | 335,498 | 343,550 | 351,795 |  |  |
| Total pregnant women | 422,239 | 442,750 | 453,376 | 464,257 | 475,399 |  |  |
| Number of infants vaccinated (to be vaccinated) with BCG | 339,584 | 399,538 | 417,650 | 427,674 | 437,938 |  |  |
| BCG coverage (%)[1] | 93% | 96% | 98% | 98% | 98% |  |  |
| Number of infants vaccinated (to be vaccinated) with OPV3 | 315,488 | 321,082 | 328,788 | 336,679 | 344,759 |  |  |
| OPV3 coverage (%)[2] | 94% | 98% | 98% | 98% | 98% |  |  |
| Number of infants vaccinated (or to be vaccinated) with DTP1[3] | 332,362 | 324,359 | 332,143 | 340,115 | 348,277 |  |  |
| Number of infants vaccinated (to be vaccinated) with DTP3[3] | 321,408 | 321,082 | 328,788 | 336,679 | 344,759 |  |  |
| DTP3 coverage (%)[2] | 96% | 98% | 98% | 98% | 98% |  |  |
| Wastage[1] rate in base-year and planned thereafter for DTP (%) | 5% | 5% | 5% | 5% | 5% |  |  |
| Wastage[1] factor in base-year and planned thereafter for DTP | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |  |  |
| Target population vaccinated with 1st dose of Rotavirus |  |  | 150,974 | 302,324 | 348,277 |  |  |
| Target population vaccinated with last dose of Rotavirus |  |  | 134,199 | 292,018 | 344,759 |  |  |
| Rotavirus coverage (%)[2] | 0% | 0% | 40% | 85% | 98% |  |  |
| Infants vaccinated (to be vaccinated) with 1st dose of Measles | 308,358 | 311,253 | 318,723 | 326,373 | 334,205 |  |  |
| Measles coverage (%)[2] | 92% | 95% | 95% | 95% | 95% |  |  |
| Infants vaccinated (to be vaccinated) with 2nd dose of Measles |  | 131,054 | 268,398 | 302,324 | 316,616 |  |  |
| Pregnant women vaccinated with TT+ | 384,135 | 398,475 | 408,038 | 417,831 | 427,859 |  |  |
| TT+ coverage (%)[4] | 91% | 90% | 90% | 90% | 90% |  |  |
| Vit A supplement to mothers within 6 weeks from delivery |  |  |  |  |  |  |  |
| Vit A supplement to infants after 6 months |  |  |  |  |  |  |  |
| Annual DTP Drop-out rate[ ( DTP1 - DTP3 ) / DTP1 ] x 100[5] | 3% | 1% | 1% | 1% | 1% |  |  |

[1] Number of infants vaccinated out of total births

[2] Number of infants vaccinated out of total surviving infants

[3] Indicate total number of children vaccinated with either DTP alone or combined

[4] Number of pregnant women vaccinated with TT+ out of total pregnant women

[5] The formula to calculate a vaccine wastage rate (in percentage):[ ( A – B ) / A ] x 100. Whereby: A = the number of doses distributed for use according to the supply records with correction for stock balance at the end of the supply period; B = the number of vaccinations with the same vaccine in the same period.

# Summary of current and future immunisation budget

(or refer to cMYP pages)

|  | Estimated costs per annum in US$ (in thousand US$) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cost category | Base Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |  |
|  | 2010 | 2012 | 2013 | 2014 | 2015 |  |  |  |  |  |
| Routine Recurrent Cost |  |  |  |  |  |  |  |  |  |  |
| Vaccines (routine vaccines only) | 3,227,781 | 8,578,164 | 13,398,258 | 18,981,426 | 21,915,176 |  |  |  |  |  |
| Traditional vaccines | 494,196 | 628,144 | 703,994 | 792,173 | 892,137 |  |  |  |  |  |
| New and underused vaccines | 2,733,585 | 7,950,020 | 12,694,264 | 18,189,253 | 21,023,039 |  |  |  |  |  |
| Injection supplies | 205,431 | 358,081 | 430,645 | 492,680 | 559,052 |  |  |  |  |  |
| Personnel | 580,200 | 603,640 | 615,713 | 628,027 | 640,588 |  |  |  |  |  |
| Salaries of full-time NIP health workers (immunisation specific) | 55,320 | 57,555 | 58,706 | 59,880 | 61,078 |  |  |  |  |  |
| Per-diems for outreach vaccinators / mobile teams | 524,880 | 546,085 | 557,007 | 568,147 | 579,510 |  |  |  |  |  |
| Transportation | 11,797 | 13,819 | 14,621 | 14,913 | 9,837 |  |  |  |  |  |
| Maintenance and overheads | 64,139 | 143,221 | 212,089 | 282,042 | 291,095 |  |  |  |  |  |
| Training | 50,000 | 52,020 | 53,060 | 54,122 | 55,204 |  |  |  |  |  |
| Social mobilisation and IEC | 60,000 | 119,646 | 122,039 | 124,480 | 126,969 |  |  |  |  |  |
| Disease surveillance | 195,000 | 416,160 | 424,483 | 432,973 | 441,632 |  |  |  |  |  |
| Program management | 135,000 | 140,454 | 143,263 | 146,128 | 149,051 |  |  |  |  |  |
| Other |  |  |  |  |  |  |  |  |  |  |
| Subtotal Recurrent Costs | 4,529,348 | 10,425,205 | 15,414,171 | 21,156,791 | 24,188,604 |  |  |  |  |  |
| Routine Capital Costs |  |  |  |  |  |  |  |  |  |  |
| Vehicle | 0 | 0 | 0 | 0 | 0 |  |  |  |  |  |
| Cold chain equipment | 35,200 | 49,766 | 55,835 | 125,900 | 76,469 |  |  |  |  |  |
| Other capital equipment | 0 | 1,044,041 | 1,063,330 | 1,058,077 | 0 |  |  |  |  |  |
| Subtotal Capital Costs | 35,200 | 1,093,807 | 1,119,165 | 1,183,977 | 76,469 |  |  |  |  |  |
| Campaigns |  |  |  |  |  |  |  |  |  |  |
| Polio | 1,496,850 | 1,815,620 | 1,955,929 | 2,109,352 | 2,277,762 |  |  |  |  |  |
| Measles | 210,393 | 1,193,190 | 0 | 0 | 1,522,326 |  |  |  |  |  |
| Yellow Fever | 0 | 0 | 0 | 0 | 0 |  |  |  |  |  |
| MNT campaigns | 0 | 0 | 0 | 0 | 0 |  |  |  |  |  |
| Other campaigns | 1,117,289 | 1,351,919 | 1,487,111 | 1,635,822 | 1,799,405 |  |  |  |  |  |
| Subtotal Campaign Costs | 2,824,532 | 4,360,729 | 3,443,040 | 3,745,174 | 5,599,493 |  |  |  |  |  |
| GRAND TOTAL | 7,389,080 | 15,879,741 | 19,976,376 | 26,085,942 | 29,864,566 |  |  |  |  |  |

# Summary of current and future financing and sources of funds

Please list in the tables below the funding sources for each type of cost category (if known). Please try and indicate which immunisation program costs are covered from the Government budget, and which costs are covered by development partners (or the GAVI Alliance), and name the partners (or refer to cMYP).

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

|  |  | Estimated costs per annum in US$ (in thousand US$) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cost category | Funding source | Base Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |  |
|  |  | 2010 | 2012 | 2013 | 2014 | 2015 |  |  |  |  |  |
| Routine Recurrent Cost |  |  |  |  |  |  |  |  |  |  |  |
| Total recurring costs | GOV, WHO, GAVI,UNICEF | 4,529,348 | 10,425,205 | 15,414,171 | 21,156,790 | 24,188,604 |  |  |  |  |  |
| Routine Capital Costs |  |  |  |  |  |  |  |  |  |  |  |
| Capital costs |  | 35,200 | 1,093,807 | 1,119,165 | 1,183,977 | 76,469 |  |  |  |  |  |
| Campaigns |  |  |  |  |  |  |  |  |  |  |  |
| SSME , Polio and Measles | GAVI,UNICEF,WHO,GOV | 2,824,532 | 4,360,729 | 3,443,040 | 3,745,174 | 5,599,493 |  |  |  |  |  |
| GRAND TOTAL |  | 7,389,080 | 15,879,741 | 19,976,376 | 26,085,941 | 29,864,566 |  |  |  |  |  |

# New and Under-Used Vaccines (NVS)

Please summarise the cold chain capacity and readiness to accommodate new vaccines, stating how the cold chain expansion (if required) will be financed, and when it will be in place. Please indicate the additional cost, if capacity is not available and the source of funding to close the gap.

At the central level, the EPI has three cold rooms with a capacity of 88.0m3 and 17 freezers. The net positive storage capacity is 23.7m3. This available cold chain capacity is sufficient for the entire period for introducing new vaccines at the central level for two to three deliveries a year (cf. table 6.1). At the intermediate and outreach level, the needs have been estimated until 2015. The gaps identified in terms of cold chain storage capacity are in the process of being filled. The Government, with the support of UNICEF, has prepared a cold chain rehabilitation plan, and the plan is now being implemented.

Please give a summary of the cMYP sections that refer to the introduction of new and under-used vaccines. Outline the key points that informed the decision-making process (data considered etc)

Serious rotavirus gastroenteritis affects mainly children from 6 to 24 months of age. Estimated fatal outcomes in 2004 of 527,000 (between 475,000 and 580,000) concern primarily low income countries. In developing countries, introducing this vaccine in the routine EPI could also reduce the high burden of morbidity from serious rotavirus-induced diarrhea, preventing a substantial number of deaths caused by this illness. This easily helps to reach the millenium development goals by helping to reduce mortality in children below the age of five. In fact, the WHO strongly recommends to countries that they introduce the anti-rotavirus vaccination in national immunization programs in the regions and countries where the data on vaccine effectiveness indicate that it could have a notable impact on public health, and where there are an appropriate infrastructure and funding mechanisms making it possible to use these vaccines over the long term. In Burundi, the epidemiological situation with regard to diarrhetic diseases due to rotaviruses is no different from the situation in other developing countries. In fact, a study done with households at the country level in 2009 showed that 18.5% of children below the age of five had had diarrhea during the two weeks preceding the survey. This frequency varies between 16.3% and 22.3% depending on the region. For children less than six months of age, the frequency is13.2%. This figure rises to 30% for children 6 to 11 months old, and to 31.3% for children 12 to 23 months old before falling to 17.5% for children 24 to 35 months old and falling to 7.4% for children 48 to 59 months old. The peak is reached at the age of 12 to 23 months. The high frequency ages for diarrhea as a reported illness (6 to 23 months) are the ages at which children begin to receive food other than mother’s milk and to explore their environment. Diarrhea is the second leading cause of mortality in children less than five years of age in Burundi behind malaria, and is closely followed by pneumonia. Therefore in 2013 Burundi wants to introduce the rotavirus vaccine in children less than one year of age in order to reduce the number of childhood deaths so it can claim to reach the MDG. Concerning measles, despite the fact that vaccine coverage in the past few years is apparently good, there are still a certain number of children who are not protected from measles, which is at the root of the epidemics observed in some regions of the country. For that, introducing the second dose of measles vaccine will increase immunity in the population in general and in children in particular.

# Capacity and cost (for positive storage)

|  |  | Formula | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| A | Annual positive volume requirement, including new vaccine (litres or m3) Liters | Sum-product of total vaccine doses multiplied by unit packed volume of the vaccine | 33,646 | 42,694 | 51,242 | 54,532 |  |  |  |  |
| B | Existing net positive cold chain capacity (litres or m3) Liters | # | 23,784 | 23,784 | 23,784 | 23,784 |  |  |  |  |
| C | Estimated minimum number of shipments per year required for the actual cold chain capacity | A / B | 2 | 2 | 3 | 3 |  |  |  |  |
| D | Number of consignments / shipments per year | Based on national vaccine shipment plan | 2 | 2 | 3 | 3 |  |  |  |  |
| E | Gap (if any) | ((A / D) - B) | -6,961 | -2,437 | -6,703 | -5,607 |  |  |  |  |
| F | Estimated additional cost of cold chain | US$ | 0 | 0 | 0 | 0 |  |  |  |  |

Please briefly describe how your country plans to move towards attaining financial sustainability for the new vaccines you intend to introduce, how the country will meet the co-financing payments, and any other issues regarding financial sustainability you have considered (refer to the cMYP)

The Government supports the EPI through funds from the HIPC initiative. It started co-financing pentavalent in 2008, and it plans to continue with the new vaccines. Among the strategies to be used to finance the new vaccine will be: - Mobilizing reliable internal and external resources; - Strategies for the effective use of resources. The term internal resources refers to the financing guaranteed by the Government, United Nations agencies, bi-lateral and multi-lateral cooperation and the NGOs working in the healthcare sector as well as the communities. The Government now funds the EPI operating expenses. As part of the initiative for vaccine independence, the State contributes 10% for the purchase of vaccines. In fact, the agreement between GAVI and the Government stipulates that the State must gradually increase its share until it funds a good portion of vaccine purchases. To that end, it will put in place mechanisms involving local businesses in the support of immunization services by creating a national fund for vaccines. Mobilizing external resources: The partnership between the Government and the customary EPI donors will be enhanced so that the new vaccines can be introduced successfully. The estimated cost of the program shows a gradual increase during the GAVI support period, especially after this intervention. The Government of Burundi will make the other partners aware of the need to fill the gap and guarantee the sustainability of the activities. As indicated in the chapter of the FVP on macroeconomic objectives, Burundi is among the fragile and most indebted countires. It was admitted to the HIPC initiative in 2006, which allowed it to receive additional funds to finance programs in the eligible sectors, including health. Thus the Expanded Program for Immunization receives these funds. The Ministry of Public Health and its partners have already made arrangements to form a partnership framework for health and development (PFHD). The PFHD is evolving towards a sector approach, whereby all financing will be put in a common basket. With this approach, all programs, including the EPI, will be taken into account.

# Assessment of burden of relevant diseases (if available)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Disease | Title of the assessment | Date | Results |  |
| --- | --- | --- | --- | --- |

If new or under-used vaccines have already been introduced in your country, please give details of the lessons learned from storage capacity, protection from accidental freezing, staff training, cold chain, logistics, drop-out rate, wastage rate etc., and suggest action points to address them

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Lessons Learned | Action Points |  |
| --- | --- | --- |
| Storage capacity: Increase the volume of the products to be stored | - A new EPI warehouse was built - Two cold rooms were installed in 2004 - Five new freezers were purchased and installed for the EPI in 2010 - Coolers now being purchased.(2011) - Twelve BDS equipped with freezers (2010) - Freezers and refrigerators for the BDS now being purchased (2011) - New fridges now being purchased for the BDS |  |
| Protection from accidental freezing: As the new capacity for keeping vaccines in the positive room was exceeded vaccines are stored next to the evaporator with a risk of freezing the vaccines | New refrigerators with a large storage capacity have been purchased and others are on order |  |
| Personnel training: Need to train immunization agents on the new vaccines | Introducing new vaccines requires training personnel at all levels. With the introduction of the rotavirus vaccine, need to take into account training all healthcare personnel including vaccinators on respecting the target group in order to avoid as much as possible risks of accidents related to this vaccine (intestinal invagination) |  |
| Cold chain logistics: Increase the amount of the different spare parts Increase the amount of oil | Install generators at the provincial health bureau (BPS) and district health offices (BDS) and use of solar plates in the health centers Use of the contribution by PBF(performance based financing) to the purchase of oil. |  |
| Drop-out rate: Focusing on the new vaccine results in an incrase in the drop-out rate for traditional vaccines | The new vaccines are aligned to the preexisting vaccine calendar |  |
| Wastage rate: High wastage rate | Implementing the open vial policy limits wastage of the Hib and HepB vaccines. |  |
| Enlisting community support on a large scale | Proper communications on Hib and HepB resulted in the prompt acceptance of these vaccines |  |

Please list the vaccines to be introduced with support from the GAVI Alliance (and presentation)

- The second dose of measles vaccine in 2012 - The rotavirus vaccine in 2013

# 6.3.1. Requested vaccine ( Measles, 10 doses/vial, Lyophilised )

As reported in the cMYP, the country plans to introduce Measles, 10 doses/vial, Lyophilised vaccine.

# 6.3.2. Co-financing information

No Co-financing for Measles

# 6.3.3. Wastage factor

Please indicate wastage rate:

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Vaccine wastage rate in % | 20% | 20% | 20% | 20% |  |  |  |  |
| Equivalent wastage factor | 1.25 | 1.25 | 1.25 | 1.25 |  |  |  |  |

# 6.3.4. Specifications of vaccinations with new vaccine

|  | Data from |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 311,253 | 318,723 | 326,373 | 334,205 |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 131,054 | 268,398 | 302,324 | 316,616 |  |  |  |  |
| Immunisation coverage with the third dose | Table 1 | # | 95.00% | 95.00% | 95.00% | 95.00% |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[3] | # | 1.25 | 1.25 | 1.25 | 1.25 |  |  |  |  |
| Country co-financing per dose[2] | Table 6.(n).2[3] | $ | 0.00 | 0.00 | 0.00 | 0.00 |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Total price per-dose includes vaccine cost, plus freight, supplies, insurance, visa costs etc.

[3] Where (n) depends on the vaccine

# 6.3.5. Portion of supply to be procured by the country (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Number of vaccine doses | # | 0 | 0 | 0 | 0 |  |  |  |  |
| Number of AD syringes | # | 0 | 0 | 0 | 0 |  |  |  |  |
| Number of re-constitution syringes | # | 0 | 0 | 0 | 0 |  |  |  |  |
| Number of safety boxes | # | 0 | 0 | 0 | 0 |  |  |  |  |
| Total value to be co-financed by country | $ | 0 | 0 | 0 | 0 |  |  |  |  |

# 6.3.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| Number of vaccine doses | # | 204,800 | 378,500 | 388,600 | 400,300 |  |  |  |  |
| Number of AD syringes | # | 191,000 | 345,600 | 347,400 | 356,500 |  |  |  |  |
| Number of re-constitution syringes | # | 22,800 | 42,100 | 43,200 | 44,500 |  |  |  |  |
| Number of safety boxes | # | 2,375 | 4,325 | 4,350 | 4,450 |  |  |  |  |
| Total value to be co-financed by GAVI | $ | 68,000 | 125,000 | 128,000 | 131,500 |  |  |  |  |

# 6.3.7. New and Under-Used Vaccine Introduction Grant

Please indicate in the tables below how the one-time Introduction Grant[1] will be used to support the costs of vaccine introduction and critical pre-introduction activities (refer to the cMYP).

Calculation of lump-sum for the Measles, 10 doses/vial, Lyophilised

If the total is lower than US$100,000, it is automatically rounded up to US$100,000

| Year of New Vaccine Introduction | Births (from Table 1) | Share per Birth in US$ | Total in US$ |
| --- | --- | --- | --- |
| 2012 | 416,185 | 0.30 | 125,000 |

[1] The Grant will be based on a maximum award of $0.30 per infant in the birth cohort with a minimum starting grant award of $100,000

Cost (and finance) to introduce the Measles, 10 doses/vial, Lyophilised (US$)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Cost Category | Full needs for new vaccine introduction in US$ | Funded with new vaccine introduction grant in US$ |  |
| --- | --- | --- | --- |
| Training | 65,000 | 50,000 |  |
| Social Mobilization, IEC and Advocacy | 26,000 | 26,000 |  |
| Cold Chain Equipment & Maintenance | 10,000 | 5,800 |  |
| Vehicles and Transportation | 10,000 | 8,000 |  |
| Programme Management | 15,000 | 5,000 |  |
| Surveillance and Monitoring | 39,000 | 15,000 |  |
| Human Resources | 0 | 0 |  |
| Waste Management | 15,000 | 15,000 |  |
| Technical assistance | 0 | 0 |  |
| Training Supervision | 30000 | 0 |  |
| Totals | 210,000 | 124,800 |  |

# 6.4.1. Requested vaccine ( Rotavirus 2-dose schedule )

As reported in the cMYP, the country plans to introduce Rotavirus 2-dose schedule vaccine.

# 6.4.2. Co-financing information

If you would like to co-finance higher amount than minimum, please overwrite information in the “Your co-financing” row.

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

| Country group | Low |
| --- | --- |

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Minimum co-financing | 0.20 | 0.20 | 0.20 |  |  |  |  |  |
| Your co-financing (please change if higher) | 0.20 | 0.20 | 0.20 |  |  |  |  |  |

# 6.4.3. Wastage factor

Please indicate wastage rate:

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Vaccine wastage rate in % | 5% | 5% | 5% |  |  |  |  |  |
| Equivalent wastage factor | 1.05 | 1.05 | 1.05 |  |  |  |  |  |

# 6.4.4. Specifications of vaccinations with new vaccine

|  | Data from |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 150,974 | 302,324 | 348,277 |  |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 134,199 | 292,018 | 344,759 |  |  |  |  |  |
| Immunisation coverage with the third dose | Table 1 | # | 40.00% | 85.00% | 98.00% |  |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[3] | # | 1.05 | 1.05 | 1.05 |  |  |  |  |  |
| Country co-financing per dose[2] | Table 6.(n).2[3] | $ | 0.20 | 0.20 | 0.20 |  |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Total price per-dose includes vaccine cost, plus freight, supplies, insurance, visa costs etc.

[3] Where (n) depends on the vaccine

# 6.4.5. Portion of supply to be procured by the country (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Number of vaccine doses | # | 15,100 | 34,000 | 39,900 |  |  |  |  |  |
| Number of AD syringes | # |  |  |  |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 175 | 400 | 450 |  |  |  |  |  |
| Total value to be co-financed by country | $ | 79,500 | 143,000 | 151,500 |  |  |  |  |  |

# 6.4.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Number of vaccine doses | # | 381,300 | 680,400 | 715,700 |  |  |  |  |  |
| Number of AD syringes | # |  |  |  |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 4,250 | 7,575 | 7,950 |  |  |  |  |  |
| Total value to be co-financed by GAVI | $ | 2,004,500 | 2,863,000 | 2,711,000 |  |  |  |  |  |

# 6.4.7. New and Under-Used Vaccine Introduction Grant

Please indicate in the tables below how the one-time Introduction Grant[1] will be used to support the costs of vaccine introduction and critical pre-introduction activities (refer to the cMYP).

Calculation of lump-sum for the Rotavirus 2-dose schedule

If the total is lower than US$100,000, it is automatically rounded up to US$100,000

| Year of New Vaccine Introduction | Births (from Table 1) | Share per Birth in US$ | Total in US$ |
| --- | --- | --- | --- |
| 2013 | 426,173 | 0.30 | 128,000 |

[1] The Grant will be based on a maximum award of $0.30 per infant in the birth cohort with a minimum starting grant award of $100,000

Cost (and finance) to introduce the Rotavirus 2-dose schedule (US$)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Cost Category | Full needs for new vaccine introduction in US$ | Funded with new vaccine introduction grant in US$ |  |
| --- | --- | --- | --- |
| Training | 62,000 | 50,000 |  |
| Social Mobilization, IEC and Advocacy | 45,000 | 26,000 |  |
| Cold Chain Equipment & Maintenance | 105,601 | 6,000 |  |
| Vehicles and Transportation | 15,000 | 8,000 |  |
| Programme Management | 15,000 | 5,000 |  |
| Surveillance and Monitoring | 48,000 | 15,000 |  |
| Human Resources | 0 |  |  |
| Waste Management | 10,000 | 18,000 |  |
| Technical assistance | 10,000 | 0 |  |
| Training Supervisions | 30000 | 0 |  |
| Totals | 340,601 | 128,000 |  |

# Procurement and Management of New and Under-Used Vaccines

Note: The PCV vaccine must be procured through UNICEF

- Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that most countries will procure vaccine and injection supplies through UNICEF)

The country submits a request for a quotation for its share of the co-financing to the UNICEF supply department. After obtaining these costs, the country pays the portion to the account of the UNICEF supply division, which in turn takes charge of delivering the vaccines and immunization equipment to the country EPI

- If an alternative mechanism for procurement and delivery of supply (financed by the country or the GAVI Alliance) is requested, please document

- Other vaccines or immunisation commodities procured by the country and descriptions of the mechanism used.

- The functions of the National Regulatory Authority (as evaluated by WHO) to show they comply with WHO requirements for procurement of vaccines and supply of assured quality.

The NRA not yet operational at the Country level

- Please describe the introduction of the vaccines (refer to cMYP)

In 2012, Burundi plans to introduce the second dose of measles vaccine and the rotavirus vaccine in 2013. Concerning measles, despite the good vaccine coverage, measles transmission remains continual, and the first dose is administered at the age of 9 months. Given the extent of the resurgence of measles epidemics, Burundi plans to introduce the second dose of the MCV in the routine immunization starting in 2012. The storage conditions for this vaccine at the central, intermediate and outreach level are all met. The country has experience in administering the first dose, which would explain that the second dose will not cause any problems. Training the personnel before introducing the second dose and the vaccine calendar will be considered. Moreover, information, education and awareness campaigns for political decision-makers and the population will be included in the other IEC activities of the EPI. The EPI management tools will be updated to take into account the second dose of MCV. A post-introduction evaluation of the second dose of MCV will be done after nine to twelve months. A retrospective survey on the prevalence of measles in children who have received the second dose a few years after it is introduced is conceivable. Concerning the rotavirus vaccine, there are plans to introduce it in 2013. The rotavirus vaccine chosen by Burundi is Rotarix in single-dose liquid form. The two required doses of this vaccine are administered orally like the OPV. This choice is justified for the following reasons: Reaching high vaccine coverage quickly (because the vaccine will quickly follow the current trend of the OPV); - Better vaccine stability compared to Rotateq - Administered orally like the OPV - Easy to handle - Ease of complying with age requirements with two doses rather than three, - Cold chain needs less substantial (17.1cm3 for Rotarix and 45.9cm3 for Rotateq, - Rotateq does not carry vaccine vial monitors - Proper control of wastage rate owing to the single-dose liquid form - Keeps at between +2°c and +8°c - The rotavirus vaccine will be introduced on the same day throughout the country and will be administered to all the EPI target children who appear. The vaccine calendar will be the same as for pentavalent and pneumoccal vaccines. Thereafter, all children who come for the first dose of their penta series will receive in addition the first dose of the rotavirus vaccine so as to finish the second dose in the tenth week of the series started beforehand. This will be done while taking into account the fact that, according to the recommendatons, the first dose of Rotarix must be administered between six and fifteen weeks and the second dose is administered no later than the 32nd week (see issue No. 51-52 of the weekly WHO epidemiology report dated 18 December 2009), No catch-up vaccination will be given. The Rotavirus vaccine will be administered orally, while the pentavalent vaccine will be injected in a single intramuscular injection. All agents, both private and public, working in the healthcare area will be trained in the introduction of the Rotavirus vaccine, with emphasis on the need to respect the very specific age instructions and the importance of closer surveillance of the AEFI. Political decision-makers, communities and clinicians will be made aware of the fight against diarrhetic disealses due to rotaviruses and on the benefits of the anti-rotavirus vaccine. There are plans to introduce the anti-rotavirus vaccine in 2013. Several points were considered for setting the time for introducing the new vaccine given the time it takes to make the request and obtain approval from GAVI, and to acquire the funds, and given the deadlines for orders of the new vaccine, personnel training and rehabilitating the cold chain. We also took into account the introduction of the pneumococcal vaccine in 2011 and the introduction of the second dose of the measles vaccine planned for 2012.

- Please indicate how funds should be transferred by the GAVI Alliance (if applicable)

In accordance with the memorandum signed in 2010 between the Government of Burundi and GAVI Alliance, the HSS-GAVI funds will be paid to a sub-account of the Treasury opened at the Central Bank, and these funds will be isolated from the other funds managed by the Public Treasury. These funds will be released from the Treasury sub-account with the signatures of both the Minister of Finance and the Minister of Public Health and AIDS Control.

- Please indicate how the co-financing amounts will be paid (and who is responsible for this)

The Government portions will be paid through UNICEF by bank transfers The person responsble for the operation is the Minister of Public Health/Director of the EPI.

- Please outline how coverage of the new vaccine will be monitored and reported (refer to cMYP)

Vaccine coverage will be monitored through monthly reports on the number of children receiving the second dose of measles vaccine and rotavirus vaccine. The data related to these vaccines will be included in the routine immunization reports. Overall surveillance of vaccine coverage will be done every three years. The main indicator of vaccine coverage for the rotavirus vaccine is rota 2 corresponding to the second dose of polio or penta vaccine in children less than one year of age, while the indicator of measles vaccine coverage will be the number of children who have received this vaccine out of the total number of children ages 12 to 23 months.

# Vaccine Management (EVSM/EVM/VMA)

When was the last Effective Vaccine Store Management (EVSM) conducted? April   - 2011

When was the last Effective Vaccine Management (EVM) or Vaccine Management Assessment (VMA) conducted? April   - 2011

- If your country conducted either EVSM, EVM, or VMA in the past three years, please attach relevant reports. (Document N°13)

- A VMA report must be attached from those countries which have introduced a New and Underused Vaccine with GAVI support before 2008.

- Please note that EVSM and VMA tools have been replaced by an integrated Effective Vaccine Management (EVM) tool. The information on EVM tool can be found at http://www.who.int/immunization_delivery/systems_policy/logistics/en/index6.html

- For countries which conducted EVSM, VMA or EVM in the past, please report on activities carried out as part of either action plan or improvement plan prepared after the EVSM/VMA/EVM.

An Effective Vaccine Management assessment at the national level in April 2011 and measures for improvement were determined based on the recommendations made in the report. We will report on the state of implementation of these measures in our subsequent report.

- When is the next Effective Vaccine Management (EVM) Assessment planned? March  - 2015

- Under new guidelines, it will be mandatory for the countries to conduct an EVM prior to an application for introduction of new vaccine.

# Additional Comments and Recommendations

Comments and Recommendations from the National Coordinating Body (ICC/HSCC)

All the comments and recommendations by the PFHD will be included in the minutes of the different meetings of the PFHD.

# Annexes

# Annex 1

# Annex 1.1 – Measles, 10 doses/vial, Lyophilised

Table 1.1 A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

| Required supply item |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # | 0 | 0 | 0 | 0 |  |  |  |  |
| Number of AD syringes | # | 0 | 0 | 0 | 0 |  |  |  |  |
| Number of re-constitution syringes | # | 0 | 0 | 0 | 0 |  |  |  |  |
| Number of safety boxes | # | 0 | 0 | 0 | 0 |  |  |  |  |
| Total value to be co-financed by the country | $ | 0 | 0 | 0 | 0 |  |  |  |  |

Table 1.1  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

| Required supply item |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # | 204,800 | 378,500 | 388,600 | 400,300 |  |  |  |  |
| Number of AD syringes | # | 191,000 | 345,600 | 347,400 | 356,500 |  |  |  |  |
| Number of re-constitution syringes | # | 22,800 | 42,100 | 43,200 | 44,500 |  |  |  |  |
| Number of safety boxes | # | 2,375 | 4,325 | 4,350 | 4,450 |  |  |  |  |
| Total value to be co-financed by the country | $ | 68,000 | 125,000 | 128,000 | 131,500 |  |  |  |  |

Table 1.1  C - Summary table for Measles, 10 doses/vial, Lyophilised

|  | Data from |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of Surviving infants | Table 1 | # | 327,635 | 335,498 | 343,550 | 351,795 |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 131,054 | 268,398 | 302,324 | 316,616 |  |  |  |  |
| Immunisation coverage with the last dose | Table 1 | # | 95.00% | 95.00% | 95.00% | 95.00% |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 311,253 | 318,723 | 326,373 | 334,205 |  |  |  |  |
| Number of doses per child |  | # | 1 | 1 | 1 | 1 |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[2] | # | 1.25 | 1.25 | 1.25 | 1.25 |  |  |  |  |
| Number of doses per vial |  | # | 10 | 10 | 10 | 10 |  |  |  |  |
| AD syringes required |  | # | Yes | Yes | Yes | Yes |  |  |  |  |
| Reconstitution syringes required |  | # | Yes | Yes | Yes | Yes |  |  |  |  |
| Safety boxes required |  | # | Yes | Yes | Yes | Yes |  |  |  |  |
| Vaccine price per dose |  | $ | 0.240 | 0.240 | 0.240 | 0.240 |  |  |  |  |
| Country co-financing per dose | Table 6.(n).2[2] | $ | 0.00 | 0.00 | 0.00 | 0.00 |  |  |  |  |
| AD syringe price per unit |  | $ | 0.053 | 0.053 | 0.053 | 0.053 |  |  |  |  |
| Reconstitution syringe price per unit |  | $ | 0.038 | 0.038 | 0.038 | 0.038 |  |  |  |  |
| Safety box price per unit |  | $ | 0.640 | 0.640 | 0.640 | 0.640 |  |  |  |  |
| Freight cost as % of vaccines value |  | % | 10.00 | 10.00 | 10.00 | 10.00 |  |  |  |  |
| Freight cost as % of devices value |  | % | 10.00 | 10.00 | 10.00 | 10.00 |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.1 D - Estimated number of doses for Measles, 10 doses/vial, Lyophilised associated injection safety material and related co-financing budget (page 1)

|  |  | Formula | 2012 |  |  | 2013 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 0.00% |  |  | 0.00% |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 131,054 | 0 | 131,054 | 268,398 | 0 | 268,398 |
| C | Number of doses per child | Vaccine parameter | 1 | 1 | 1 | 1 | 1 | 1 |
| D | Number of doses needed | B * C | 131,054 | 0 | 131,054 | 268,398 | 0 | 268,398 |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 |
| F | Number of doses needed including wastage | D * E | 163,818 | 0 | 163,818 | 335,498 | 0 | 335,498 |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 40,955 | 0 | 40,955 | 42,920 | 0 | 42,920 |
| I | Total vaccine doses needed | F + G | 204,773 | 0 | 204,773 | 378,418 | 0 | 378,418 |
| J | Number of doses per vial | Vaccine parameter | 10 | 10 | 10 | 10 | 10 | 10 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 | 190,930 | 0 | 190,930 | 345,563 | 0 | 345,563 |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 | 22,730 | 0 | 22,730 | 42,005 | 0 | 42,005 |
| M | Total of safety boxes (+ 10% of extra need) needed | (K + L) / 100 x 1.11 | 2,372 | 0 | 2,372 | 4,303 | 0 | 4,303 |
| N | Cost of vaccines needed | I * vaccine price per dose | 49,146 | 0 | 49,146 | 90,821 | 0 | 90,821 |
| O | Cost of AD syringes needed | K * AD syringe price per unit | 10,120 | 0 | 10,120 | 18,315 | 0 | 18,315 |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit | 864 | 0 | 864 | 1,597 | 0 | 1,597 |
| Q | Cost of safety boxes needed | M * safety box price per unit | 1,519 | 0 | 1,519 | 2,754 | 0 | 2,754 |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 4,915 | 0 | 4,915 | 9,083 | 0 | 9,083 |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 1,251 | 0 | 1,251 | 2,267 | 0 | 2,267 |
| T | Total fund needed | (N + O + P + Q + R + S) | 67,815 | 0 | 67,815 | 124,837 | 0 | 124,837 |
| U | Total country co-financing | I * country co-financing per dose | 0 |  |  | 0 |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 0.00% |  |  | 0.00% |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.1 D - Estimated number of doses for Measles, 10 doses/vial, Lyophilised associated injection safety material and related co-financing budget (page 2)

|  |  | Formula | 2014 |  |  | 2015 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 0.00% |  |  | 0.00% |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 302,324 | 0 | 302,324 | 316,616 | 0 | 316,616 |
| C | Number of doses per child | Vaccine parameter (schedule) | 1 | 1 | 1 | 1 | 1 | 1 |
| D | Number of doses needed | B * C | 302,324 | 0 | 302,324 | 316,616 | 0 | 316,616 |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 | 1.25 |
| F | Number of doses needed including wastage | D * E | 377,905 | 0 | 377,905 | 395,770 | 0 | 395,770 |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 10,602 | 0 | 10,602 | 4,467 | 0 | 4,467 |
| I | Total vaccine doses needed | F + G | 388,507 | 0 | 388,507 | 400,237 | 0 | 400,237 |
| J | Number of doses per vial | Vaccine parameter | 10 | 10 | 10 | 10 | 10 | 10 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 | 347,348 | 0 | 347,348 | 356,403 | 0 | 356,403 |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 | 43,125 | 0 | 43,125 | 44,427 | 0 | 44,427 |
| M | Total of safety boxes (+ 10% of extra need) needed | (K + L) / 100 x 1.11 | 4,335 | 0 | 4,335 | 4,450 | 0 | 4,450 |
| N | Cost of vaccines needed | I * vaccine price per dose | 93,242 | 0 | 93,242 | 96,057 | 0 | 96,057 |
| O | Cost of AD syringes needed | K * AD syringe price per unit | 18,410 | 0 | 18,410 | 18,890 | 0 | 18,890 |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit | 1,639 | 0 | 1,639 | 1,689 | 0 | 1,689 |
| Q | Cost of safety boxes needed | M * safety box price per unit | 2,775 | 0 | 2,775 | 2,848 | 0 | 2,848 |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 9,325 | 0 | 9,325 | 9,606 | 0 | 9,606 |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 2,283 | 0 | 2,283 | 2,343 | 0 | 2,343 |
| T | Total fund needed | (N + O + P + Q + R + S) | 127,674 | 0 | 127,674 | 131,433 | 0 | 131,433 |
| U | Total country co-financing | I * country co-financing per dose | 0 |  |  | 0 |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 0.00% |  |  | 0.00% |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Annex 1.2 – Rotavirus 2-dose schedule

Table 1.2 A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

| Required supply item |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # |  | 15,100 | 34,000 | 39,900 |  |  |  |  |
| Number of AD syringes | # |  |  |  |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # |  | 175 | 400 | 450 |  |  |  |  |
| Total value to be co-financed by the country | $ |  | 79,500 | 143,000 | 151,500 |  |  |  |  |

Table 1.2  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

| Required supply item |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # |  | 381,300 | 680,400 | 715,700 |  |  |  |  |
| Number of AD syringes | # |  |  |  |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # |  | 4,250 | 7,575 | 7,950 |  |  |  |  |
| Total value to be co-financed by the country | $ |  | 2,004,500 | 2,863,000 | 2,711,000 |  |  |  |  |

Table 1.2  C - Summary table for Rotavirus 2-dose schedule

|  | Data from |  | 2012 | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of Surviving infants | Table 1 | # |  | 335,498 | 343,550 | 351,795 |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # |  | 134,199 | 292,018 | 344,759 |  |  |  |  |
| Immunisation coverage with the last dose | Table 1 | # |  | 40.00% | 85.00% | 98.00% |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # |  | 150,974 | 302,324 | 348,277 |  |  |  |  |
| Number of doses per child |  | # |  | 2 | 2 | 2 |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[2] | # |  | 1.05 | 1.05 | 1.05 |  |  |  |  |
| Number of doses per vial |  | # |  | 1 | 1 | 1 |  |  |  |  |
| AD syringes required |  | # |  | No | No | No |  |  |  |  |
| Reconstitution syringes required |  | # |  | No | No | No |  |  |  |  |
| Safety boxes required |  | # |  | Yes | Yes | Yes |  |  |  |  |
| Vaccine price per dose |  | $ |  | 5.000 | 4.000 | 3.600 |  |  |  |  |
| Country co-financing per dose | Table 6.(n).2[2] | $ |  | 0.20 | 0.20 | 0.20 |  |  |  |  |
| AD syringe price per unit |  | $ |  | 0.053 | 0.053 | 0.053 |  |  |  |  |
| Reconstitution syringe price per unit |  | $ |  |  |  |  |  |  |  |  |
| Safety box price per unit |  | $ |  | 0.640 | 0.640 | 0.640 |  |  |  |  |
| Freight cost as % of vaccines value |  | % |  | 5.00 | 5.00 | 5.00 |  |  |  |  |
| Freight cost as % of devices value |  | % |  | 10.00 | 10.00 | 10.00 |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.2 D - Estimated number of doses for Rotavirus 2-dose schedule associated injection safety material and related co-financing budget (page 1)

|  |  | Formula | 2013 |  |  | 2014 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 3.80% |  |  | 4.75% |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 150,974 | 5,743 | 145,231 | 302,324 | 14,370 | 287,954 |
| C | Number of doses per child | Vaccine parameter | 2 | 2 | 2 | 2 | 2 | 2 |
| D | Number of doses needed | B * C | 301,948 | 11,486 | 290,462 | 604,648 | 28,740 | 575,908 |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |
| F | Number of doses needed including wastage | D * E | 317,046 | 12,061 | 304,985 | 634,881 | 30,177 | 604,704 |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 79,262 | 3,016 | 76,246 | 79,459 | 3,777 | 75,682 |
| I | Total vaccine doses needed | F + G | 396,308 | 15,076 | 381,232 | 714,340 | 33,953 | 680,387 |
| J | Number of doses per vial | Vaccine parameter | 1 | 1 | 1 | 1 | 1 | 1 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 |  |  |  |  |  |  |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | I / 100 x 1.11 | 4,400 | 168 | 4,232 | 7,930 | 377 | 7,553 |
| N | Cost of vaccines needed | I * vaccine price per dose | 1,981,540 | 75,376 | 1,906,164 | 2,857,360 | 135,812 | 2,721,548 |
| O | Cost of AD syringes needed | K * AD syringe price per unit |  |  |  |  |  |  |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 2,816 | 108 | 2,708 | 5,076 | 242 | 4,834 |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 99,077 | 3,769 | 95,308 | 142,868 | 6,791 | 136,077 |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 282 | 11 | 271 | 508 | 25 | 483 |
| T | Total fund needed | (N + O + P + Q + R + S) | 2,083,715 | 79,262 | 2,004,453 | 3,005,812 | 142,868 | 2,862,944 |
| U | Total country co-financing | I * country co-financing per dose | 79,262 |  |  | 142,868 |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 3.80% |  |  | 4.75% |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.2 D - Estimated number of doses for Rotavirus 2-dose schedule associated injection safety material and related co-financing budget (page 2)

|  |  | Formula | 2015 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 5.28% |  |  |  |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 348,277 | 18,390 | 329,887 |  |  |  |
| C | Number of doses per child | Vaccine parameter (schedule) | 2 | 2 | 2 | 2 | 2 | 2 |
| D | Number of doses needed | B * C | 696,554 | 36,779 | 659,775 |  |  |  |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.05 | 1.05 | 1.05 |  |  |  |
| F | Number of doses needed including wastage | D * E | 731,382 | 38,618 | 692,764 |  |  |  |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 24,126 | 1,274 | 22,852 |  |  |  |
| I | Total vaccine doses needed | F + G | 755,508 | 39,892 | 715,616 |  |  |  |
| J | Number of doses per vial | Vaccine parameter | 1 | 1 | 1 | 1 | 1 | 1 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 |  |  |  |  |  |  |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | I / 100 x 1.11 | 8,387 | 443 | 7,944 |  |  |  |
| N | Cost of vaccines needed | I * vaccine price per dose | 2,719,829 | 143,610 | 2,576,219 |  |  |  |
| O | Cost of AD syringes needed | K * AD syringe price per unit |  |  |  |  |  |  |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 5,368 | 284 | 5,084 |  |  |  |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 135,992 | 7,181 | 128,811 |  |  |  |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 537 | 29 | 508 |  |  |  |
| T | Total fund needed | (N + O + P + Q + R + S) | 2,861,726 | 151,102 | 2,710,624 |  |  |  |
| U | Total country co-financing | I * country co-financing per dose | 151,102 |  |  |  |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 5.28% |  |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Annex 2

Estimated prices of supply and related freight cost: 2011 from UNICEF Supply Division; 2012 onwards: GAVI Secretariat

Table A - Commodities Cost

| Vaccine | Presentation | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AD syringe | 0 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 |
| DTP-HepB | 2 | 1.600 |  |  |  |  |  |  |
| DTP-HepB | 10 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-Hib | 10 | 3.400 | 3.400 | 3.400 | 3.400 | 3.400 | 3.200 | 3.200 |
| HepB monoval | 1 |  |  |  |  |  |  |  |
| HepB monoval | 2 |  |  |  |  |  |  |  |
| Hib monoval | 1 | 3.400 |  |  |  |  |  |  |
| Measles | 10 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 |
| Pneumococcal(PCV10) | 2 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 |
| Pneumococcal(PCV13) | 1 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 |
| Reconstit syringe for Pentaval (2ml) | 0 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 |
| Reconstit syringe for YF | 0 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 |
| Rotavirus 2-dose schedule | 1 | 7.500 | 6.000 | 5.000 | 4.000 | 3.600 | 3.600 | 3.600 |
| Rotavirus 3-dose schedule | 1 | 5.500 | 4.000 | 3.333 | 2.667 | 2.400 | 2.400 | 2.400 |
| Safety box | 0 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 |
| Yellow Fever | WAP | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 |
| Yellow Fever | WAP | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 |

Note: WAP - weighted average price (to be used for any presentation: For DTP-HepB-Hib, it applies to 1 dose liquid, 2 dose lyophilised and 10 dose liquid. For Yellow Fever, it applies to 5 dose lyophilised and 10 dose lyophilised)

Table B - Commodities Freight Cost

| Vaccines | Group | No Threshold | 200’000 $ |  | 250’000 $ |  | 2’000’000 $ |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | <= | > | <= | > | <= | > |
| Yellow Fever | Yellow Fever |  | 20% |  |  |  | 10% | 5% |
| DTP+HepB | HepB and or Hib | 2% |  |  |  |  |  |  |
| DTP-HepB-Hib | HepB and or Hib |  |  |  | 15% | 3,50% |  |  |
| Pneumococcal vaccine (PCV10) | Pneumococcal | 5% |  |  |  |  |  |  |
| Pneumococcal vaccine (PCV13) | Pneumococcal | 5% |  |  |  |  |  |  |
| Rotavirus | Rotavirus | 5% |  |  |  |  |  |  |
| Measles | Measles | 10% |  |  |  |  |  |  |

Table C - Low - Minimum country's co-payment per dose of co-financed vaccine.

| vaccine | 2012 | 2013 | 2014 | 2015 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Measles, 10 doses/vial, Lyophilised | 0.00 | 0.00 | 0.00 | 0.00 |  |  |  |
| Rotavirus 2-dose schedule |  | 0.20 | 0.20 | 0.20 |  |  |  |

Table D - Wastage rates and factors

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2 | 2.22 | 2.5 |

WHO International shipping guidelines: maximum packed volumes of vaccines

Table E - Vaccine maximum packed volumes

| Vaccine product | Designation | Vaccine formulation | Admin route | No. Of doses in the schedule | Presentation (doses/vial, prefilled) | Packed volume vaccine (cm3/dose) | Packed volume diluents (cm3/dose) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| BCG | BCG | lyophilized | ID | 1 | 20 | 1.2 | 0.7 |
| Diphtheria-Tetanus-Pertussis | DTP | liquid | IM | 3 | 20 | 2.5 |  |
| Diphtheria-Tetanus-Pertussis | DTP | liquid | IM | 3 | 10 | 3.0 |  |
| Diphtheria-Tetanus | DT | liquid | IM | 3 | 10 | 3.0 |  |
| Tetanus-Diphtheria | Td | liquid | IM | 2 | 10 | 3.0 |  |
| Tetanus Toxoid | TT | liquid | IM | 2 | 10 | 3.0 |  |
| Tetanus Toxoid | TT | liquid | IM | 2 | 20 | 2.5 |  |
| Tetanus Toxoid UniJect | TT | liquid | IM | 2 | Uniject | 12.0 |  |
| Measles | Measles | lyophilized | SC | 1 | 1 | 26.1 | 20.0 |
| Measles | Measles | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles | Measles | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles | Measles | lyophilized | SC | 1 | 10 | 3.5 | 4.0 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 1 | 26.1 | 26.1 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 1 | 26.1 | 26.1 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 10 | 3.0 | 4.0 |
| Polio | OPV | liquid | Oral | 4 | 10 | 2.0 |  |
| Polio | OPV | liquid | Oral | 4 | 20 | 1.0 |  |
| Yellow fever | YF | lyophilized | SC | 1 | 5 | 6.5 | 7.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 10 | 2.5 | 3.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 20 | 1.5 | 2.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 50 | 0.7 | 1.0 |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 1 | 9.7 |  |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 2 | 6.0 |  |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 10 | 3.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 1 | 18.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 2 | 13.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 6 | 4.5 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 10 | 4.0 |  |
| Hepatitis B UniJect | HepB | liquid | IM | 3 | Uniject | 12.0 |  |
| Hib liquid | Hib_liq | liquid | IM | 3 | 1 | 15.0 |  |
| Hib liquid | Hib_liq | liquid | IM | 3 | 10 | 2.5 |  |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 1 | 13.0 | 35.0 |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 2 | 6.0 |  |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 10 | 2.5 | 3.0 |
| DTP liquid + Hib freeze-dried | DTP+Hib | liquid+lyop. | IM | 3 | 1 | 45.0 |  |
| DTP-Hib combined liquid | DTP+Hib | liquid+lyop. | IM | 3 | 10 | 12.0 |  |
| DTP-Hib combined liquid | DTP-Hib | liquid | IM | 3 | 1 | 32.3 |  |
| DTP-HepB liquid + Hib freeze-dried | DTP-Hib | liquid | IM | 3 | 10 | 2.5 |  |
| DTP-HepB liquid + Hib freeze-dried | DTP-HepB+Hib | liquid+lyop. | IM | 3 | 1 | 22.0 |  |
| DTP-HepB-Hib liquid | DTP-HepB+Hib | liquid+lyop. | IM | 3 | 2 | 11.0 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 10 | 4.4 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 2 | 13.1 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 1 | 19.2 |  |
| Meningitis A/C | MV_A/C | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis A/C | MV_A/C | lyophilized | SC | 1 | 50 | 1.5 | 3.0 |
| Meningococcal A/C/W/ | MV_A/C/W | lyophilized | SC | 1 | 50 | 1.5 | 3.0 |
| Meningococcal A/C/W/Y | MV_A/C/W/Y | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis W135 | MV_W135 | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis A conjugate | Men_A | lyophilized | SC | 2 | 10 | 2.6 | 4.0 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 10 | 15.0 |  |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 10 | 8.1 | 8.1 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 5 | 2.5 | 2.9 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 1 | 12.6 | 11.5 |
| Japanese Encephalitis | JE_liq | liquid | SC | 3 | 10 | 3.4 |  |
| Rota vaccine | Rota_lyo | lyophilized | Oral | 2 | 1 | 156.0 |  |
| Rota vaccine | Rota_liq | liquid | Oral | 2 | 1 | 17.1 |  |
| Rota vaccine | Rota_liq | liquid | Oral | 3 | 1 | 45.9 |  |
| Pneumo. conjugate vaccine 7-valent | PCV-7 | liquid | IM | 3 | PFS | 55.9 |  |
| Pneumo. conjugate vaccine 7-valent | PCV-7 | liquid | IM | 3 | 1 | 21.0 |  |
| Pneumo. conjugate vaccine 10-valent | PCV-10 | liquid | IM | 3 | 1 | 11.5 |  |
| Pneumo. conjugate vaccine 10-valent | PCV-10 | liquid | IM | 3 | 2 | 4.8 |  |
| Pneumo. conjugate vaccine 13-valent | PCV-13 | liquid | IM | 3 | 1 | 12.0 |  |
| Polio inactivated | IPV | liquid | IM | 3 | PFS | 107.4 |  |
| Polio inactivated | IPV | liquid | IM | 3 | 10 | 2.5 |  |
| Polio inactivated | IPV | liquid | IM | 3 | 1 | 15.7 |  |
| Human Papilomavirus vaccine | HPV | liquid | IM | 3 | 1 | 15.0 |  |
| Human Papilomavirus vaccine | HPV | liquid | IM | 3 | 2 | 5.7 |  |
| Monovalent OPV-1 | mOPV1 | liquid | Oral |  | 20 | 1.5 |  |
| Monovalent OPV-3 | mOPV3 | liquid | Oral |  | 20 | 1.5 |  |

# Attachments

# List of Supporting Documents Attached to this Proposal

| Document | Section | Document Number | Mandatory[1] |
| --- | --- | --- | --- |
| MoH Signature (or delegated authority) of Proposal |  | 1 | Yes |
| MoF Signature (or delegated authority) of Proposal |  | 3 | Yes |
| Signatures of ICC or HSCC or equivalent in Proposal |  | 8 | Yes |
| Minutes of ICC/HSCC meeting endorsing Proposal |  | 11 | Yes |
| comprehensive Multi Year Plan - cMYP |  | 4 | Yes |
| cMYP Costing tool for financial analysis |  | 7 | Yes |
| Minutes of last three ICC/HSCC meetings |  | 12 | Yes |
| Improvement plan based on EVM |  | 10, 13 | Yes |
| WHO/UNICEF Joint Reporting Form (JRF) |  | 2 |  |
| ICC/HSCC workplan for forthcoming 12 months |  | 9 |  |
| National policy on injection safety |  |  |  |
| Action plans for improving injection safety |  |  |  |
| Plan for NVS introduction (if not part of cMYP) |  | 5, 6 |  |
| Banking details |  |  |  |

[1] Please indicate the duration of the plan / assessment / document where appropriate

# Attachments

List of all the mandatory and optional documents attached to this form

Note: Use the Upload file arrow icon to upload the document. Use the Delete item icon to delete a line. To add new lines click on the New item icon in the Action column.

| ID | File type | File name |  | New file | Actions |
| --- | --- | --- | --- | --- | --- |
|  | Description | Date and Time | Size |  |  |
| 1 | File Type: MoH Signature (or delegated authority) of Proposal * File Desc: Point 4.1.1 corresponds to the signatures of the governement. That page was completed, printed and signed by both Ministers: the Minister of Finance and the Minister of Health. | File name: Signature Proposal.pdf Date/Time: 26.05.2011 05:19:06 Size: 299 KB |  |  |  |
| 2 | File Type: WHO/UNICEF Joint Reporting Form (JRF) File Desc: | File name: BUU_JRF_data_pour_2010_français_AFR_ 04 April 11.xls Date/Time: 26.05.2011 05:22:49 Size: 433 KB |  |  |  |
| 3 | File Type: MoF Signature (or delegated authority) of Proposal * File Desc: Pint 4.1.1 corresponds to the signatures of the governement. That page was completed, printed and signed by both Ministers: the MoF and the MoH | File name: Signature Proposal.pdf Date/Time: 26.05.2011 05:26:23 Size: 299 KB |  |  |  |
| 4 | File Type: comprehensive Multi Year Plan - cMYP * File Desc: | File name: PPAC Burundi 2011_ 2015. .zip Date/Time: 26.05.2011 05:49:32 Size: 630 KB |  |  |  |
| 5 | File Type: Plan for NVS introduction (if not part of cMYP) File Desc: | File name: BDI Plan d'introduction VAR.zip Date/Time: 26.05.2011 05:59:25 Size: 501 KB |  |  |  |
| 6 | File Type: Plan for NVS introduction (if not part of cMYP) File Desc: | File name: BDI Plan d'introduction du vaccin contre le Rotavirus .zip Date/Time: 26.05.2011 06:04:06 Size: 551 KB |  |  |  |
| 7 | File Type: cMYP Costing tool for financial analysis * File Desc: | File name: cMYP_Costing_Tool_Vs 2 5_Fr. finale BURUNDI 27 4 11 rev.zip Date/Time: 26.05.2011 06:08:12 Size: 825 KB |  |  |  |
| 8 | File Type: Signatures of ICC or HSCC or equivalent in Proposal * File Desc: | File name: Signatures des membres du PFHD.zip Date/Time: 26.05.2011 06:19:37 Size: 767 KB |  |  |  |
| 9 | File Type: ICC/HSCC workplan for forthcoming 12 months File Desc: | File name: Plan d'action du PFHD.zip Date/Time: 26.05.2011 07:55:59 Size: 570 KB |  |  |  |
| 10 | File Type: Improvement plan based on EVM * File Desc: | File name: Plan d'amélioration basée sur la GEV.doc Date/Time: 26.05.2011 09:49:41 Size: 43 KB |  |  |  |
| 11 | File Type: Minutes of ICC/HSCC meeting endorsing Proposal * File Desc: | File name: Réunions du 11 mai 2011.zip Date/Time: 27.05.2011 10:45:14 Size: 251 KB |  |  |  |
| 12 | File Type: Minutes of last three ICC/HSCC meetings * File Desc: | File name: Trois dernières réunions PFHD.zip Date/Time: 27.05.2011 10:56:53 Size: 620 KB |  |  |  |
| 13 | File Type: Improvement plan based on EVM * File Desc: Efficient Vaccine Management Assessment report completed in April 2011 | File name: Rapport_GEV_Burundi_Avril_2011.pdf Date/Time: 27.05.2011 14:17:37 Size: 386 KB |  |  |  |