GAVI Alliance

Application Form for Country Proposals

For Support to New and Under-Used Vaccines (NVS)

Submitted by

The Government of

Central African Republic

Date of submission: 31.05.2011 14:12:03

Deadline for submission: 1 Jun 2011

Select Start and End Year of your Comprehensive Multi-Year Plan (cMYP)

| Start Year | 2011 | End Year | 2015 |
| --- | --- | --- | --- |

Revised in January 2011

(To be used with Guidelines of December 2010)

Please submit the Proposal using the online platform https://AppsPortal.gavialliance.org/PDExtranet.

Enquiries to: proposals@gavialliance.org or representatives of a GAVI partner agency. The documents can be shared with GAVI partners, collaborators and general public. The Proposal and attachments must be submitted in English, French, Spanish, or Russian.

Note: Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline.

The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents will be shared with the GAVI Alliance partners and the general public.

GAVI ALLIANCE GRANT TERMS AND CONDITIONS FUNDING USED SOLELY FOR APPROVED PROGRAMMES The applicant country (“Country”) confirms that all funding provided by the GAVI Alliance will be used and applied for the sole purpose of fulfilling the programme(s) described in the Country’s application. Any significant change from the approved programme(s) must be reviewed and approved in advance by the GAVI Alliance. All funding decisions for the application are made at the discretion of the GAVI Alliance Board and are subject to IRC processes and the availability of funds. AMENDMENT TO THE APPLICATION The Country will notify the GAVI Alliance in its Annual Progress Report if it wishes to propose any change to the programme(s) description in its application. The GAVI Alliance will document any change approved by the GAVI Alliance, and the Country’s application will be amended. RETURN OF FUNDS The Country agrees to reimburse to the GAVI Alliance all funding amounts that are not used for the programme(s) described in its application. The country’s reimbursement must be in US dollars and be provided, unless otherwise decided by the GAVI Alliance, within sixty (60) days after the Country receives the GAVI Alliance’s request for a reimbursement and be paid to the account or accounts as directed by the GAVI Alliance. SUSPENSION/ TERMINATION The GAVI Alliance may suspend all or part of its funding to the Country if it has reason to suspect that funds have been used for purpose other than for the programmes described in the Country’s application, or any GAVI Alliance-approved amendment to the application. The GAVI Alliance retains the right to terminate its support to the Country for the programmes described in its application if a misuse of GAVI Alliance funds is confirmed. ANTICORRUPTION The Country confirms that funds provided by the GAVI Alliance shall not be offered by the Country to any third person, nor will the Country seek in connection with its application any gift, payment or benefit directly or indirectly that could be construed as an illegal or corrupt practice. AUDITS AND RECORDS The Country will conduct annual financial audits, and share these with the GAVI Alliance, as requested. The GAVI Alliance reserves the right, on its own or through an agent, to perform audits or other financial management assessment to ensure the accountability of funds disbursed to the Country. The Country will maintain accurate accounting records documenting how GAVI Alliance funds are used. The Country will maintain its accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of GAVI Alliance funds. If there is any claims of misuse of funds, Country will maintain such records until the audit findings are final. The Country agrees not to assert any documentary privilege against the GAVI Alliance in connection with any audit. CONFIRMATION OF LEGAL VALIDITY The Country and the signatories for the Country confirm that its application, and Annual Progress Report, are accurate and correct and form legally binding obligations on the Country, under the Country’s law, to perform the programmes described in its application, as amended, if applicable, in the APR. CONFIRMATION OF COMPLIANCE WITH THE GAVI ALLIANCE TRANSPARANCY AND ACCOUNTABILITY POLICY The Country confirms that it is familiar with the GAVI Alliance Transparency and Accountability Policy (TAP) and complies with the requirements therein. USE OF COMMERCIAL BANK ACCOUNTS The Country is responsible for undertaking the necessary due diligence on all commercial banks used to manage GAVI cash-based support. The Country confirms that it will take all responsibility for replenishing GAVI cash support lost due to bank insolvency, fraud or any other unforeseen event. ARBITRATION Any dispute between the Country and the GAVI Alliance arising out of or relating to its application that is not settled amicably within a reasonable period of time, will be submitted to arbitration at the request of either the GAVI Alliance or the Country. The arbitration will be conducted in accordance with the then-current UNCITRAL Arbitration Rules. The parties agree to be bound by the arbitration award, as the final adjudication of any such dispute. The place of arbitration will be Geneva, Switzerland. The language of the arbitration will be English. For any dispute for which the amount at issue is US$ 100,000 or less, there will be one arbitrator appointed by the GAVI Alliance. For any dispute for which the amount at issue is greater than US $100,000 there will be three arbitrators appointed as follows: The GAVI Alliance and the Country will each appoint one arbitrator, and the two arbitrators so appointed will jointly appoint a third arbitrator who shall be the chairperson. The GAVI Alliance will not be liable to the country for any claim or loss relating to the programmes described in the application, including without limitation, any financial loss, reliance claims, any harm to property, or personal injury or death. Country is solely responsible for all aspects of managing and implementing the programmes described in its application.

# Application Specification

Please specify for which type of GAVI support you would like to apply to.

Important note: To enable proper functioning of the form, please first select the cMYP years on the previous page.

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Type of Support | Vaccine | Start Year | End Year | Preferred second presentation[1] | Action |
| --- | --- | --- | --- | --- | --- |
| New Vaccines Support | Rotavirus 2-dose schedule | 2013 | 2015 | Rotavirus 3-dose schedule |  |

[1] This "Preferred second presentation" will be used in case there is no supply available for the preferred presentation of the selected vaccine ("Vaccine" column). If left blank, it will be assumed that the country will prefer waiting until the selected vaccine becomes available.

# Table of Contents

Sections

Main

Cover Page

GAVI Alliance Grants Terms and Conditions

1. Application Specification

2. Table of Contents

3. Executive Summary

4. Signatures

4.1. Signatures of the Government and National Coordinating Bodies

4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation

4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation

4.1.3. The Inter-Agency Coordinating Committee for Immunisation

4.2. National Immunization Technical Advisory Group for Immunisation

4.2.1. The NITAG Group for Immunisation

5. Immunisation Programme Data

5.1. Basic facts

5.2. Current vaccination schedule

5.3. Trends of immunisation coverage and disease burden

5.4. Baseline and Annual Targets

Table 1: baseline figures

5.5. Summary of current and future immunisation budget

5.6. Summary of current and future financing and sources of funds

6. NVS

6.1. Capacity and cost (for positive storage)

6.2. Assessment of burden of relevant diseases (if available)

6.3.1. Requested vaccine ( Rotavirus 2-dose schedule )

6.3.2. Co-financing information

6.3.3. Wastage factor

6.3.4. Specifications of vaccinations with new vaccine

6.3.5. Portion of supply to be procured by the country (and cost estimate, US$)

6.3.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

6.3.7. New and Under-Used Vaccine Introduction Grant

7. Procurement and Management of New and Under-Used Vaccines

7.1. Vaccine management (EVSM/EVM/VMA)

8. Additional Comments and Recommendations

9. Annexes

Annex 1

Annex 1.1 - Rotavirus 2-dose schedule

Table 1.1  A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

Table 1.1  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

Table 1.1  C - Summary table for vaccine Rotavirus 2-dose schedule

Table 1.1  D - Estimated number of doses for vaccine Rotavirus 2-dose schedule associated injection safety material and related co-financing budget

Annex 2

10. Attachments

10.1 Documents required for NVS support

10.2 Attachments

Banking Form

# Executive Summary

Rotavirus is the most common cause of severe diarrheal disease in infants and young children worldwide. According to 2004 WHO estimates, 527 000 (475 000–580 000) children under five years of age die each year from a vaccine-preventable rotavirus infection, primarily in low-income countries. In sub-Saharan Africa there are 110–230 000 deaths related to rotavirus infections each year. Surveillance data show that rotavirus infections account for 40% of hospitalizations for diarrheal disease worldwide. 
The preliminary findings of a study on rotavirus conducted in February–September 2008 by the Institut Pasteur de Bangui on 250 stool samples collected from children 0–5 years during visits for acute diarrhea at the pediatric ward of the Centre National Hospitalier et Universitaire de Bangui (CPB) showed that 100 samples (40%) tested positive for rotavirus using the VIKIA Rota-Adeno (BioMérieux) sensitive particle agglutination technique.

While there is a broad diversity of viral strains, five serotype combinations (G1P[8], G2P[4], G3P[8], G4P[8] and G9P[8]) are the source of about 90% of all human rotavirus infections, with the G1P[8] serotype having the highest incidence. Rotaviruses are faeco-orally transmitted and affect a large majority of children worldwide before the age of three, and children in most developing countries before their first birthday. 
Two new types of oral live attenuated rotavirus vaccines were authorized in 2006: the monovalent human rotavirus vaccine (RotarixTM) and the pentavalent human-bovine reassortant vaccine (RotaTeqTM). In its 2007 information note on rotavirus vaccines, WHO recommended including the rotavirus vaccine in national immunization programmes in regions where the data on its effectiveness suggest it would have a significant effect on public health—i.e., mostly in the Americas and Europe. As of 2009, WHO recommends immunizing infants worldwide against rotavirus infections.

The current rotavirus vaccines are deemed equally safe and effective, but their antigen compositions and administration schedules differ. They generally confer approximately 90–100% protection against severe rotavirus infections and about 74–85% protection against all rotavirus diarrhea, depending on administration schedule and population evaluated. It has been shown that the protection conferred against severe rotavirus infection persists during the second year of monitoring for these two vaccines.

In order to increase the spectrum of protection for children in CAR against vaccine-preventable disease and thus play a more effective role in reducing child mortality and morbidity, the Ministry of Public Health, Population and AIDS Control, in accordance with the 2011–2015 cMYP, proposes to introduce the rotavirus vaccine into the routine immunization programme in 2003. 
According to the 2011–2015 cMYP, the immunization coverage goal set for rotavirus is 60% of children less than one year of age immunized in 2011, and 70% by 2015.
Given the availability on the international market of both types of vaccine, CAR opted for the single-dose liquid Rotarix as its first choice for the following reasons: 2-dose administration and cross-protection for several strains.  

It should be noted that CAR has received GAVI support since 2008 for the introduction of the two new vaccines into routine EPI, i.e., the pentavalent vaccine and the pneumococcal vaccine that will be introduced in July 2011. This introduction of the two new vaccines will enable CAR to reduce morbidity and mortality caused by vaccine-preventable disease.

The introduction of the rotavirus vaccine beginning in 2013 will increase the storage capacity requirement by 5 001 additional litres at the national storage facility level. The net available capacity of 15 000 litres is sufficient to cover the storage needs for all routine vaccines until 2015. 

Nevertheless, given the fact that the current cold rooms are expected to be replaced in 2012 because of obsolescence, it is prudent to plan for procurement of three 15 000–liter cold rooms, one in 2012 and one in 2014, to allow for greater flexibility during mass immunization campaigns. The cost of these three cold rooms is estimated at US$ 324 375.

# Signatures

# Signatures of the Government and National Coordinating Bodies

# Government and the Inter-Agency Coordinating Committee for Immunisation

The Government of Central African Republic would like to expand the existing partnership with the GAVI Alliance for the improvement of the infants routine immunisation programme of the country, and specifically hereby requests for GAVI support for Rotavirus 2-dose schedule introduction.

The Government of Central African Republic commits itself to developing national immunisation services on a sustainable basis in accordance with the Comprehensive Multi-Year Plan (cMYP) presented with this document. The Government requests that the GAVI Alliance and its partners contribute financial and technical assistance to support immunisation of children as outlined in this application.

Tables 6.(n).5. (where (n) depends on the vaccine) in the NVS section of this application shows the amount of support in either supply or cash that is required from the GAVI Alliance. Tables 6.(n).4. of this application shows the Government financial commitment for the procurement of this new vaccine (NVS support only).

Following the regulations of the internal budgeting and financing cycles the Government will annually release its portion of the co-financing funds in the month of October.

Please note that this application will not be reviewed or approved by the Independent Review Committee (IRC) without the signatures of both the Minister of Health & Minister of Finance or their delegated authority.

Enter the family name in capital letters.

| Minister of Health (or delegated authority) |  | Minister of Finance (or delegated authority) |  |
| --- | --- | --- | --- |
| Name | Mme Marguerite PETRO KONI-ZEZE ZARAMBAUD, Acting Minister of Health | Name | Sylvain NDOUTINGAÏ |
| Date |  | Date |  |
| Signature |  | Signature |  |

This report has been compiled by

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Full name | Position | Telephone | Email | Action |
| --- | --- | --- | --- | --- |
| Rock OUAMBITA-MABO | Director of EPI | (00236) 70407808 | ouambita_mr@yahoo.fr |  |

# National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation

We the members of the ICC, HSCC, or equivalent committee[1] met on the 09 April 2011 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

[1] Inter-agency Coordinating Committee or Health Sector Coordinating Committee, or equivalent committee which has the authority to endorse this application in the country in question.

The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: 4.

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Name/Title | Agency/Organisation | Signature | Action |
| --- | --- | --- | --- |
| Zakaria MAIGA/Representative | WHO |  |  |
| Tanya CHAPUISAT/Representative | UNICEF |  |  |
| Antoine MBAO BOGO/ President | Central African Red Cross |  |  |
| Jeannette GBROUKA, National Director | SOS Children’s Village |  |  |
| Emmanuel DJADA, Mission Chief | Ministry of Family, Social Affairs and National Solidarity |  |  |
| Philémon DERANT LAKOUE, Chief of Staff | Ministry of Communication, National Reconciliation and Peace Culture |  |  |
| Louis NAMBOUA/Director General of Public Health | Ministry of Public Health |  |  |
| Germain WAMOUSTOYO/Director General of the Budget | Ministry of Finance and Budget |  |  |
| Irène POUNEBINGUI/Department Head | Ministry of Economy, Planning and International Cooperation |  |  |
| Christian YANGUE/Representative | Rotary International |  |  |

In case the GAVI Secretariat has queries on this submission, please contact

Enter the family name in capital letters.

| Name | Rosk OUAMBITA-MABO | Title | Director of EPI |
| --- | --- | --- | --- |
| Tel no | (00236) 70407808 |  |  |
| Fax no |  | Address | Ministère Santé Publique BP 883, Bangui |
| Email | ouambita_mr@yahoo.fr |  |  |

# The Inter-Agency Coordinating Committee for Immunisation

Agencies and partners (including development partners and NGOs) supporting immunisation services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC, HSCC, or equivalent committee). The ICC, HSCC, or equivalent committee is responsible for coordinating and guiding the use of the GAVI NVS support. Please provide information about the ICC, HSCC, or equivalent committee in your country in the table below.

Profile of the ICC, HSCC, or equivalent committee

| Name of the committee | Inter-Agency Coordinating Committee (ICC) |
| --- | --- |
| Year of constitution of the current committee | 2002 |
| Organisational structure (e.g., sub-committee, stand-alone) | Committee for Technical Support to EPI (CTAPEV) |
| Frequency of meetings | 4 times/year |

Composition

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Function | Title / Organisation | Name |  |
| --- | --- | --- | --- |
| Chair | Minister of Health/Ministry of Public Health, Population and AIDS Control | Jean Michel MANDABA |  |
| Secretary | Director of EPI/Immunization Programme | Rosk OUAMBITA-MABO |  |
| Members | WHO Representative | Zakaria MAIGA | Action |
|  | UNICEF Representative | Tanya CHAPUISAT |  |
|  | President, Central African Red Cross | Antoine MBAO BOGO |  |
|  | National Director, SOS Children’s Village | Jeannette GBROUKA |  |
|  | Mission Chief, Ministry of Family, Social Affairs and National Solidarity | Emmanuel DJADA |  |
|  | Chief of Staff, Ministry of Communication, National Reconciliation and Peace Culture | Philémon DERANT LAKOUE |  |
|  | Director General of Public Health, Ministry of Public Health, Population and AIDS Control | Louis NAMBOUA |  |
|  | Director General of the Budget, Ministry of Finance and Budget | Germain WAMOUSTOYO |  |
|  | Department Head, Ministry of Economy, Planning and International Cooperation | Irène POUNEBINGUI |  |

Major functions and responsibilities of the committee

- Coordinate the activities of partners in the area of immunization - Help examine and approve the plans for routine EPI, National/Local Immunization Days and integrated epidemiological surveillance of diseases - Mobilize the internal and external resources needed to carry out immunization activities - Ensure transparent, accountable management of resources by working with EPI teams to regularly verify programme resources - Encourage and support information exchange at the operational, national and international levels - Ensure proper programme execution - Seek ways and means of resolving constraints that could hamper programme performance.

Three major strategies to enhance the committee's role and functions in the next 12 months

| 1. | Development of the partnership at the strategic level |
| --- | --- |
| 2. | Advocate with partners and donors on behalf of EPI |
| 3. | Programme monitoring and evaluation |

# National Immunization Technical Advisory Group for Immunisation

(If it has been established in the country)

We the members of the NITAG met on the 30 May 2011 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.

The endorsed minutes of this meeting are attached as DOCUMENT NUMBER: 4.

In case the GAVI Secretariat has queries on this submission, please contact

Enter the family name in capital letters.

| Name | Rock OUAMBITA-MABO | Title | Director of EPI |
| --- | --- | --- | --- |
| Tel no | (00236) 70407808 |  |  |
| Fax no |  | Address | Ministère de la Santé, BP 883, Bangui |
| Email | ouambita_mr@yahoo.fr |  |  |

# The NITAG Group for Immunisation

Profile of the NITAG

| Name of the NITAG | Committee for Technical Support to EPI (CTAPEV) |
| --- | --- |
| Year of constitution of the current NITAG | 2003 |
| Organisational structure (e.g., sub-committee, stand-alone) |  |
| Frequency of meetings | Once/month |

Composition

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

Enter the family name in capital letters.

| Function | Title / Organisation | Name |  |
| --- | --- | --- | --- |
| Chair | Director General of Public Health | Louis NAMBOUA |  |
| Secretary | Director of EPI | Rock OUAMBITA-MABO |  |
| Members |  |  | Action |

Major functions and responsibilities of the NITAG

- Examine and approve the operational action plans for EPI - Approve the budgets for implementation of these plans - Monitor the execution of the plan activities - Prepare the technical records for the audits - Produce periodic status reports on the programme implementation - Propose any measures likely to improve programme performance to the ICC.

Three major strategies to enhance the NITAG’s role and functions in the next 12 months

| 1. | Formulation and approval of programme guidelines, standards, plans and tools |
| --- | --- |
| 2. | Technical monitoring and evaluation of the programme |
| 3. | Development of the partnership |

# Immunisation Programme Data

Please complete the tables below, using data from available sources. Please identify the source of the data, and the date. Where possible use the most recent data and attach the source document.

- Please refer to the Comprehensive Multi-Year Plan for Immunisation (cMYP) (or equivalent plan) and attach a complete copy (with an Executive Summary) as DOCUMENT NUMBER 5

- Please refer to the two most recent annual WHO/UNICEF Joint Reporting Forms (JRF) on Vaccine Preventable Diseases.

- Please refer to Health Sector Strategy documents, budgetary documents, and other reports, surveys etc, as appropriate.

# Basic facts

For the year 2010 (most recent; specify dates of data provided)

|  | Figure |  | Year | Source |
| --- | --- | --- | --- | --- |
| Total population | 4,479,442 |  | 2010 | 2003 RGPH Projections |
| Infant mortality rate (per 1000) | 106 |  | 2006 | 2006 MICS |
| Surviving Infants[1] | 136,175 |  | 2010 | 2003 RGPH Projections |
| GNI per capita (US$) | 437 |  | 2010 | Ministry of Planning |
| Total Health Expenditure (THE) as a percentage of GDP | 1.90 | % | 2010 | Ministry of Planning |
| General government expenditure on health (GGHE) as % of General government expenditure | 8.98 | % | 2010 | Ministry of Planning |

[1] Surviving infants = Infants surviving the first 12 months of life

Please provide some additional information on the planning and budgeting context in your country; also indicate the name and date of the relevant planning document for health

Two documents serve as the basis for planning in CAR: - 2008–2010 Poverty Reduction Strategy Paper (PRSP); a second-generation PRSP is being developed. - National Health Development Plan (PNDSII) 2006–2015

Is the cMYP (or updated Multi-Year Plan) aligned with this document (timing, content, etc.)?

The 2011–2015 cMYP is aligned with the 2006–2015 PNDS

Please indicate the national planning budgeting cycle for health

The 2011–2015 cMYP is aligned with the 2006–2015 PNDS

Please indicate the national planning cycle for immunisation

The strategic planning cycle for EPI is five years, and the operational planning cycle is annual.

Please indicate if sex disaggregated data (SDD) is used in immunisation routine reporting systems

Immunization routine reporting data in CAR is not sex-disaggregated.

Please indicate if gender aspects relating to introduction of a new vaccine have been addressed in the introduction plan

Gender aspects are not taken into account in the plan for introduction of the rotavirus vaccine.

# Current vaccination schedule

Traditional, New Vaccines and Vitamin A supplement (refer to cMYP pages)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Vaccine (do not use trade name) | Ages of administration (by routine immunisation services) | Given in entire country | Comments | Action |
| --- | --- | --- | --- | --- |
| BCG | At birth | Yes |  |  |
| Polio | At birth, 6 weeks, 10 weeks and 14 weeks | Yes |  |  |
| Penta | 6 weeks, 10 weeks and 14 weeks | Yes |  |  |
| Measles | 9 months | Yes |  |  |
| Yellow fever | 9 months | Yes |  |  |
| TT+ | Pregnant women at 3 months, 6 months and next pregnancy | Yes |  |  |
| Other | 6 weeks, 10 weeks and 14 weeks |  | Pneumoccal vaccine (PCV13) to be introduced in July 2011 |  |
| Vitamin A | Starting at 6 months | Yes | Vitamin A is under-used in routine EPI but catch-ups in supplementary immunization activities |  |

# Trends of immunisation coverage and disease burden

(as per last two annual WHO/UNICEF Joint Reporting Form on Vaccine Preventable Diseases)

| Trends of immunisation coverage (percentage) |  |  |  |  |  | Vaccine preventable disease burden |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Vaccine |  | Reported |  | Survey |  | Disease | Number of reported cases |  |
|  |  | 2009 | 2010 | 2006 |  |  | 2009 | 2010 |
| BCG |  | 74 | 64 | 71 |  | Tuberculosis |  | 3,638 |
| DTP | DTP1 | 76 | 75 |  |  | Diphtheria | 0 | 0 |
|  | DTP3 | 49 | 57 | 34 |  | Pertussis | 63 | 1 |
| Polio 3 |  | 49 | 56 | 40 |  | Polio | 14 | 0 |
| Measles (first dose) |  | 60 | 63 | 50 |  | Measles | 11 | 2 |
| TT2+ (Pregnant women) |  | 86 | 50 |  |  | NN Tetanus | 15 | 20 |
| Hib3 |  | 49 | 57 |  |  | Hib[2] |  |  |
| Yellow Fever |  | 60 | 64 |  |  | Yellow fever | 29 | 6 |
| HepB3 |  | 49 | 57 |  |  | HepBsero-prevalence[1] |  |  |
| Vitamin A supplement Mothers (< 6 weeks post-delivery) |  |  |  |  |  |  |  |  |
| Vitamin A supplement Infants (>6 months) |  |  |  |  |  |  |  |  |

[1] If available

[2] Note: JRF asks for Hib meningitis

If survey data is included in the table above, please indicate the years the surveys were conducted, the full title and if available, the age groups the data refers to

Results of MICS survey conducted in 2006.

# Baseline and Annual Targets

(refer to cMYP pages)

Table 1: baseline figures

| Number | Base Year | Baseline and Targets |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2010 | 2013 | 2014 | 2015 |  |  |  |
| Total births | 156,780 | 166,546 | 169,922 | 173,356 |  |  |  |
| Total infants' deaths | 20,605 | 21,889 | 22,333 | 22,784 |  |  |  |
| Total surviving infants | 136,175 | 144,657 | 147,589 | 150,572 |  |  |  |
| Total pregnant women | 179,178 | 190,338 | 194,196 | 198,121 |  |  |  |
| Number of infants vaccinated (to be vaccinated) with BCG | 100,865 | 149,891 | 156,328 | 164,688 |  |  |  |
| BCG coverage (%)[1] | 64% | 90% | 92% | 95% |  |  |  |
| Number of infants vaccinated (to be vaccinated) with OPV3 | 76,679 | 115,726 | 125,451 | 135,715 |  |  |  |
| OPV3 coverage (%)[2] | 56% | 80% | 85% | 90% |  |  |  |
| Number of infants vaccinated (or to be vaccinated) with DTP1[3] | 102,408 | 144,657 | 147,589 | 150,572 |  |  |  |
| Number of infants vaccinated (to be vaccinated) with DTP3[3] | 77,817 | 115,726 | 125,451 | 135,715 |  |  |  |
| DTP3 coverage (%)[2] | 57% | 80% | 85% | 90% |  |  |  |
| Wastage[1] rate in base-year and planned thereafter for DTP (%) | 5% | 10% | 10% | 10% |  |  |  |
| Wastage[1] factor in base-year and planned thereafter for DTP | 1.05 | 1.11 | 1.11 | 1.11 |  |  |  |
| Target population vaccinated with 1st dose of Rotavirus |  | 144,657 | 147,589 | 150,572 |  |  |  |
| Target population vaccinated with last dose of Rotavirus |  | 86,794 | 95,933 | 105,400 |  |  |  |
| Rotavirus coverage (%)[2] | 0% | 60% | 65% | 70% |  |  |  |
| Infants vaccinated (to be vaccinated) with 1st dose of Measles | 85,726 | 115,726 | 125,451 | 135,715 |  |  |  |
| Measles coverage (%)[2] | 63% | 80% | 85% | 90% |  |  |  |
| Pregnant women vaccinated with TT+ | 89,589 | 133,237 | 145,647 | 158,497 |  |  |  |
| TT+ coverage (%)[4] | 50% | 70% | 75% | 80% |  |  |  |
| Vit A supplement to mothers within 6 weeks from delivery |  |  |  |  |  |  |  |
| Vit A supplement to infants after 6 months |  |  |  |  |  |  |  |
| Annual DTP Drop-out rate[ ( DTP1 - DTP3 ) / DTP1 ] x 100[5] | 24% | 20% | 15% | 10% |  |  |  |

[1] Number of infants vaccinated out of total births

[2] Number of infants vaccinated out of total surviving infants

[3] Indicate total number of children vaccinated with either DTP alone or combined

[4] Number of pregnant women vaccinated with TT+ out of total pregnant women

[5] The formula to calculate a vaccine wastage rate (in percentage):[ ( A – B ) / A ] x 100. Whereby: A = the number of doses distributed for use according to the supply records with correction for stock balance at the end of the supply period; B = the number of vaccinations with the same vaccine in the same period.

# Summary of current and future immunisation budget

(or refer to cMYP pages)

|  | Estimated costs per annum in US$ (in thousand US$) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cost category | Base Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |  |
|  | 2010 | 2013 | 2014 | 2015 |  |  |  |  |  |  |
| Routine Recurrent Cost |  |  |  |  |  |  |  |  |  |  |
| Vaccines (routine vaccines only) | 965,806 | 4,780,772 | 4,975,687 | 5,538,477 |  |  |  |  |  |  |
| Traditional vaccines | 134,479 | 188,375 | 209,963 | 231,931 |  |  |  |  |  |  |
| New and underused vaccines | 831,327 | 4,592,397 | 4,765,724 | 5,306,546 |  |  |  |  |  |  |
| Injection supplies | 38,588 | 142,410 | 134,354 | 167,173 |  |  |  |  |  |  |
| Personnel | 417,095 | 517,578 | 537,716 | 555,123 |  |  |  |  |  |  |
| Salaries of full-time NIP health workers (immunisation specific) | 182,001 | 207,466 | 211,616 | 215,848 |  |  |  |  |  |  |
| Per-diems for outreach vaccinators / mobile teams | 235,094 | 310,112 | 326,100 | 339,275 |  |  |  |  |  |  |
| Transportation | 89,922 | 150,604 | 161,160 | 173,642 |  |  |  |  |  |  |
| Maintenance and overheads | 1,687,983 | 2,620,769 | 3,538,512 | 4,927,586 |  |  |  |  |  |  |
| Training | 50,221 | 73,195 | 131,553 | 60,704 |  |  |  |  |  |  |
| Social mobilisation and IEC | 0 | 105,524 | 49,903 | 99,696 |  |  |  |  |  |  |
| Disease surveillance | 359,582 | 435,952 | 444,671 | 453,565 |  |  |  |  |  |  |
| Program management | 144,636 | 187,598 | 191,350 | 195,177 |  |  |  |  |  |  |
| Other | 12,240 | 70,028 | 54,904 | 57,602 |  |  |  |  |  |  |
| Subtotal Recurrent Costs | 3,766,073 | 9,084,430 | 10,219,810 | 12,228,745 |  |  |  |  |  |  |
| Routine Capital Costs |  |  |  |  |  |  |  |  |  |  |
| Vehicle | 46,605 | 73,334 | 97,415 | 48,794 |  |  |  |  |  |  |
| Cold chain equipment | 30,626 | 23,955 | 116,171 | 159,873 |  |  |  |  |  |  |
| Other capital equipment | 154,231 | 247,837 | 247,837 | 247,837 |  |  |  |  |  |  |
| Subtotal Capital Costs | 231,462 | 345,126 | 461,423 | 456,504 |  |  |  |  |  |  |
| Campaigns |  |  |  |  |  |  |  |  |  |  |
| Polio | 1,661,956 | 1,390,393 | 1,409,524 | 1,429,408 |  |  |  |  |  |  |
| Measles | 0 | 1,073,613 | 0 | 1,137,694 |  |  |  |  |  |  |
| Yellow Fever | 3,643,139 | 1,010,408 | 1,050,478 | 1,094,458 |  |  |  |  |  |  |
| MNT campaigns | 0 | 38,814 | 33,265 | 29,324 |  |  |  |  |  |  |
| Other campaigns |  |  |  |  |  |  |  |  |  |  |
| Subtotal Campaign Costs | 5,305,095 | 3,513,228 | 2,493,267 | 3,690,884 |  |  |  |  |  |  |
| GRAND TOTAL | 9,302,630 | 12,942,784 | 13,174,500 | 16,376,133 |  |  |  |  |  |  |

# Summary of current and future financing and sources of funds

Please list in the tables below the funding sources for each type of cost category (if known). Please try and indicate which immunisation program costs are covered from the Government budget, and which costs are covered by development partners (or the GAVI Alliance), and name the partners (or refer to cMYP).

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

|  |  | Estimated costs per annum in US$ (in thousand US$) |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cost category | Funding source | Base Year | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |  |
|  |  | 2010 | 2013 | 2014 | 2015 |  |  |  |  |  |  |
| Routine Recurrent Cost |  |  |  |  |  |  |  |  |  |  |  |
|  | Government | 701,524 | 2,378,038 | 3,215,813 | 3,956,865 |  |  |  |  |  |  |
|  | UNICEF | 1,758,177 | 1,572,021 | 1,692,659 | 2,417,461 |  |  |  |  |  |  |
|  | GAVI | 789,297 | 4,564,262 | 4,678,977 | 5,511,809 |  |  |  |  |  |  |
|  | WHO | 612,864 | 723,543 | 806,933 | 816,163 |  |  |  |  |  |  |
| Routine Capital Costs |  |  |  |  |  |  |  |  |  |  |  |
|  | Government | 154,231 | 247,837 | 354,423 | 352,160 |  |  |  |  |  |  |
|  | UNICEF | 77,231 | 60,617 | 107,000 | 104,344 |  |  |  |  |  |  |
|  | GAVI | 0 | 36,672 | 0 | 0 |  |  |  |  |  |  |
|  | WHO | 0 | 0 | 0 | 0 |  |  |  |  |  |  |
| Campaigns |  |  |  |  |  |  |  |  |  |  |  |
|  | Government | 0 | 503,879 | 117,111 | 3,105,916 |  |  |  |  |  |  |
|  | UNICEF | 477,716 | 992,391 | 710,013 | 4,314,398 |  |  |  |  |  |  |
|  | GAVI | 2,924,522 | 790,050 | 824,611 | 860,935 |  |  |  |  |  |  |
|  | WHO | 1,902,857 | 1,226,909 | 841,532 | 3,831,362 |  |  |  |  |  |  |
| GRAND TOTAL |  | 9,398,419 | 13,096,219 | 13,349,072 | 25,271,413 |  |  |  |  |  |  |

# New and Under-Used Vaccines (NVS)

Please summarise the cold chain capacity and readiness to accommodate new vaccines, stating how the cold chain expansion (if required) will be financed, and when it will be in place. Please indicate the additional cost, if capacity is not available and the source of funding to close the gap.

At the national level, the EPI has two positive cold rooms with a total gross capacity of 60 m3 and two negative cold rooms with a 40 m3 total gross capacity. All of these cold rooms meet WHO and UNICEF standards. The net positive storage capacity of the cold rooms at the national EPI storage facility is 15 m3 (15 000 litres). In 2013, the available net capacity will be sufficient for storing routine vaccines even after the rotavirus vaccine is introduced at a rate of two supply deliveries per year. Table 6.1 summarizes the cold chain storage capacities at the national storage facility. Nevertheless, given the fact that the current cold rooms are expected to be replaced in 2012 because of obsolescence, it is prudent to plan for procurement of three 15 000–liter cold rooms, one in 2012 and one in 2014, to allow for greater flexibility during mass immunization campaigns. The cost of these three cold rooms is estimated at US$ 324 375. At the regional level, all the districts are equipped with refrigerators and freezers for vaccine storage. The available capacity covers current needs, with a supply delivery every two months. When the rotavirus vaccine is introduced in 2013, the majority of districts (14/24) will require additional cold chain capacity. The total additional requirement for all district storage facilities is estimated at 35 refrigerators (Sibir V170KE-type) by 2015. This equipment will be procured prior to the introduction of the rotavirus vaccine in 2013. The total cost of procurement and installation of the new equipment is estimated at US$ 90 000.

Please give a summary of the cMYP sections that refer to the introduction of new and under-used vaccines. Outline the key points that informed the decision-making process (data considered etc)

- Rotavirus is the most common cause of severe diarrheal disease in infants and young children worldwide. According to 2004 WHO estimates, 527 000 (475 000–580 000) children under five years of age die each year from a vaccine-preventable rotavirus infection, primarily in low-income countries. - In sub-Saharan Africa there are 110–230 000 deaths related to rotavirus infections each year. Surveillance data show that rotavirus infections account for 40% of hospitalizations for diarrheal disease worldwide. - The preliminary findings of a study on rotavirus conducted in February–September 2008 by the Institut Pasteur de Bangui on 250 stool samples collected from children 0–5 years during visits for acute diarrhea at the pediatric ward of the Centre National Hospitalier et Universitaire de Bangui (CPB) showed that 100 samples (40%) tested positive for rotavirus using the VIKIA Rota-Adeno (BioMérieux) sensitive particle agglutination technique. - In order to increase the spectrum of protection for children in CAR against vaccine-preventable disease and thus play a more effective role in reducing child mortality and morbidity, the Ministry of Public Health, Population and AIDS Control, in accordance with the 2011–2015 cMYP, proposes to introduce the rotavirus vaccine into the routine immunization programme in 2003. - CAR is seizing the opportunity provided by GAVI to enable countries with vaccine coverage of at least 50% to apply for introduction of the rotavirus vaccine this year. - Given the availability on the international market of both types of vaccine, CAR opted for the single-dose liquid Rotarix as its first choice for the following reasons: 2-dose administration and cross-protection for several strains.

# Capacity and cost (for positive storage)

|  |  | Formula | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2013 | 2014 | 2015 |  |  |  |  |  |
| A | Annual positive volume requirement, including new vaccine (litres or m3) Litres | Sum-product of total vaccine doses multiplied by unit packed volume of the vaccine | 17,153 | 18,768 | 20,442 |  |  |  |  |  |
| B | Existing net positive cold chain capacity (litres or m3) Litres | # | 15,000 | 15,000 | 15,000 |  |  |  |  |  |
| C | Estimated minimum number of shipments per year required for the actual cold chain capacity | A / B | 2 | 2 | 2 |  |  |  |  |  |
| D | Number of consignments / shipments per year | Based on national vaccine shipment plan | 2 | 2 | 2 |  |  |  |  |  |
| E | Gap (if any) | ((A / D) - B) | -6,424 | -5,616 | -4,779 |  |  |  |  |  |
| F | Estimated additional cost of cold chain | US$ |  |  |  |  |  |  |  |  |

Please briefly describe how your country plans to move towards attaining financial sustainability for the new vaccines you intend to introduce, how the country will meet the co-financing payments, and any other issues regarding financial sustainability you have considered (refer to the cMYP)

1. The development of a financial sustainability mechanism for EPI on the part of the Government, including promotion of the Vaccine Independence Initiative, will be based on the following strategies: - Advocate with decision-makers: President of the Republic (Chairman of the Treasury Committee). National Mediator, National Assembly, Cabinet - Development of the collaboration with the planning and finance ministries for a streamlined credit allocation procedure (advance payment) - Updating of the financing plan and submission to the arbitration committee during preparation of the State budget 2. Preparation of the medium-term sector expenditure framework (MTEF) showing the role of immunization in health sector expenditures. 3. Expansion of the active partnership with local authorities, private enterprises, NGOs, etc.: - Involvement of the private health sector and NGOs in vaccine financing from planning to implementation of activities - Targeting advocacy to potential partners (diplomatic representations, international organizations, religious denominations) and renew those that have lapsed

# Assessment of burden of relevant diseases (if available)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Disease | Title of the assessment | Date | Results |  |
| --- | --- | --- | --- | --- |

If new or under-used vaccines have already been introduced in your country, please give details of the lessons learned from storage capacity, protection from accidental freezing, staff training, cold chain, logistics, drop-out rate, wastage rate etc., and suggest action points to address them

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Lessons Learned | Action Points |  |
| --- | --- | --- |
| - Opportunity to strengthen staff capabilities - The need for a detailed timetable of activities for introducing the new vaccine - Importance of outreach communication and social mobilization - Frequent cold chain failures (power outage in Bangui, lack of fuel) - Lack of written guidelines for waste disposal - Lack of procedures/guidelines for monitoring adverse effects following immunization (AEFI) - Surveillance of Hib bacterial meningitis has not yet begun | - Develop and implement a plan to strengthen health care staff capabilities in programme management - Organize supportive supervision visits of health clinics - Strengthen outreach communication and social mobilization - Integrate the new vaccines into the PIC and implement it effectively - Formulate clear guidelines for safe disposal of EPI immunization waste - Organize quarterly internal reviews at each prefecture for routine EPI - Implement surveillance of pediatric Hib bacterial meningitis and of AEFI monitoring |  |

Please list the vaccines to be introduced with support from the GAVI Alliance (and presentation)

Rotavirus vaccine (ROTARIX): Presentation: Single-dose liquid squeeze tube

# 6.3.1. Requested vaccine ( Rotavirus 2-dose schedule )

As reported in the cMYP, the country plans to introduce Rotavirus 2-dose schedule vaccine.

# 6.3.2. Co-financing information

If you would like to co-finance higher amount than minimum, please overwrite information in the “Your co-financing” row.

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

| Country group | Low |
| --- | --- |

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Minimum co-financing | 0.20 | 0.20 | 0.20 |  |  |  |  |  |
| Your co-financing (please change if higher) | 0.20 | 0.20 | 0.20 |  |  |  |  |  |

# 6.3.3. Wastage factor

Please indicate wastage rate:

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

Note: Selection of this field has direct impact on automatic calculations of support you are requesting and should not be left empty.

|  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Vaccine wastage rate in % | 5% | 5% | 5% |  |  |  |  |  |
| Equivalent wastage factor | 1.05 | 1.05 | 1.05 |  |  |  |  |  |

# 6.3.4. Specifications of vaccinations with new vaccine

|  | Data from |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 144,657 | 147,589 | 150,572 |  |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 86,794 | 95,933 | 105,400 |  |  |  |  |  |
| Immunisation coverage with the third dose | Table 1 | # | 60.00% | 65.00% | 70.00% |  |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[3] | # | 1.05 | 1.05 | 1.05 |  |  |  |  |  |
| Country co-financing per dose[2] | Table 6.(n).2[3] | $ | 0.20 | 0.20 | 0.20 |  |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Total price per-dose includes vaccine cost, plus freight, supplies, insurance, visa costs etc.

[3] Where (n) depends on the vaccine

# 6.3.5. Portion of supply to be procured by the country (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Number of vaccine doses | # | 14,500 | 14,900 | 16,800 |  |  |  |  |  |
| Number of AD syringes | # |  |  |  |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 175 | 175 | 200 |  |  |  |  |  |
| Total value to be co-financed by country | $ | 76,000 | 62,500 | 64,000 |  |  |  |  |  |

# 6.3.6. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$)

|  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | 2013 | 2014 | 2015 |  |  |  |  |  |
| Number of vaccine doses | # | 365,300 | 296,700 | 301,000 |  |  |  |  |  |
| Number of AD syringes | # |  |  |  |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 4,075 | 3,300 | 3,350 |  |  |  |  |  |
| Total value to be co-financed by GAVI | $ | 1,921,000 | 1,248,500 | 1,140,500 |  |  |  |  |  |

# 6.3.7. New and Under-Used Vaccine Introduction Grant

Please indicate in the tables below how the one-time Introduction Grant[1] will be used to support the costs of vaccine introduction and critical pre-introduction activities (refer to the cMYP).

Calculation of lump-sum for the Rotavirus 2-dose schedule

If the total is lower than US$100,000, it is automatically rounded up to US$100,000

| Year of New Vaccine Introduction | Births (from Table 1) | Share per Birth in US$ | Total in US$ |
| --- | --- | --- | --- |
| 2013 | 166,546 | 0.30 | 100,000 |

[1] The Grant will be based on a maximum award of $0.30 per infant in the birth cohort with a minimum starting grant award of $100,000

Cost (and finance) to introduce the Rotavirus 2-dose schedule (US$)

Note: To add new lines click on the New item icon in the Action column. Use the Delete item icon to delete a line.

| Cost Category | Full needs for new vaccine introduction in US$ | Funded with new vaccine introduction grant in US$ |  |
| --- | --- | --- | --- |
| Training | 45,700 | 45,700 |  |
| Social Mobilization, IEC and Advocacy | 39,000 | 39,000 |  |
| Cold Chain Equipment & Maintenance |  |  |  |
| Vehicles and Transportation |  |  |  |
| Programme Management | 12,500 | 12,500 |  |
| Surveillance and Monitoring | 39,000 |  |  |
| Human Resources |  |  |  |
| Waste Management |  |  |  |
| Technical assistance |  |  |  |
| Evaluation post-introduction | 17000 |  |  |
| Totals | 153,200 | 97,200 |  |

# Procurement and Management of New and Under-Used Vaccines

Note: The PCV vaccine must be procured through UNICEF

- Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that most countries will procure vaccine and injection supplies through UNICEF)

- The country fills out the vaccine order form and submits it to the UNICEF central purchasing office to obtain a supply of vaccine; - Payment of the applicable amount is made into UNICEF’s country office account, which transfers it to the central purchasing office to make up the vaccine doses.

- If an alternative mechanism for procurement and delivery of supply (financed by the country or the GAVI Alliance) is requested, please document

- Other vaccines or immunisation commodities procured by the country and descriptions of the mechanism used.

- The functions of the National Regulatory Authority (as evaluated by WHO) to show they comply with WHO requirements for procurement of vaccines and supply of assured quality.

- Please describe the introduction of the vaccines (refer to cMYP)

- Preparation of the operating plan for introduction of the new vaccine and the submission document for GAVI - Evaluation and preparation of cold chain capacity - Review and reproduction of the data management tools - Staff training - Ordering and procurement of vaccines - Supplying of districts with the new vaccine - Implementation of communication activities - Official launch of the introduction - Immunization of children in the EPI centres - Monitoring and evaluation of the new vaccine introduction

- Please indicate how funds should be transferred by the GAVI Alliance (if applicable)

Transfer against the bank account opened by the Ministry of Health

- Please indicate how the co-financing amounts will be paid (and who is responsible for this)

Bank transfer through the UNICEF account

- Please outline how coverage of the new vaccine will be monitored and reported (refer to cMYP)

- Monitoring of completion and timeliness of monthly immunization reports - Monthly immunization reports sent to partners at the national, inter-country and regional levels - Monthly monitoring meetings organized at the health prefecture level - Meeting to review and coordinate the data, held monthly at the national level - Supportive supervision of workers at EPI centres based on the DQS tool; - Joint report with Ministry of Health, WHO and UNICEF

# Vaccine Management (EVSM/EVM/VMA)

When was the last Effective Vaccine Store Management (EVSM) conducted? August  - 2007

When was the last Effective Vaccine Management (EVM) or Vaccine Management Assessment (VMA) conducted? November  - 2008

- If your country conducted either EVSM, EVM, or VMA in the past three years, please attach relevant reports. (Document N°)

- A VMA report must be attached from those countries which have introduced a New and Underused Vaccine with GAVI support before 2008.

- Please note that EVSM and VMA tools have been replaced by an integrated Effective Vaccine Management (EVM) tool. The information on EVM tool can be found at http://www.who.int/immunization_delivery/systems_policy/logistics/en/index6.html

- For countries which conducted EVSM, VMA or EVM in the past, please report on activities carried out as part of either action plan or improvement plan prepared after the EVSM/VMA/EVM.

Most of the recommendations from the 2007 EVSM have not been implemented: - Take steps to set up a national steering committee to manage biomedical waste and injection safety by the end of August 2007. - In the first two weeks of September 2007, organize the workshop to formulate the guidelines and national policy on biomedical waste management. - Train all storage facility managers in cold chain management principles and vaccine management, and institutionalize wastage monitoring. - Prepare the fact sheets on injection safety and biomedical waste management, and ensure broad distribution. - Strengthen freezer capacity in the districts by allocating 45 freezers already stored in the national storage facilities. - Reallocate supplies assigned during measles SIA. A partial evaluation of vaccine management conducted in November 2008 led to the development of an action plan for improvement that has not yet been approved or implemented. The evaluation will be completed in 2011 and the action plan for improving vaccine management will be implemented before the next evaluation set for October 2012. The country will also take the following actions: - Computerization of vaccine management at the national level (DVDMT) - Monthly monitoring of vaccine management and EPI input at the national and operational levels (health prefectures)

- When is the next Effective Vaccine Management (EVM) Assessment planned? October  - 2012

- Under new guidelines, it will be mandatory for the countries to conduct an EVM prior to an application for introduction of new vaccine.

# Additional Comments and Recommendations

Comments and Recommendations from the National Coordinating Body (ICC/HSCC)

1. The problem of low vaccine coverage should be taken into account for EPI strengthening; 2. We must increasingly think about innovations to improve immunization services in our country: Contracting with NGOs for routine EPI activities should be considered in order to expand EPI activities into hard-to-access emergency zones; 3. The restructuring of the National Health Information System currently underway should be put to good use in strengthening the collection and transmission of immunization data; 4. The department managers’ poor understanding of the contracting process is a handicap for monitoring budget allocations intended for health; 5. With regrd to the fuel assistance allocated by UNICEF, WHO and GAVI, it is more a matter of ensuring a regular supply of fuel for operating the EPI refrigerators; 6. The issue of taking into account GAVI financing in the Central African Republic’s budget law should be clarified; 7. The reallocation of a portion of the GAVI/HSS funds intended for procurement of fuel, refrigerators and cold chain supplies to strengthen immunization services was a positive experience; 8. The timetable for introducing the rotavirus vaccine beginning on 1 July 2011 should be widely distributed at all levels; 9. The matter of under-financing for EPI should be the subject of advocacy with the Government so that CAR will meet its obligations in connection with vaccine independence; 10. Since the country is still in the post-conflict stage (and therefore fragile), it is still experiencing difficulties with internal and external mobilization of financial resources.

# Annexes

# Annex 1

# Annex 1.1 – Rotavirus 2-dose schedule

Table 1.1 A - Rounded up portion of supply that is procured by the country and estimate of related cost in US$

| Required supply item |  | 2013 | 2014 | 2015 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # | 14,500 | 14,900 | 16,800 |  |  |  |  |  |
| Number of AD syringes | # |  |  |  |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 175 | 175 | 200 |  |  |  |  |  |
| Total value to be co-financed by the country | $ | 76,000 | 62,500 | 64,000 |  |  |  |  |  |

Table 1.1  B - Rounded up portion of supply that is procured by GAVI and estimate of related cost in US$.

| Required supply item |  | 2013 | 2014 | 2015 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of vaccine doses | # | 365,300 | 296,700 | 301,000 |  |  |  |  |  |
| Number of AD syringes | # |  |  |  |  |  |  |  |  |
| Number of re-constitution syringes | # |  |  |  |  |  |  |  |  |
| Number of safety boxes | # | 4,075 | 3,300 | 3,350 |  |  |  |  |  |
| Total value to be co-financed by the country | $ | 1,921,000 | 1,248,500 | 1,140,500 |  |  |  |  |  |

Table 1.1  C - Summary table for Rotavirus 2-dose schedule

|  | Data from |  | 2013 | 2014 | 2015 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Number of Surviving infants | Table 1 | # | 144,657 | 147,589 | 150,572 |  |  |  |  |  |
| Number of children to be vaccinated with the third dose[1] | Table 1 | # | 86,794 | 95,933 | 105,400 |  |  |  |  |  |
| Immunisation coverage with the last dose | Table 1 | # | 60.00% | 65.00% | 70.00% |  |  |  |  |  |
| Number of children to be vaccinated with the first dose | Table 1 | # | 144,657 | 147,589 | 150,572 |  |  |  |  |  |
| Number of doses per child |  | # | 2 | 2 | 2 |  |  |  |  |  |
| Estimated vaccine wastage factor | Table 6.(n).3[2] | # | 1.05 | 1.05 | 1.05 |  |  |  |  |  |
| Number of doses per vial |  | # | 1 | 1 | 1 |  |  |  |  |  |
| AD syringes required |  | # | No | No | No |  |  |  |  |  |
| Reconstitution syringes required |  | # | No | No | No |  |  |  |  |  |
| Safety boxes required |  | # | Yes | Yes | Yes |  |  |  |  |  |
| Vaccine price per dose |  | $ | 5.000 | 4.000 | 3.600 |  |  |  |  |  |
| Country co-financing per dose | Table 6.(n).2[2] | $ | 0.20 | 0.20 | 0.20 |  |  |  |  |  |
| AD syringe price per unit |  | $ | 0.053 | 0.053 | 0.053 |  |  |  |  |  |
| Reconstitution syringe price per unit |  | $ |  |  |  |  |  |  |  |  |
| Safety box price per unit |  | $ | 0.640 | 0.640 | 0.640 |  |  |  |  |  |
| Freight cost as % of vaccines value |  | % | 5.00 | 5.00 | 5.00 |  |  |  |  |  |
| Freight cost as % of devices value |  | % | 10.00 | 10.00 | 10.00 |  |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.1 D - Estimated number of doses for Rotavirus 2-dose schedule associated injection safety material and related co-financing budget (page 1)

|  |  | Formula | 2013 |  |  | 2014 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 3.80% |  |  | 4.75% |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 144,657 | 5,503 | 139,154 | 147,589 | 7,016 | 140,573 |
| C | Number of doses per child | Vaccine parameter | 2 | 2 | 2 | 2 | 2 | 2 |
| D | Number of doses needed | B * C | 289,314 | 11,006 | 278,308 | 295,178 | 14,031 | 281,147 |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 | 1.05 |
| F | Number of doses needed including wastage | D * E | 303,780 | 11,556 | 292,224 | 309,937 | 14,732 | 295,205 |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 75,945 | 2,889 | 73,056 | 1,540 | 74 | 1,466 |
| I | Total vaccine doses needed | F + G | 379,725 | 14,445 | 365,280 | 311,477 | 14,805 | 296,672 |
| J | Number of doses per vial | Vaccine parameter | 1 | 1 | 1 | 1 | 1 | 1 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 |  |  |  |  |  |  |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | I / 100 x 1.11 | 4,215 | 161 | 4,054 | 3,458 | 165 | 3,293 |
| N | Cost of vaccines needed | I * vaccine price per dose | 1,898,625 | 72,222 | 1,826,403 | 1,245,908 | 59,220 | 1,186,688 |
| O | Cost of AD syringes needed | K * AD syringe price per unit |  |  |  |  |  |  |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 2,698 | 103 | 2,595 | 2,214 | 106 | 2,108 |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 94,932 | 3,612 | 91,320 | 62,296 | 2,961 | 59,335 |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 270 | 11 | 259 | 222 | 11 | 211 |
| T | Total fund needed | (N + O + P + Q + R + S) | 1,996,525 | 75,945 | 1,920,580 | 1,310,640 | 62,296 | 1,248,344 |
| U | Total country co-financing | I * country co-financing per dose | 75,945 |  |  | 62,296 |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 3.80% |  |  | 4.75% |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Table 1.1 D - Estimated number of doses for Rotavirus 2-dose schedule associated injection safety material and related co-financing budget (page 2)

|  |  | Formula | 2015 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Total | Government | GAVI | Total | Government | GAVI |
| A | Country Co-finance |  | 5.28% |  |  |  |  |  |
| B | Number of children to be vaccinated with the first dose[1] | Table 1 (baseline & annual targets) | 150,572 | 7,951 | 142,621 |  |  |  |
| C | Number of doses per child | Vaccine parameter (schedule) | 2 | 2 | 2 | 2 | 2 | 2 |
| D | Number of doses needed | B * C | 301,144 | 15,901 | 285,243 |  |  |  |
| E | Estimated vaccine wastage factor | Table 6.(n).3. in NVS section[2] | 1.05 | 1.05 | 1.05 |  |  |  |
| F | Number of doses needed including wastage | D * E | 316,202 | 16,696 | 299,506 |  |  |  |
| G | Vaccines buffer stock | (F - F of previous year) * 0.25 | 1,567 | 83 | 1,484 |  |  |  |
| I | Total vaccine doses needed | F + G | 317,769 | 16,779 | 300,990 |  |  |  |
| J | Number of doses per vial | Vaccine parameter | 1 | 1 | 1 | 1 | 1 | 1 |
| K | Number of AD syringes (+ 10% wastage) needed | (D + G) * 1.11 |  |  |  |  |  |  |
| L | Reconstitution syringes (+ 10% wastage) needed | I / J * 1.11 |  |  |  |  |  |  |
| M | Total of safety boxes (+ 10% of extra need) needed | I / 100 x 1.11 | 3,528 | 187 | 3,341 |  |  |  |
| N | Cost of vaccines needed | I * vaccine price per dose | 1,143,969 | 60,403 | 1,083,566 |  |  |  |
| O | Cost of AD syringes needed | K * AD syringe price per unit |  |  |  |  |  |  |
| P | Cost of reconstitution syringes needed | L * reconstitution price per unit |  |  |  |  |  |  |
| Q | Cost of safety boxes needed | M * safety box price per unit | 2,258 | 120 | 2,138 |  |  |  |
| R | Freight cost for vaccines needed | N * freight cost as % of vaccines value | 57,199 | 3,021 | 54,178 |  |  |  |
| S | Freight cost for devices needed | (O + P + Q) * freight cost as % of devices value | 226 | 12 | 214 |  |  |  |
| T | Total fund needed | (N + O + P + Q + R + S) | 1,203,652 | 63,554 | 1,140,098 |  |  |  |
| U | Total country co-financing | I * country co-financing per dose | 63,554 |  |  |  |  |  |
| V | Country co-financing % of GAVI supported proportion | U / T | 5.28% |  |  |  |  |  |

[1] 2nd dose if Measles vaccine or Rotavirus 2-dose schedule

[2] Where (n) depends on the vaccine

# Annex 2

Estimated prices of supply and related freight cost: 2011 from UNICEF Supply Division; 2012 onwards: GAVI Secretariat

Table A - Commodities Cost

| Vaccine | Presentation | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AD syringe | 0 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 | 0.053 |
| DTP-HepB | 2 | 1.600 |  |  |  |  |  |  |
| DTP-HepB | 10 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 | 0.620 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-HepB-Hib | WAP | 2.580 | 2.470 | 2.320 | 2.030 | 1.850 | 1.850 | 1.850 |
| DTP-Hib | 10 | 3.400 | 3.400 | 3.400 | 3.400 | 3.400 | 3.200 | 3.200 |
| HepB monoval | 1 |  |  |  |  |  |  |  |
| HepB monoval | 2 |  |  |  |  |  |  |  |
| Hib monoval | 1 | 3.400 |  |  |  |  |  |  |
| Measles | 10 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 | 0.240 |
| Pneumococcal(PCV10) | 2 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 |
| Pneumococcal(PCV13) | 1 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 | 3.500 |
| Reconstit syringe for Pentaval (2ml) | 0 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 | 0.032 |
| Reconstit syringe for YF | 0 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 | 0.038 |
| Rotavirus 2-dose schedule | 1 | 7.500 | 6.000 | 5.000 | 4.000 | 3.600 | 3.600 | 3.600 |
| Rotavirus 3-dose schedule | 1 | 5.500 | 4.000 | 3.333 | 2.667 | 2.400 | 2.400 | 2.400 |
| Safety box | 0 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 | 0.640 |
| Yellow Fever | WAP | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 |
| Yellow Fever | WAP | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 | 0.856 |

Note: WAP - weighted average price (to be used for any presentation: For DTP-HepB-Hib, it applies to 1 dose liquid, 2 dose lyophilised and 10 dose liquid. For Yellow Fever, it applies to 5 dose lyophilised and 10 dose lyophilised)

Table B - Commodities Freight Cost

| Vaccines | Group | No Threshold | 200’000 $ |  | 250’000 $ |  | 2’000’000 $ |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | <= | > | <= | > | <= | > |
| Yellow Fever | Yellow Fever |  | 20% |  |  |  | 10% | 5% |
| DTP+HepB | HepB and or Hib | 2% |  |  |  |  |  |  |
| DTP-HepB-Hib | HepB and or Hib |  |  |  | 15% | 3,50% |  |  |
| Pneumococcal vaccine (PCV10) | Pneumococcal | 5% |  |  |  |  |  |  |
| Pneumococcal vaccine (PCV13) | Pneumococcal | 5% |  |  |  |  |  |  |
| Rotavirus | Rotavirus | 5% |  |  |  |  |  |  |
| Measles | Measles | 10% |  |  |  |  |  |  |

Table C - Low - Minimum country's co-payment per dose of co-financed vaccine.

| vaccine | 2013 | 2014 | 2015 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Rotavirus 2-dose schedule | 0.20 | 0.20 | 0.20 |  |  |  |  |

Table D - Wastage rates and factors

Countries are expected to plan for a maximal wastage rate of:

- 50% - for a lyophilised vaccine in 10 or 20-dose vial,

- 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,

- 10% - for a lyophilised/liquid vaccine in 2-dose vial, and

- 5% - for a liquid vaccine in 1-dose vial

| Vaccine wastage rate | 5% | 10% | 15% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Equivalent wastage factor | 1.05 | 1.11 | 1.18 | 1.25 | 1.33 | 1.43 | 1.54 | 1.67 | 1.82 | 2 | 2.22 | 2.5 |

WHO International shipping guidelines: maximum packed volumes of vaccines

Table E - Vaccine maximum packed volumes

| Vaccine product | Designation | Vaccine formulation | Admin route | No. Of doses in the schedule | Presentation (doses/vial, prefilled) | Packed volume vaccine (cm3/dose) | Packed volume diluents (cm3/dose) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| BCG | BCG | lyophilized | ID | 1 | 20 | 1.2 | 0.7 |
| Diphtheria-Tetanus-Pertussis | DTP | liquid | IM | 3 | 20 | 2.5 |  |
| Diphtheria-Tetanus-Pertussis | DTP | liquid | IM | 3 | 10 | 3.0 |  |
| Diphtheria-Tetanus | DT | liquid | IM | 3 | 10 | 3.0 |  |
| Tetanus-Diphtheria | Td | liquid | IM | 2 | 10 | 3.0 |  |
| Tetanus Toxoid | TT | liquid | IM | 2 | 10 | 3.0 |  |
| Tetanus Toxoid | TT | liquid | IM | 2 | 20 | 2.5 |  |
| Tetanus Toxoid UniJect | TT | liquid | IM | 2 | Uniject | 12.0 |  |
| Measles | Measles | lyophilized | SC | 1 | 1 | 26.1 | 20.0 |
| Measles | Measles | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles | Measles | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles | Measles | lyophilized | SC | 1 | 10 | 3.5 | 4.0 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 1 | 26.1 | 26.1 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles-Rubella freeze dried | MR | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 1 | 26.1 | 26.1 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 2 | 13.1 | 13.1 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 5 | 5.2 | 7.0 |
| Measles-Mumps-Rubella freeze dried | MMR | lyophilized | SC | 1 | 10 | 3.0 | 4.0 |
| Polio | OPV | liquid | Oral | 4 | 10 | 2.0 |  |
| Polio | OPV | liquid | Oral | 4 | 20 | 1.0 |  |
| Yellow fever | YF | lyophilized | SC | 1 | 5 | 6.5 | 7.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 10 | 2.5 | 3.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 20 | 1.5 | 2.0 |
| Yellow fever | YF | lyophilized | SC | 1 | 50 | 0.7 | 1.0 |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 1 | 9.7 |  |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 2 | 6.0 |  |
| DTP-HepB combined | DTP-HepB | liquid | IM | 3 | 10 | 3.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 1 | 18.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 2 | 13.0 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 6 | 4.5 |  |
| Hepatitis B | HepB | liquid | IM | 3 | 10 | 4.0 |  |
| Hepatitis B UniJect | HepB | liquid | IM | 3 | Uniject | 12.0 |  |
| Hib liquid | Hib_liq | liquid | IM | 3 | 1 | 15.0 |  |
| Hib liquid | Hib_liq | liquid | IM | 3 | 10 | 2.5 |  |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 1 | 13.0 | 35.0 |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 2 | 6.0 |  |
| Hib freeze-dried | Hib_lyo | lyophilized | IM | 3 | 10 | 2.5 | 3.0 |
| DTP liquid + Hib freeze-dried | DTP+Hib | liquid+lyop. | IM | 3 | 1 | 45.0 |  |
| DTP-Hib combined liquid | DTP+Hib | liquid+lyop. | IM | 3 | 10 | 12.0 |  |
| DTP-Hib combined liquid | DTP-Hib | liquid | IM | 3 | 1 | 32.3 |  |
| DTP-HepB liquid + Hib freeze-dried | DTP-Hib | liquid | IM | 3 | 10 | 2.5 |  |
| DTP-HepB liquid + Hib freeze-dried | DTP-HepB+Hib | liquid+lyop. | IM | 3 | 1 | 22.0 |  |
| DTP-HepB-Hib liquid | DTP-HepB+Hib | liquid+lyop. | IM | 3 | 2 | 11.0 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 10 | 4.4 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 2 | 13.1 |  |
| DTP-HepB-Hib liquid | DTP-HepB-Hib | liquid | IM | 3 | 1 | 19.2 |  |
| Meningitis A/C | MV_A/C | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis A/C | MV_A/C | lyophilized | SC | 1 | 50 | 1.5 | 3.0 |
| Meningococcal A/C/W/ | MV_A/C/W | lyophilized | SC | 1 | 50 | 1.5 | 3.0 |
| Meningococcal A/C/W/Y | MV_A/C/W/Y | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis W135 | MV_W135 | lyophilized | SC | 1 | 10 | 2.5 | 4.0 |
| Meningitis A conjugate | Men_A | lyophilized | SC | 2 | 10 | 2.6 | 4.0 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 10 | 15.0 |  |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 10 | 8.1 | 8.1 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 5 | 2.5 | 2.9 |
| Japanese Encephalitis | JE_lyo | lyophilized | SC | 3 | 1 | 12.6 | 11.5 |
| Japanese Encephalitis | JE_liq | liquid | SC | 3 | 10 | 3.4 |  |
| Rota vaccine | Rota_lyo | lyophilized | Oral | 2 | 1 | 156.0 |  |
| Rota vaccine | Rota_liq | liquid | Oral | 2 | 1 | 17.1 |  |
| Rota vaccine | Rota_liq | liquid | Oral | 3 | 1 | 45.9 |  |
| Pneumo. conjugate vaccine 7-valent | PCV-7 | liquid | IM | 3 | PFS | 55.9 |  |
| Pneumo. conjugate vaccine 7-valent | PCV-7 | liquid | IM | 3 | 1 | 21.0 |  |
| Pneumo. conjugate vaccine 10-valent | PCV-10 | liquid | IM | 3 | 1 | 11.5 |  |
| Pneumo. conjugate vaccine 10-valent | PCV-10 | liquid | IM | 3 | 2 | 4.8 |  |
| Pneumo. conjugate vaccine 13-valent | PCV-13 | liquid | IM | 3 | 1 | 12.0 |  |
| Polio inactivated | IPV | liquid | IM | 3 | PFS | 107.4 |  |
| Polio inactivated | IPV | liquid | IM | 3 | 10 | 2.5 |  |
| Polio inactivated | IPV | liquid | IM | 3 | 1 | 15.7 |  |
| Human Papilomavirus vaccine | HPV | liquid | IM | 3 | 1 | 15.0 |  |
| Human Papilomavirus vaccine | HPV | liquid | IM | 3 | 2 | 5.7 |  |
| Monovalent OPV-1 | mOPV1 | liquid | Oral |  | 20 | 1.5 |  |
| Monovalent OPV-3 | mOPV3 | liquid | Oral |  | 20 | 1.5 |  |

# Attachments

# List of Supporting Documents Attached to this Proposal

| Document | Section | Document Number | Mandatory[1] |
| --- | --- | --- | --- |
| MoH Signature (or delegated authority) of Proposal |  | 1 | Yes |
| MoF Signature (or delegated authority) of Proposal |  | 2 | Yes |
| Signatures of ICC or HSCC or equivalent in Proposal |  | 3 | Yes |
| Minutes of ICC/HSCC meeting endorsing Proposal |  | 4 | Yes |
| comprehensive Multi Year Plan - cMYP |  | 5 | Yes |
| cMYP Costing tool for financial analysis |  | 6 | Yes |
| Minutes of last three ICC/HSCC meetings |  | 11, 12, 13 | Yes |
| Improvement plan based on EVM |  | 7 | Yes |
| WHO/UNICEF Joint Reporting Form (JRF) |  | 9 |  |
| ICC/HSCC workplan for forthcoming 12 months |  |  |  |
| National policy on injection safety |  | 10 |  |
| Action plans for improving injection safety |  |  |  |
| Plan for NVS introduction (if not part of cMYP) |  | 8 |  |
| Banking details |  |  |  |

[1] Please indicate the duration of the plan / assessment / document where appropriate

# Attachments

List of all the mandatory and optional documents attached to this form

Note: Use the Upload file arrow icon to upload the document. Use the Delete item icon to delete a line. To add new lines click on the New item icon in the Action column.

| ID | File type | File name |  | New file | Actions |
| --- | --- | --- | --- | --- | --- |
|  | Description | Date and Time | Size |  |  |
| 1 | File Type: MoH Signature (or delegated authority) of Proposal * File Desc: | File name: C:\Documents and Settings\Dr CASIMIR\Mes documents\Mission Douala_Avril 2011\Documents propres\Dossier BON 23.05.11\Annexes\Siganture Ministre de la Santé et des Finances_Proposal.doc Date/Time: 31.05.2011 12:36:43 Size: 473 KB |  |  |  |
| 2 | File Type: MoF Signature (or delegated authority) of Proposal * File Desc: | File name: C:\Documents and Settings\Dr CASIMIR\Mes documents\Mission Douala_Avril 2011\Documents propres\Dossier BON 23.05.11\Annexes\Siganture Ministre de la Santé et des Finances_Proposal.doc Date/Time: 31.05.2011 12:38:45 Size: 473 KB |  |  |  |
| 3 | File Type: Signatures of ICC or HSCC or equivalent in Proposal * File Desc: | File name: C:\Documents and Settings\Dr CASIMIR\Mes documents\Mission Douala_Avril 2011\Documents propres\Dossier BON 23.05.11\Annexes\Signature des membres du CCIA_Proposal.doc Date/Time: 31.05.2011 12:42:32 Size: 501 KB |  |  |  |
| 4 | File Type: Minutes of ICC/HSCC meeting endorsing Proposal * File Desc: | File name \Rapport Réunion CCIA_30-05-2011.pdf Date/Time: 31.05.2011 12:48:28 Size: 1 MB |  |  |  |
| 5 | File Type: comprehensive Multi Year Plan - cMYP * File Desc: | File name: PPAC RCA_ 2011-2015 23 05 11_DEF.pdf Date/Time: 31.05.2011 12:55:30 Size: 1 MB |  |  |  |
| 6 | File Type: cMYP Costing tool for financial analysis * File Desc: | File name: cMYP_Costing_Tool_Vs 2.5_Fr_23.05.11_ RCA revisé_Bgui.zip Date/Time: 01.06.2011 09:01:36 Size: 851 KB |  |  |  |
| 7 | File Type: Improvement plan based on EVM * File Desc: | File name: PLAN REDUCTION PERTE_VACCINS_RCA.zip Date/Time: 01.06.2011 09:02:41 Size: 1 MB |  |  |  |
| 8 | File Type: Plan for NVS introduction (if not part of cMYP) File Desc: | File name: Plan d'introduction Vaccin antirotavirus_RCA_FINAL.zip Date/Time: 01.06.2011 09:05:07 Size: 549 KB |  |  |  |
| 9 | File Type: WHO/UNICEF Joint Reporting Form (JRF) File Desc: | File name: JRF_2010_RCA_FINAL_02 04 2011.xls Date/Time: 31.05.2011 13:11:32 Size: 472 KB |  |  |  |
| 10 | File Type: National policy on injection safety File Desc: | File name: Politique Nationale securite des injections RCA.zip Date/Time: 31.05.2011 13:14:35 Size: 388 KB |  |  |  |
| 11 | File Type: Minutes of last three ICC/HSCC meetings * File Desc: | File name: Rapport CCSS 04 février 2010.pdf Date/Time: 31.05.2011 13:27:16 Size: 2 MB |  |  |  |
| 12 | File Type: Minutes of last three ICC/HSCC meetings * File Desc: | File name: Rapport CCSS 11_12 mai 2010.pdf Date/Time: 31.05.2011 13:31:31 Size: 302 KB |  |  |  |
| 13 | File Type: Minutes of last three ICC/HSCC meetings * File Desc: | File name: Rapport CCSS 1er juin 2010.pdf Date/Time: 31.05.2011 13:36:16 Size: 795 KB |  |  |  |
| 14 | File Type: other File Desc: EVSM/EVM/VMA Report | File name: \Evaluation de la CDF_Lukadi Camille_RCA_08_07.pdf Date/Time: 31.05.2011 14:00:32 Size: 1 MB |  |  |  |
| 15 | File Type: other File Desc: EVSM/EVM/VMA Report | File name: Rapport de Mission Logistique_EGV 2008.pdf Date/Time: 31.05.2011 14:02:25 Size: 202 KB |  |  |  |

GAVI Alliance

Application Form for Country Proposals

Response to conditions

For Support to New and Under-Used Vaccines (NVS)

Submitted by

The Government of

[The Central African Republic]

Deadline for submission: 15 November 2011

Select Start and End Year of your Comprehensive Multi-Year Plan (cMYP)

| Start Year | 2011 | End Year | 2015 |
| --- | --- | --- | --- |

Revised in January 2011

(To be used with Guidelines of December 2010)

Please submit the Proposal using the online platform https://AppsPortal.gavialliance.org/PDExtranet.

Enquiries to: proposals@gavialliance.org or representatives of a GAVI partner agency. The documents can be shared with GAVI partners, collaborators and general public. The Proposal and attachments must be submitted in English, French, Spanish, or Russian.

Note: Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline.

The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents will be shared with the GAVI Alliance partners and the general public.

# Response to conditions

Vaccine: 2-dose Rotavirus

Condition 1:

The CAR must provide proof of implementation of its plan to improve its cold chain capacities in accordance with the schedule, particularly at the regional and outreach levels of its healthcare system. The CAR must provide items that can be used to judge whether or not the financial commitments have been met.

Condition 1a: Proof of implementation of its plan to improve its cold chain capacities in accordance with the schedule, particularly at the regional and outreach levels of its healthcare system.

The assessment of vaccine storage volume (positive part) made in late 2010 showed a gap of 1216 litres, which was filled by acquiring 66 new refrigerators purchased from GAVI/HSS and UNICEF funds in 2011 (cf appendix: bills of lading).

Improving the cold chain capacity with the acquisition of these new refrigerators made it possible to fill the gap of 26 refrigerators in the prefectures of Lobaye, Ombella Mpoko, Mambéré Kadéi, Nana Mambéré, Ouham, Ouham Pendé, Ouaka, Basse Kotto, 2nd, 3rd,4th, 5th, 6th and 8th districts, as shown in the charts below.

Fig 9 : Evaluation des besoins en chaîne de froid (partie positive) (après renforcement chaîne de froid)

Fig 8 : Evaluation des besoins en chaîne de froid (partie positive) (avant renforcement chaîne de froid)

Condition 1b

The country has agreed to pay the equivalent of the purchase price of the vaccines and injection supplies (co-financing).  To date the Central African Republic has paid FCFA 119,850,000 (USD 249,688) out of the FCFA 192,150,000 (USD 400,313) expected. A letter of agreement to settle any amounts in arrears for the funding of the new vaccines, co-signed by the Ministry of Health and the Ministry of Finance and Budget will be sent to. (See table below)

The country plans to set up a permanent mechanism for the EPI with the Government, including promoting the initiative for vaccine independence.

To honour its medium-term financial commitments, the following strategies will be implemented to raise the funds from the Government and partners:

1. Raising funds from the Government:

-Continued advocacy at the highest level with the support of the partners (WHO, UNICEF, GAVI, World Bank, Sabin Institute, etc.) to appropriate the budget for financing the EPI as well as annual growth of 10% in the EPI budget;

-Regular monitoring of the disbursement of the funds listed on the budget line item of the Expanded Program of Immunisation by the Ministry of Finance and Budget,

-Recognition by the Resource Manager of the MSPPLS for submission to the arbitration committee;

-Payments of the government’s portion will be made when due.

2. Design of the medium term sector expenses framework (MTEF) showing the amount of the healthcare sector budget accounted for by immunisation.

3. Expanding the active partnership with local authorities, private companies, NGOs, etc.:

- Involving the private healthcare sector NGO sector in financing immunisations from planning to implementation of the activities:

- Targeted advocacy with potential partners (diplomatic representatives, international organisations, religious organisations) and 2. Design the medium term sector expense framework (MTEF) showing the amount of healthcare sector expenses accounted for by immunisation.

| YEARS | Type of Vaccine | Contribution by GAVI |  | Contribution by the Government |  | Amount already paid by the Government |  | Remainder to be paid |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | CFA | USD | CFA | USD | CFA | USD | CFA | USD |
| 2008 | VAA + Pentavalent | 53,475,000 | 111,406 | 27,000,000 | 56,250 | 27,000,000 | 56,250 | - | - |
| 2009 | VAA + Pentavalent | 917,250,000 | 1,910,938 | 44,000,000 | 91,667 | 44,000,000 | 91,667 | - | - |
| 2010 | VAA + Pentavalent | 649,440,000 | 1,353,000 | 37,440,000 | 78,000 | 37,850,000 | 78,854 | - | - |
| 2011 | VAA + Pentavalent + PCV13 | 1,422,780,000 | 2,964,125 | 83,710,000 | 174,396 | 11,000,000 | 22,917 | 72,710 ,000 | 51,479 |

Condition 2:

The CAR must provide a progress report on implementation of the recommendations by its vaccine management strengthening programme based on EVM:

Two vaccine management/vaccine warehouse management (VMA/VWA) assessments were made in August 2007 and September 2011 with the technical support of the WHO and UNICEF. Some recommendations were made after those evaluations, including the implementation of one part that is summarised in Table 14 below.

| VMA/VWA assessments recommended 11 to 26 August, 2007 | VMA recommendations 22 August to 18 September 2011 | Level of completion | Comments |
| --- | --- | --- | --- |
| 1- Set up a national steering committee to manage biomedical waste and injection safety by the end of August 2007. |  | In progress | The working group was established in 2008 but was not created by an official law. Nonetheless, the group designed a national biomedical waste plan and guidelines that were validated nationally in 2010. |
| 2- In the first half of September 2007 hold the workshop to design national and political standards on the management of biomedical waste. |  | Totally completed | Recommendation followed : a workshop to design national standards, a policy and a plan for managing biomedical waste was held in Boali from 21-24 November 2007. Look for the report (the report alone is not enough 4 years later). |
| 3- Train all warehouse managers on the principles of cold chain management and vaccine management and institutionalise the monitoring of losses. | Training of all EPI staff at all levels, covering the 9 EVM criteria plus daily equipment maintenance. | Partially completed | Training was held partly at the national level. and locally at Health Region No. 7 and at the Ombella Mpoko Health Prefecture from 21 to 23 December 2008, and the training report is available. Under the 2011 and 2012 action plan, there are plans to continue this training. |
|  | Extensive training of personnel in data gathering and analysis procedures and sufficient computer skills to produce complete reports in a timely manner. |  |  |
|  | Training of trainers at the Prefecture level to train the personnel of the training program and the cold chain logistics workers, MLM modules at the national and Prefecture levels on procedures for gathering, inputting and communicating EPI data. |  |  |
| 4- Prepare and distribute widely technical sheets on injection safety and biomedical waste management. |  | Totally completed | The technical sheets on injection safety and biomedical waste management are contained in the training modules of the EPI workers and distributed to all the EPI centres. |
| 5- Strengthen freezer capacity in the districts by allocating 45 freezers still stored in the central warehouses. |  | Totally completed | 2008: Every Health Prefecture warehouse was equipped with 1 to 2 freezers to improve the freezer capacity. 2011: Freezer capacity improved with 66 Sibir V KE refrigerators in the 24 health prefectures. |
| 6- Reallocate the supplies assigned during the measles SIA. |  | Totally completed | The coolers and especially the “Geostyle” vaccine carriers remaining in storage after the measles SIA were gradually and regularly reassigned. (324 vaccine carriers) |

Out of sixteen recommendations made in the latest 2011 assessment, three are being implemented (3, 10 and 16). We were unable to implement the other recommendations for reasons related to insufficient local technical capacities, and insufficient financial and logistical resources, i.e.:

Table 15: Timeline for implementing the recommendations by the EVM assessment.

| RECOMMENDATIONS | TARGET DATES |
| --- | --- |
| - Subcontract the transportation and maintenance system to organizations with experience in those areas... | Starting in 2012 |
| - Acquire two 4x4 unrefrigerated small vans with a net capacity of 15 - 20m3 to supply the healthcare prefectures with vaccines every month. | 2nd half 2012 |
| - Emergency repair of positive cold chamber at the national warehouse (two cooling units). | 4th quarter 2011 – 1st quarter 2012 |
| - Establish a maintenance contract for the national warehouse between the Ministry of Health (EPI) and a competent certified local contractor. | 1st quarter 2012 |
| - Acquire and install a new 30m3 positive cold chamber in 2012 before introducing Rota. | 2nd half 2012 |
| - Equip each cold chamber with a continuous temperature reading system with GSM alarm. (The “Multilog” product with “Autodialer” is recommended). | 1st half 2012 |
| - Install solar panels and inverters in the right size to operate an IT system at each prefecture to transmit data. | 1st half 2012 |
| - Acquire “Fridge Tags” in all the refrigerators used to store vaccines, and “Freeze Tags” in each batch of TT, Penta or PCV13 vaccines transported in coolers or vaccine carriers. | 1st half 2012 |
| - Conduct a temperature study in the CAR as soon as possible by applying the WHO Protocol. Following that study, a decision must be made on using the batteries. | 1st half 2013 |
| - Deploy in the Prefecture bases the 33 Sibir refrigerators stored in reserve in the UNICEF warehouse to meet the immediate storage need with a monthly distribution system. | 4th quarter 2011 – 1st quarter 2012 |
| - Transmit within the deadline required (72 hours after receipt of the vaccines) the vaccine receipt reports (VRR) to UNICEF to ensure the validity of the guarantees. | In progress |
| - Plan study tours to other countries by the Ministry of Health official responsible for the EPI so he or she can learn from their experience in terms of transportation and maintenance, including the financial implications. | 2nd half 2012 |
| - Strengthen the capacity of EPI personnel at all levels in the 9 EVM criteria, daily equipment maintenance, data-gathering and analysis procedures so that reports can be completed in a timely manner, cold chain logistics, MLM modules, procedures for gathering, inputting and communicating EPI data. | 4th quarter 2011 – 1st quarter 2012 |
| - Improve the quality of EPI data at all levels. | 4th quarter 2011 – 1st quarter 2012 |
| - Make certain there is a regular supply of data-gathering tools at each prefecture. | 4th quarter 2011 – 1st quarter 2012 |
| - Obtain medium-term technical assistance (6-12 months) from the partners to strengthen the programme and implement the recommendations from the EVM assessment. | 4th quarter 2011 – 1st quarter 2012 |

Signatures of the Government

Enter the family name in capital letters.

| Minister of Health (or delegated authority) |  | Minister of Finance (or delegated authority) |  |
| --- | --- | --- | --- |
| Name | Mr. Jan Michel MANDABA | Name | Lt. Col. Sylvain NDOUTINGAI |
| Date |  | Date |  |
| Signature |  | Signature |  |

This report has been compiled by (these persons may be contacted in case the GAVI Secretatiat has queries on this document):

Enter the family name in capital letters.

| Full name | Position | Telephone | Email |
| --- | --- | --- | --- |
| Rock OUAMBITA-MABO | EPI Director | (00236) 70407808 | Ouambita_mr@yahoo.fr |