|  |  |  |  |  | [V2.7]. |  |
| --- | --- | --- | --- | --- | --- | --- |
| GAVI Alliance. |
| Application Form for Country Proposals. |
| For Support to:. |
| Routine New Vaccines Support. |
| Submitted by. |
| The Government of. |
| Mali. |
| Date of submission: 8/29/2012. |
| Deadline for submission: 8/31/2012. |
| Select Start and End Year of your Comprehensive Multi-Year Plan (cMYP). |
| Start Year. | 2012. |  |  |  |  |  |  |
|  |  |  | End Year. | 2016. |  |  |
| Form revised in 2012. |
| (To be used with Guidelines of September 2012). |
| Please submit the Proposal using the online platform. https://AppsPortal.gavialliance.org/PDExtranet. |
| Enquiries to: proposals@gavialliance.org or representatives of a GAVI partner agency. The documents can be shared with GAVI partners, collaborators and general public. The Proposal and attachments must be submitted in English, French, Spanish, or Russian.. Note: Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline.. The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents will be shared with the GAVI Alliance partners and the general public.. |

GAVI ALLIANCE GRANT TERMS AND CONDITIONS. FUNDING USED SOLELY FOR APPROVED PROGRAMMES. The applicant country ("Country") confirms that all funding provided by the GAVI Alliance will be used and applied for the sole purpose of fulfilling the programme(s) described in the Country's application. Any significant change from the approved programme(s) must be reviewed and approved in advance by the GAVI Alliance. All funding decisions for the application are made at the discretion of the GAVI Alliance Board and are subject to IRC processes and the availability of funds.. AMENDMENT TO THE APPLICATION. The Country will notify the GAVI Alliance in its Annual Progress Report if it wishes to propose any change to the programme(s) description in its application.The GAVI Alliance will document any change approved by the GAVI Alliance, and the Country's application will be amended.. RETURN OF FUNDS. The Country agrees to reimburse to the GAVI Alliance all funding amounts that are not used for the programme(s) described in its application. The country's reimbursement must be in US dollars and be provided, unless otherwise decided by the GAVI Alliance, within sixty (60) days after the Country receives the GAVI Alliance's request for a reimbursement and be paid to the account or accounts as directed by the GAVI Alliance.. SUSPENSION/ TERMINATION. The GAVI Alliance may suspend all or part of its funding to the Country if it has reason to suspect that funds have been used for purpose other than for the programmes described in the Country's application, or any GAVI Alliance-approved amendment to the application.The GAVI Alliance retains the right to terminate its support to the Country for the programmes described in its application if a misuse of GAVI Alliance funds is confirmed.. ANTICORRUPTION. The Country confirms that funds provided by the GAVI Alliance shall not be offered by the Country to any third person, nor will the Country seek in connection with its application any gift, payment or benefit directly or indirectly that could be construed as an illegal or corrupt practice.. AUDITS AND RECORDS. The Country will conduct annual financial audits, and share these with the GAVI Alliance, as requested. The GAVI Alliance reserves the right, on its own or through an agent, to perform audits or other financial management assessment to ensure the accountability of funds disbursed to the Country.. The Country will maintain accurate accounting records documenting how GAVI Alliance funds are used. The Country will maintain its accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of GAVI Alliance funds. If there is any claims of misuse of funds, Country will maintain such records until the audit findings are final. The Country agrees not to assert any documentary privilege against the GAVI Alliance in connection with any audit.. CONFIRMATION OF LEGAL VALIDITY. The Country and the signatories for the Country confirm that its application, and Annual Progress Report, are accurate and correct and form legally binding obligations on the Country, under the Country's law, to perform the programmes described in its application, as amended, if applicable, in the APR.. CONFIRMATION OF COMPLIANCE WITH THE GAVI ALLIANCE TRANSPARANCY AND ACCOUNTABILITY POLICY. The Country confirms that it is familiar with the GAVI Alliance Transparency and Accountability Policy (TAP) and complies with the requirements therein.. USE OF COMMERCIAL BANK ACCOUNTS. The Country is responsible for undertaking the necessary due diligence on all commercial banks used to manage GAVI cash-based support. The Country confirms that it will take all responsibility for replenishing GAVI cash support lost due to bank insolvency, fraud or any other unforeseen event.. ARBITRATION. Any dispute between the Country and the GAVI Alliance arising out of or relating to its application that is not settled amicably within a reasonable period of time, will be submitted to arbitration at the request of either the GAVI Alliance or the Country. The arbitration will be conducted in accordance with the then-current UNCITRAL Arbitration Rules. The parties agree to be bound by the arbitration award, as the final adjudication of any such dispute. The place of arbitration will be Geneva, Switzerland. . The languages of the arbitration will be English or French.. For any dispute for which the amount at issue is US$ 100,000 or less, there will be one arbitrator appointed by the GAVI Alliance. For any dispute for which the amount at issue is greater than US $100,000 there will be three arbitrators appointed as follows: The GAVI Alliance and the Country will each appoint one arbitrator, and the two arbitrators so appointed will jointly appoint a third arbitrator who shall be the chairperson.. The GAVI Alliance will not be liable to the country for any claim or loss relating to the programmes described in the application, including without limitation, any financial loss, reliance claims, any harm to property, or personal injury or death. Country is solely responsible for all aspects of managing and implementing the programmes described in its application..

1. Application Specification Please specify for which type of GAVI support you would like to apply to..

Type of Support; Vaccine; Start Year; End Year; Preferred second presentation[1]. Routine New Vaccines Support; Rotavirus, 3 -dose schedule; 2013; 2016; Rotavirus, 2 -dose schedule.

[1] This "Preferred second presentation" will be used in case there is no supply available for the preferred presentation of the selected vaccine ("Vaccine" column). If left blank, it will be assumed that the country will prefer waiting until the selected vaccine becomes available..

2. Table of Contents.

1. Application Specification. 2. Table of Contents. 3. Executive Summary. 4. Signatures. 4.1. Signatures of the Government and National Coordinating Bodies. 4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation. 4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation. 4.1.3. The Inter-Agency Coordinating Committee for Immunisation. 4.2. National Immunization Technical Advisory Group for Immunisation. 4.2.1. The NITAG Group for Immunisation. 5. Immunisation Programme Data. 5.1. Basic facts. 5.2. Baseline and Annual Targets (NVS Routine Support). 5.3. Baseline and Annual Targets for Preventive Campaign(s). 6. New and Under-Used Vaccines (NVS Routine). 6.1. Assessment of burden of relevant diseases (if available). 6.2 Requested vaccine (Rotavirus, 3 -dose schedule). 6.2.1 Co-financing information. 6.2.2 Specifications of vaccinations with new vaccine. 6.2.3 Portion of supply to be procured by the country (and cost estimate, US$). 6.2.4 Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$). 6.2.5 New and Under-Used Vaccine Introduction Grant. 7. NVS Preventive Campains. 8. Procurement and Management. 8.1. Procurement and Management of New and Under-Used Vaccines Routine. 8.2. Procurement and Management for NVS Preventive Campaign(s). 8.3. Vaccine Management (EVSM/EVM/VMA). 9. Additional Comments and Recommendations from the National Coordinating Body (ICC/HSCC). 10. Attachments. 11. Annexes. Annex 1 - NVS Routine Support. Annex 1.1 Rotavirus, 3 -dose schedule. Table Annex 1.1 A Rounded up portion of supply that is procured by the country and estimate of relative costs in US$. Table Annex 1.1 B Rounded up portion of supply that is procured by GAVI and estimate of relative costs in US$. Table Annex 1.1 C Summary table for vaccine Rotavirus, 3 -dose schedule. Table Annex 1.1 D Estimated numbers for Rotavirus, 3 -dose schedule, associated injection safety material and related co-financing budget (page 1). Annex 2 - NVS Routine – Preferred Second Presentation. Annex 2.1 Rotavirus, 2 -dose schedule. Table Annex 2.1 A Rounded up portion of supply that is procured by the country and estimate of relative costs in US$. Table Annex 2.1 B Rounded up portion of supply that is procured by GAVI and estimate of relative costs in US$. Table Annex 2.1 C Summary table for vaccine Rotavirus, 2 -dose schedule. Table Annex 2.1 D Estimated numbers for Rotavirus, 2 -dose schedule, associated injection safety material and related co-financing budget (page 1). Annex 3 - NVS Preventive campaign(s). Annex 4. Table Annex 4A: Commodities Cost. Table Annex 4B: Freight cost as percentage of value. Table Annex 4C: Low - Minimum country's co-payment per dose of co-financed vaccine.. Table Annex 4D: Wastage rates and factors. Table Annex 4E: Vaccine maximum packed volumes. 12. Banking Form.

3. Executive Summary.

Please provide a summary of your country's proposal, including the following the information:. ; For each specific request, NVS routine support or NVS campaign :. ; The duration of support. ; The total amount of funds. ; Details of the vaccine(s), if applicable. ; Relevant baseline data, including:. ; DTP3 and Measles coverage data (as reported on the WHO/UNICEF Joint Reporting Form). ; Birth cohort, targets and immunisation coverage by vaccines. ; Country preparedness. ; Summary of EVM assessment. ; The nature of stakeholders' participation in developing this proposal. ; Inter-Agency Coordinating Committee. Every year, rotavirus-related diarrhoea kills nearly 800,000 children under five in Africa (Boschi- Puito et al, Bull Word Health 2008, Black RE et al, Lancet 2010). Recent surveillance data from the CVD-Mali study (2008-2011) (Global Enteri Multicentre Study in Africa and Asia (GEMS)) from hospitals and communities in the Bamako district about moderate and severe diarrhoea in children 0-5 years shows that rotavirus is the primary causative pathogen of diarrhoeas. The proportions attributable to rotavirus are, respectively: 21% in children 0-11 months, 12% in children 12-23 months and 4% in children 24-59 months. The estimated annual incidence is 8.0, 4.0 and 0.4 per 100 child years of observation in 0-11 months, 12-23 months and 24-59 months, respectively. This allows us to estimate the number of new rotavirus-related diarrhoea cases in Mali at about 60,000 children under age one, with a very high mortality due to factors that limit proper treatment (severe status of cases seen late in health facilities, self-medication, inadequate modern or traditional consultations, absence of adequate etiological treatment, etc.). Rotavirus diarrhoea is responsible for more than half of all hospitalizations for severe diarrhoea in children in the Paediatrics Unit of the Gabriel Touré Hospital. Unlike other diarrhoeal diseases like cholera or shigella, which can be prevented by using potable water and good food and sanitation hygiene, vaccination is the only method of preventing rotavirus diarrhoea. Because effective, well-tolerated vaccines exits, and following the WHO recommendation to introduce the rotavirus vaccine into routine immunisation programmes in developing countries, it is both important and urgent that our country is able to benefit from this opportunity offered by GAVI and other partners. In accordance with its comprehensive Multi-Year Plan (cMYP) for 2012-2016, and as part of accelerating achievement of the MDGs, Mali opted to introduce the 3-dose rotavirus vaccine Rotateq into the EPI in 2013, with GAVI support. This introduction will occur over three progressive stages (see attached introduction plan): The first stage, in 2013, will concern coverage for the capital city of Bamako (15% of the target is found in the capital Bamako); The second stage, in 2014, will cover the county seats in the regions of Mali (25% of the target is found in the regional capitals of Mali, in addition to the 15% in Bamako, for a total of 40%); The third stage, in 2015, will cover the remainder of the country (60% of the target is found in the remainder of the country, in addition to the above 40%). The State has made significant efforts to implement the recommendations from the Effective Vaccine Management assessment. To this end, two (2) cold room of 30m3 each were acquired from the State budget. These two cold rooms will be installed by December 2012, which will eliminate the storage capacity deficit at the central level. Also, a plan for renewing and strengthening the cold chain has been drawn up that takes the energy transition (gas to solar) into account. Several initiatives are under way to strengthen routine immunisation activities and to increase vaccine coverage in all regions. In 2011 the programme achieved satisfactory results: BCG 100%; OPV3 87%; MCV: 82%; and Penta3 88%. Technical partners and civil society organisations helped alongside State technical services in drawing up this submission document. For the first year of introduction, the rotavirus vaccine requirement will be 396,000 doses, for an estimated cost of US$1,455,500, including cofinancing by the State for the amount of US$79,500. State expenditures in 2013 for the purchase and cofinancing of routine EPI vaccines is expected to reach US$7,014,462, or 3,703,635,936 FCFA..

| 4. Signatures. |
| --- |
| 4.1. Signatures of the Government and National Coordinating Bodies. |
| 4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation. |
| The Government of Mali would like to expand the existing partnership with the GAVI Alliance for the improvement of the infants routine immunisation programme of the country, and specifically hereby requests for GAVI support for. |
|  | Rotavirus, 1 dose(s) per vial, ORAL routine introduction. |  |
| The Government of Mali commits itself to developing national immunisation services on a sustainable basis in accordance with the Comprehensive Multi-Year Plan presented with this document. The Government requests that the GAVI Alliance and its partners contribute financial and technical assistance to support immunisation of children as outlined in this application.. |
| Table(s) 6.2.4 in the NVS Routine section of this application shows the amount of support in either supply or cash that is required from the GAVI Alliance. Table(s) 6.2.3 of this application shows the Government financial commitment for the procurement of this new vaccine (NVS support only).. |
| Following the regulations of the internal budgeting and financing cycles the Government will annually release its portion of the co-financing funds in the month of March.. |
| The payment for the first year of co-financed support will be around September 2013 for Rotavirus, 1 dose(s) per vial, ORAL.. |
| Please note that this application will not be reviewed or approved by the Independent Review Committee (IRC) without the signatures of both the Minister of Health and Minister of Finance or their delegated authority.. |
| Minister of Health (or delegated authority); Minister of Finance (or delegated authority). Name; Mr Soumana MAKADJI; Name; Mr Marimpa SAMOURA. Date; Date. Signature; Signature. |
| This report has been compiled by (these persons may be contacted in case the GAVI Secretatiat has queries on this document):. |
| Full name; Position; Telephone; Email. Dr Baba TOUNKARA; WHO IVD Advisor, Mali; 00223 75 24 68 01; tounkarab@ml.afro.who.int. Dr Etienne DEMBELE; UNICEF EPI Advisor, Mali; 00223 66 90 04 07; edembele@unicef.org. Dr Aboubacrine MAIGA; Focal Point, HSS CPS/SS/DS/PF Mali; 00223 75 49 72 78; aboubacrinemaiga@hotmail.com. Dr Alboucary TOURE; Head, Immunisation Section; 00223 76 31 78 40/ 00223 69 55 62 93; cni@afribonemali.net/albouharytoure@gmail.com. Dr Ibrahim DOLO; PEV/ATNplus/USAID Advisor, Mali; 00223 20 24 17 52; idoloatnsante.org. Dr Sarmoye CISSE; WHO Health Systems Advisor, Mali; 00223 66 81 33 17; cisses@ml.afro.who.int. |
| 4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation. |
| We the members of the ICC, HSCC, or equivalent committee [1] met on the 13/08/2012 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.. |
| [1] Inter-agency Coordinating Committee or Health Sector Coordinating Committee, or equivalent committee which has the authority to endorse this application in the country in question.. |
| The endorsed minutes of this meeting are attached as document number 4.. |
| Name/Title*; Agency/Organisation*; Signature. Dr DIALLO Fatoumata Binta T./WHO Representative; World Health Organization, Mali. Dr Mamadou Namory TRAORE/National Director of Health; Ministry of Health. Dr Mountaga BOUARE/Technical Advisor; Ministry of Health. Dr Nouhoum COULIBALY; Lion's Club. Dr Souleymane DOLO/Director; Health and Population Pivot Group. Mme Rebecca BLACK/Director; USAID Mali. Mr Daouda SACKO/Chair, National Polio Plus Commission; Rotary International Mali. Mr Souleymane TRAORE/Director of Finance and Equipment; Ministry of Health. Mr Soumana MAKADJI/ Minister of Health; Ministry of Health. Mr Théophane NIKYEMA/Interim Representative; UNICEF Mali. Pr Mamadou Souncalo TRAORE/Secretary General; Ministry of Health. |
| 4.1.3. The Inter-Agency Coordinating Committee for Immunisation. |
| Agencies and partners (including development partners and NGOs) supporting immunisation services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC, HSCC, or equivalent committee). The ICC, HSCC, or equivalent committee is responsible for coordinating and guiding the use of the GAVI NVS routine support and/or campaign support. Please provide information about the ICC, HSCC, or equivalent committee in your country in the table below.. |
| Profile of the ICC, HSCC, or equivalent committee. |
| Name of the committee; ICC. Year of constitution of the current committee; 2002. Organisational structure (e.g., sub-committee, stand-alone); ICC, technical committee. Frequency of meetings; 1 regular meeting per quarter. |
| Composition. |
| Function; Title / Organisation; Name. Chair; Minister of Health/Ministry of Health; Mr Soumana MAKADJI. Secretary; National Director of Health//Ministry of Health; Dr Mamadou Namory TRAORE. Members; Secretary General/Ministry of Health; Pr Mamadou Souncalo TRAORE. Technical Advisor/Ministry of Health; Dr Mountaga BOUARE. Director of Finance and Equipment/Ministry of Health; Mr Souleymane TRAORE. WHO Representative/World Health Organization, Mali; Dr DIALLO Fatoumata Binta T.. Director/USAID Mali; Ms Rebecca BLACK. Mr Daouda SACKO/ Chair, National Polio Plus Commission; Rotary International Mali. Interim Representative/UNICEF Mali; Mr Théophane NIKYEMA. Director/Health/Population Pivot Groiup; Dr Souleymane DOLO. |
| Major functions and responsibilities of the ICC/HSCC:. |
| Mali’s ICC has been operational since 2002 and fully involved in its multiple roles supporting and monitoring the EPI in the country. It approves all the cMYPs as well as all immunisation activity plans submitted by the Technical Committee, such as the new vaccine introduction plan, plans to eliminate and control measles, yellow fever and maternal and neonatal tetanus, and the polio eradication plan. It also approves plans for implementing Supplementary Immunisation Activities (polio, measles, yellow fever, tetanus, meningitis, etc.). The ICC also plays a M&E role in the implementation of scheduled immunisation activities and in the mobilisation of required resources.. |
| Three major strategies to enhance the committee's role and functions in the next 12 months. |
| 1.; Holding quarterly regular meetings of the ICC with the effective presence of members. 2.; Opening the ICC to certain civil society organisations, like NGOs involved in northern Mali and in child survival; also the HSS arm. 3.; Making decisions regarding the level of vaccine coverage indicators and resource mobilisation. |
| 4.2. National Immunization Technical Advisory Group for Immunisation. |
| (If it has been established in the country). |
| We the members of the NITAG met on the to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.. |
| The endorsed minutes of this meeting are attached as document number 4.. |

4.2.1. The NITAG Group for Immunisation.

Profile of the NITAG.

Name of the NITAG; Non applicable. Year of constitution of the current NITAG. Organisational structure (e.g., sub-committee, stand-alone). Frequency of meetings.

Composition.

Function; Title / Organisation; Name. Chair. Secretary. Members.

Major functions and responsibilities of the NITAG.

NITAG is not yet set up in Mali.

Three major strategies to enhance the NITAG's role and functions in the next 12 months.

1.. 2.. 3..

5. Immunisation Programme Data.

5.1. Basic facts.

Please complete the tables below, using data from available sources. Please identify the source of the data, and the date. Where possible use the most recent data and attach the source document..

▪; Please refer to the Comprehensive Multi-Year Plan for Immunisation (cMYP) (or equivalent plan) and attach a complete copy (with an Executive Summary) as DOCUMENT NUMBER : 6. ▪; Please attach relevant Vaccine Introduction Plans as DOCUMENT NUMBER : 7. ▪; Please refer to the two most recent annual WHO/UNICEF Joint Reporting Forms (JRF) on Vaccine Preventable Diseases. ▪; Please refer to Health Sector Strategy documents, budgetary documents, and other reports, surveys etc, as appropriate..

For the year 2011 (most recent; specify dates of data provided).

Figure; Year; Source. Total population; 15,593,555; 2011; GCPH 2009. Infant mortality rate (per 1000); 96; 2006; EDS-Mali IV. Surviving infants[1]; 624,478; 2011; GCPH 2009. GNI per capita (US$); 620; 2011; Ministry of Finance. Total Health Expenditure (THE) as a percentage of GDP; 7; %; 2006; CNS. General government expenditure on health (GGHE) as % of General government expenditure; 12; %; 2010; Ministry of Finance.

[1] Surviving infants = Infants surviving the first 12 months of life.

Please provide some additional information on the planning and budgeting context in your country. References used include health sector policy documents, the Ten-year Health and Social Development Plan, the Strategic Framework for Growth and Poverty Reduction (CSCRP), the Medium-Term Expenditure Framework (MTEF) for the Ministry of Health (2012-2014), the Medium-Term Budget Framework (MTBF) for the Ministry of the Economy and Finance (2012-2014), GIVS (2006-2015), the 2006 EPI review, the 2006 EDS IV, the 2009-2010 vaccine coverage assessment, the Strategic Plan to Combat Poliomyelitis (2010-2012), the Strategic Plan to Combat Measles (2006-2009) and various departmental activity reports.. Please indicate the name and date of the relevant planning document for health. 2005-2009 Health and Social Development Programme (Programme de Développement Sanitaire et Social, PRODESS II). Note: PRODESS II was extended in 2012. A new ten-year plan for health and social development is being developed. Is the CMYP (or updated Multi-Year Plan) aligned with the document (timing, content, etc.). The contents of the updated multi-year plan conforms with the major directions of policy documents (PRODESS II), the extension of which will allow them to have the same cycle.. Please indicate the national planning budgeting cycle for health. Activities to strengthen immunisation services are scheduled into the Ministry of Health’s annual action plans through the operational plan for the National Health Directorate (Direction nationale de la santé, DNS). Goods and services are procured through PRODESS management procedures. Activity implementation is assessed in the National Health Directorate’s annual assessment framework. Through its Immunisation Section, the National Health Directorate assesses the country’s needs for immunisation service strengthening. The budget associated with these activities is submitted to the ICC for approval before being executed. Funding requests for scheduled activities are financed according to the procedures for the “ACCT” account. Funds are mobilized upon DNS request to the DFM. The DFM attaches the ACCT. The Ministry of health planning cycle follows that for the Ministry of Finance budget process. This is a “bottom-up” process that follows national reference documents (MTEF, CSCRP, PRODESS prorities): - Circle management council, -CROCEP at the Region level and National Assessment Days for central structures (March-April), -State budget arbitration (June) - PRODESS Technical Committee (April/May) and Monitoring Committee (September) for validating Operational Plans at the national level. Please indicate the national planning cycle for immunisation. Activities to strengthen immunisation services are scheduled into the Ministry of Health’s annual action plans through the operational plan for the National Directorate for Health. Goods and services are procured through PRODESS management procedures. Activity implementation is assessed in the National Health Directorate’s annual assessment framework. Through its Immunisation Section, the National Health Directorate assesses the country’s needs for immunisation service strengthening. The budget associated with these activities is submitted to the ICC for approval before being executed. Funding requests for scheduled activities are financed according to the procedures for the “ACCT” account. Funds are mobilized upon DNS request to the DFM. The DFM attaches the ACCT. The Ministry of Health planning cycle follows that for the Ministry of Finance budget process. This is a “bottom-up” process that follows national reference documents (MTEF, CSCRP, PRODESS prorities): -- Circle management council, - CROCEP at the Region level and National Assessment Days for central structures (March-April), - State budget arbitration (June) - PRODESS Technical Committee (April/May) and Monitoring Committee (September) for validating Operational Plans at the national level. Please indicate if sex disaggregated data (SDD) is used in immunisation routine reporting systems. No. Please indicate if gender aspects relating to introduction of a new vaccine have been addressed in the introduction plan. No sex discrimination in Mali. Please describe any recent evidence of socio-economic and/or gender barriers to the immunisation programme through studies or surveys?. Not available. Country should provide an outline of all preparatory activities for vaccine(s) introduction. The plan for introducing the rotavirus vaccine in Mali has been prepared and will be appended to the proposal as an annex. Tools (immunisation card, register) and the communication plan were subsequently revised..

5.2. Baseline and Annual Targets (NVS Routine Support)

Please refer to cMYP pages to assist in filling-in this section..

Number; Base Year; Baseline and Targets; Baseline and Targets; Baseline and Targets; Baseline and Targets. 2011; 2013; 2014; 2015; 2016. Total births; 690,794; 741,427; 768,118; 795,771; 824,418. Total infants’ deaths; 66,316; 71,177; 73,739; 76,394; 79,144. Total surviving infants; 624,478; 670,250; 694,379; 719,377; 745,274. Total pregnant women; 779,678; 836,825; 866,951; 898,161; 930,495. Target population vaccinated with BCG; 691,802; 689,527; 737,394; 787,813; 816,174. BCG coverage; 100 %; 93 %; 96 %; 99 %; 99 %. Target population vaccinated with OPV3. OPV3 coverage; 87 %; 83 %; 86 %; 89 %; 95 %. Number of infants vaccinated (to be vaccinated) with DTP1; 636,411; 623,333; 666,604; 712,183; 782,538. Number of infants vaccinated (to be vaccinated) with DTP3; 547,144; 556,307; 597,166; 640,245; 708,010. DTP3 coverage; 88 %; 83 %; 86 %; 89 %; 95 %. Wastage[1] rate in base-year and planned thereafter (%) for DTP; 5; 5; 5; 5; 5. Wastage[1] factor in base-year and planned thereafter for DTP; 1.05; 1.05; 1.05; 1.05; 1.05. Target population vaccinated with 1st dose of Rotavirus; 0; 100,537; 277,752; 712,183; 782,538. Target population vaccinated with 2nd dose of Rotavirus; 0; 100,537; 277,752; 640,245; 708,010. Rotavirus coverage; 0 %; 15 %; 40 %; 89 %; 95 %. First Presentation: Rotavirus, 3-dose schedule. Wastage[1] rate in base-year and planned thereafter (%); 0; 5; 5; 5; 5. Wastage[1] factor in base-year and planned thereafter (%); 1.00; 1.05; 1.05; 1.05; 1.05. Maximum wastage rate value for Rotavirus, 3-dose schedule; 5 %; 5 %; 5 %; 5 %; 5 %. Second Presentation: Rotavirus, 2-dose schedule. Wastage[1] rate in base-year and planned thereafter (%); 0; 0; 0; 0; 0. Wastage[1] factor in base-year and planned thereafter (%); 1.00; 1.00; 1.00; 1.00; 1.00. Maximum wastage rate value for Rotavirus, 2-dose schedule; 5 %; 5 %; 5 %; 5 %; 5 %. Target population vaccinated with 1st dose of Measles; 509,571; 522,795; 562,447; 604,276; 648,389. Measles coverage; 82 %; 78 %; 81 %; 84 %; 87 %. Number of infants vaccinated (to be vaccinated) with 1st dose of TT+; 464,604; 694,565; 866,951; 898,161; 930,495. TT+ coverage; 60 %; 83 %; 100 %; 100 %; 100 %. Annual DTP Drop out rate [ ( DTP1 – DTP3 ) / DTP1 ] x 100; 14 %; 11 %; 10 %; 10 %; 10 %.. [1] Number of infants vaccinated out of total births. [2] Number of infants vaccinated out of total surviving infants. [3] Indicate total number of children vaccinated with either DTP alone or combined. [4] Number of pregnant women vaccinated with TT+ out of total pregnant women. [5] The formula to calculate a vaccine wastage rate (in percentage): [ ( A - B ) / A ] x 100. Whereby: A = the number of doses distributed for use according to the supply records with correction for stock balance at the end of the supply period; B = the number of vaccinations with the same vaccine in the same period...

5.3. Baseline and Annual Targets for Preventive Campaign(s)

No NVS Prevention Campaign Support this year.

6. New and Under-Used Vaccines (NVS Routine)

6.1. Assessment of burden of relevant diseases (if available).

Disease; Title of the assessment; Date; Results. Rotavirus diarrhoea; Multicentre surveillance of diarrhoeal diseases in hospital and community environments; December 2007 to December 2011; For 2008-2011, the incidence of moderate/severe rotavirus diarrhoeas in Bamako, Mali was: - children 0-11 months = 8.0 per 100 people/year/observation- children 12-23 months = 4.0 per 100 people/year/observation- children 24-59 months = 0.4 per 100 people/year/observation.

If new or under-used vaccines have already been introduced in your country, please give details of the lessons learned from previous introduction(s) specifically for: storage capacity, protection from accidental freezing, staff training, cold chain, logistics, coverage and drop-out rates, wastage rate, etc., and suggest action points to address them..

Lessons Learned; Action Points. 1. Thanks to Japanese funds received in 2010, strengthening of cold chain capacity significantly helped in improving the vaccine supply and distribution system in Mali. 2. Initiatives developed to strengthen routine EPI (performance contracts, SASDE, SOS, RED approach, ARIVA project) and the advent of GAVI support have allowed health districts to improve their vaccine coverage performance from 2002 to today. 3. New vaccine introduction has been an opportunity for the EPI in that: - supervisions were conducted more frequently than usual;- the cold chain was strengthened;- vaccine coverage was significantly improved; Introduce the rotavirus diarrhoea vaccine into the routine EPI in Mali. Strengthen the surveillance of diarrhoeal diseases. Conduct an impact study before and after the vaccine introduction with the support of the Centre for Vaccine Development (CVD-Mali / CNAM)..

Please list the vaccines to be introduced with support from the GAVI Alliance (and presentation).

Oral rotavirus, 3-dose, liquid in single-dose vial (Rotateq).

6.2. Requested vaccine (Rotavirus, 3 -dose schedule). As reported in the cMYP, the country plans to introduce Rotavirus, using Rotavirus, 3 -dose schedule.. 6.2.1. Co-financing information. If you would like to co-finance higher amount than minimum, please overwrite information in the Your co-financing row... Country group; Low.. Year 1; Year 2; Year 3; Year 4. 2013; 2014; 2015; 2016. Minimum co-financing; 0.13; 0.13; 0.13; 0.13. Your co-financing (please change if higher); 0.20; 0.20; 0.20; 0.20.. 6.2.2. Specifications of vaccinations with new vaccine.. Data from; Year 1; Year 2; Year 3; Year 4. 2013; 2014; 2015; 2016. Number of children to be vaccinated with the first dose; Table 5.2; #; 100,537; 277,752; 712,183; 782,538. Number of children to be vaccinated with the third dose; Table 5.2; #; 100,537; 277,752; 640,245; 708,010. Immunisation coverage with the third dose; Table 5.2; #; 15.00 %; 40.00 %; 89.00 %; 95.00 %. Country co-financing per dose [1]; Table 6.2.1; $; 0.2; 0.2; 0.2; 0.2.. [1] Total price per-dose includes vaccine cost, plus insurance, etc....

6.2.3. Portion of supply to be procured by the country (and cost estimate, US$)... 2013; 2014; 2015; 2016. Number of vaccine doses; #; 21,600; 55,300; 140,800; 137,200. Number of AD syringes; #; 0; 0; 0; 0. Number of re-constitution syringes; #; 0; 0; 0; 0. Number of safety boxes; #; 0; 0; 0; 0. Total value to be co-financed by country; $; 79,500; 203,000; 517,500; 504,500... 6.2.4. Portion of supply to be procured by the GAVI Alliance (and cost estimate, US$).. 2013; 2014; 2015; 2016. Number of vaccine doses; #; 374,400; 959,300; 2,444,800; 2,383,300. Number of AD syringes; #; 0; 0; 0; 0. Number of re-constitution syringes; #; 0; 0; 0; 0. Number of safety boxes; #; 4,400; 11,275; 25,575; 25,350. Total value to be co-financed by country; $; 1,376,000; 3,525,500; 8,985,000; 8,758,500....

6.2.5. New and Under-Used Vaccine Introduction Grant.. Please indicate in the tables below the full costs/needs and how the one-time Introduction Grant [1] will be used to support the costs of vaccine introduction and critical pre-introduction activities (refer to the cMYP). GAVI’s support may not be enough to cover the full needs so please indicate in the table below how much and who will be complementing the funds needed.. Calculation of lump-sum for the Rotavirus, 3 -dose schedule.. Year of New Vaccine Introduction; Births (from Table 5.2); Share per Birth in US$; Total in US$. 2013; 741,427; 0.80; 593,142.. [1] The Grant will be based on a maximum award of $0.80 per infant in the birth cohort with a minimum starting grant award of $100,000.. Cost (and finance) to introduce the Rotavirus, 3 -dose schedule US$.. Cost Category. Full needs for new vaccine introduction in US$; Funded with GAVI introduction grant in US$. Training; 219,884. Social Mobilization, IEC and advocacy; 18,939. Cold Chain Equipment & Maintenance; 151,452; 223,148. Vehicles and Transportation; 66,288. Programme Management; 47,818. Surveillance and Monitoring; 17,045. Human Resources; 0. Waste Management; 0. Technical Assistance; 0. Other (please specify). Total; 151,452; 593,122..... Please describe other sources of funding if available to cover your full needs.. The State (government) funded the purchase and installation of two (2) cold rooms, 30m3 each, for a total of US$151,452 (see attached allocation for rota introduction)....

7. NVS Preventive Campains

No NVS Prevention Campaign Support this year.

8. Procurement and Management.

8.1. Procurement and Management of New and Under-Used Vaccines Routine.

Note: The PCV vaccine must be procured through UNICEF to be able to access the price awarded by the Advance Market Commitment (AMC)..

a) Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that most countries will procure vaccine and injection supplies through UNICEF):. The Government of Mali has signed a vaccine and supplies procurement assistance agreement with UNICEF since 1996. All traditional and new or under-used vacines are procured through this route. Co-financing will be paid through the UNICEF Representation office in Mali, through UNICEF supply in Copenhagen (Denmark).. b) If an alternative mechanism for procurement and delivery of vaccine supply (financed by the country or the GAVI Alliance) is requested, please document. ; Other vaccines or immunisation commodities procured by the country and descriptions of the mechanism used.. ; The functions of the National Regulatory Authority (as evaluated by WHO) to show they comply with WHO requirements for procurement of vaccines and supply of assured quality.. Mali will not be using any other vaccine procurement mechanism. c) Please describe the introduction of the vaccines (refer to cMYP). Introduction of the rotavirus vaccine was approved by the ICC ahead of time. Preparatory activities (training, communication and social mobilisation, strengthening of logistics and surveillance, etc.) for this introduced should be conducted before February 2013. The vaccine will be introduced in three stages. The first stage will concern the country’s capital city (Bamako in 2013), the second will concern regional capitals (2014) and the third will cover the entire country (starting in 2015). There will not be any catch-up doses for children over 12 months. The Government of Mali has opted for the oral liquid 3-dose rotavirus vaccine in the single-dose vial presentation.. d) Please indicate how funds should be transferred by the GAVI Alliance (if applicable). GAVI funds should be transferred into an account called “ISS projects accont” at the Mali Ministry of Health.. e) Please indicate how the co-financing amounts will be paid (and who is responsible for this). State co-financing will be paid through the UNICEF Representation office in Mali. Co-financing amounts will be transferred by the Mali Public Treasury into a UNICEF account. The Director of Finances and Equipment in the MInistry of Health is responsible for such transfer operations.. f) Please outline how coverage of the new vaccine will be monitored and reported (refer to cMYP). Monthly reports provided by the various structures will be recorded in the Immunisation Register” file to enable coverage to be calculated. Reports will be sent monthly to the country’s WHO office. At the end of each year, a joint Government-WHO-UNICEF report and a GAVI progress report will be provided. A post-introduction assessment of the rotavirus vaccine will be performed in 2014. Studies will be conducted by the CVD/CNAM-Mali to determine the impact of rotavirus vaccine introduction in selected communities (in terms of morbidity, mortality and immune status)..

8.2. Procurement and Management for NVS Preventive Campaign(s).

No NVS Prevention Campaign Support this year.

8.3. Vaccine Management (EVSM/EVM/VMA).

Did the country have Effective Vaccine Management Assessment (VMA) in the past? Yes. When was the last VMA conducted? December 2007. Did the country have Effective Vaccine Store Management (EVSM) in the past? Yes. When was the last EVSM conducted? July 2005. Did the country have Effective Vaccine Management (EVM) in the past? Yes. When was the EVM conducted? July 2011. If your country conducted either EVSM or VMA in the past two years, please attach relevant reports. (Document N°8). A VMA report must be attached from those countries which have introduced a New and Underused Vaccine with GAVI support before 2008.. Please note that Effective Vaccine Store Management (EVSM) and Vaccine Management Assessment(VMA) tools have been replaced by an integrated Effective Vaccine Management (EVM) tool. The information on EVM tool can be found at http://www.who.int/immunization_delivery/systems_policy/logistics/en/index6.html. For countries which conducted EVSM, VMA or EVM in the past, please report on activities carried out as part of either action plan or improvement plan prepared after the EVSM/VMA/EVM.. Cold chain capacity has been strengthened at all levels (central, intermediate and operational) with the construction of five (5) cold rooms and the provision of refrigerators and vaccine carriers. Staff competencies have been strengthened in all regions. Acquisition of two (2) cold rooms, 30m3 each, by the State.. Does the country plan to conduct an Effective Vaccine Management (EVM) Assessment in the future? Yes. When is the next Effective Vaccine Management (EVM) Assessment planned? July 2014. Under new guidelines, it will be mandatory for the countries to conduct an EVM prior to an application for introduction of new vaccine..

9. Additional Comments and Recommendations from the National Coordinating Body (ICC/HSCC).

Comments and Recommendations from the National Coordinating Body (ICC/HSCC).

Specify the reasons why the initial submission proposals for this vaccine were not accepted; Review the deadline for the Ten-Year Social-Heatlh Plan (Plan Décennal Socio Sanitaire, PDSS); In the section of Mali’s experience in introducing new vaccines, highlight the meningitis A immunisation campaign with MenAfriVacTM , which was led in three phases in Mali; Only include cold rooms actually acquired when planning for cold chain equipment. The Health/Population Pivot Group representative drew participants’ attention to a need for advocacy for acquiring and installing cold rooms at the central level. The CVD-CNAM representative confirmed that the vaccine proposed by Mali is in fact the oral 3-dose Rotateq vaccine that was the subject of research by the Centre for Vaccines in Development in Mali. The WHO representative expressed concerns about the non-installation of the cold rooms paid for by the State, which could be a stumbling block for GAVI regarding introduction of this vaccine. The representative from the Directorate of Finances and Equipment assured that State cofinancing for the introduction of the vaccine in 2013 will be provided and that the budget line allocated to immunisation had increased by 3% in relation to 2012. Assess the cost of installing the two State budget cold rooms and take all necessary measures so that this installation occurs before the end of 2012..

10. Attachments.

10.1. List of documents attached to this proposal.

Document Number; Document; Section; Mandatory; File. SignaturesMS_MINFI.pdf. 1; MoH Signature (or delegated authority) of Proposal; File desc:. Date/time: 8/18/2012 1:52:58 PM. Size: 933727. SignaturesMS_MINFI.pdf. 2; MoF Signature (or delegated authority) of Proposal; File desc:. Date/time: 8/18/2012 1:54:01 PM. Size: 933727. SignaturesCCIA.pdf. 3; Signatures of ICC or HSCC or equivalent in Proposal; File desc:. Date/time: 8/18/2012 1:56:06 PM. Size: 1028412. CR_CCIA.zip. 4; Minutes of ICC/HSCC meeting endorsing Proposal; File desc:. Date/time: 8/18/2012 1:58:53 PM. Size: 1935195. PPAC 2012-2016_VF.pdf. 5; comprehensive Multi Year Plan - cMYP; File desc:. Date/time: 8/18/2012 2:14:24 PM. Size: 3670104. cMYP_Costing_Tool_Vs.2.5_FR 27_06_ 2012_Mali.pdf. 6; cMYP Costing tool for financial analysis; File desc:. Date/time: 8/18/2012 2:18:25 PM. Size: 20241. Plan introduction rotavirus Mali 23_07_12-2.pdf. 7; Plan for NVS introduction (if not part of cMYP); 5.1; File desc:. Date/time: 8/18/2012 2:16:12 PM. Size: 740961. Plan améliorationGEV.zip. 8; Improvement plan based on EVM; File desc: Rapport GEV& Niveau d’exécution du plan d'amélioration de la GE& Plan de réhabilitation de la logistique PEV& Epi_Log_forcasting_Tool_2012_Mali. Date/time: 8/18/2012 7:22:47 PM. Size: 3627503.

11. Annexes... Annex 1 - NVS Routine Support

Annex 1.1 - NVS Routine Support (Rotavirus, 3 -dose schedule). Table Annex 1.1 A: Rounded up portion of supply that is procured by the country and estimate of relative costs in US$.. 2013; 2014; 2015; 2016. Number of vaccine doses; #; 21,600; 55,300; 140,800; 137,200. Number of AD syringes; #; 0; 0; 0; 0. Number of re-constitution syringes; #; 0; 0; 0; 0. Number of safety boxes; #; 0; 0; 0; 0. Total value to be co-financed by country; $; 79,500; 203,000; 517,500; 504,500... Table Annex 1.1 B: Rounded up portion of supply that is procured by GAVI and estimate of relative costs in US$.. 2013; 2014; 2015; 2016. Number of vaccine doses; #; 374,400; 959,300; 2,444,800; 2,383,300. Number of AD syringes; #; 0; 0; 0; 0. Number of re-constitution syringes; #; 0; 0; 0; 0. Number of safety boxes; #; 4,400; 11,275; 25,575; 25,350. Total value to be co-financed by country; $; 1,376,000; 3,525,500; 8,985,000; 8,758,500....

Table Annex 1.1 C: Summary table for vaccine Rotavirus, 3 -dose schedule. ID. Data from; 2013; 2014; 2015; 2016. Number of surviving infants; Table 5.2; #; 670,250; 694,379; 719,377; 745,274. Number of children to be vaccinated with the first dose; Table 5.2; #; 100,537; 277,752; 712,183; 782,538. Number of children to be vaccinated with the third dose; Table 5.2; #; 100,537; 277,752; 640,245; 708,010. Immunisation coverage with the third dose; Table 5.2; %; 15.00 %; 40.00 %; 89.00 %; 95.00 %. Number of doses per child; Parameter; #; 3; 3; 3; 3. Estimated vaccine wastage factor; Table 5.2; #; 1.05; 1.05; 1.05; 1.05. Number of doses per vial; Parameter; #; 1; 1; 1; 1. AD syringes required; Parameter; #; No; No; No; No. Reconstitution syringes required; Parameter; #; No; No; No; No. Safety boxes required; Parameter; #; No; No; No; No. g; Vaccine price per dose; Table Annexes 4A; $; 3.5; 3.5; 3.5; 3.5. cc; Country co-financing per dose; Table 6.4.1; $; 0.2; 0.2; 0.2; 0.2. ca; AD syringe price per unit; Table Annexes 4A; $; 0.0465; 0.0465; 0.0465; 0.0465. cr; Reconstitution syringe price per unit; Table Annexes 4A; $; 0; 0; 0; 0. cs; Safety box price per unit; Table Annexes 4A; $; 0.0058; 0.0058; 0.0058; 0.0058. fv; Freight cost as % of vaccines value; Table Annexes 4B; %; 5.00 %; 5.00 %; 5.00 %; 5.00 %. fd; Freight cost as % of devices value; Parameter; %; 10.00 %; 10.00 %; 10.00 %; 10.00 %....

Table Annex 1.1 D: Estimated numbers for Rotavirus, 3 -dose schedule, associated injection safety material and related co-financing budget (page 1). Formula; 2013. Total; Government; GAVI. A; Country co-finance; 5.44 %. B; Number of children to be vaccinated with the first dose; Table 1; 100,537; 5,472; 95,065. C; Number of doses per child; Vaccine parameter (schedule); 3.00. D; Number of doses needed; B x C; 301,611; 16,415; 285,196. E; Estimated vaccine wastage factor; Wastage factor table; 1.05. F; Number of doses needed including wastage; D x E; 316,692; 17,235; 299,457. G; Vaccines buffer stock; (F – F of previous year) * 0.25; 79,173; 4,309; 74,864. I; Total vaccine doses needed; F + G; 395,865; 21,544; 374,321. J; Number of doses per vial; Vaccine parameter; 1.00. K; Number of AD syringes (+ 10% wastage) needed; (D + G) x 1.11; 0; 0; 0. L; Reconstitution syringes (+ 10% wastage) needed; I / J * 1.11; 0; 0; 0. M; Total of safety boxes (+ 10% of extra need) needed; (K + L) /100 * 1.11; 4,395; 0; 4,395. N; Cost of vaccines needed; I x g; 1,385,528; 75,403; 1,310,125. O; Cost of AD syringes needed; K x ca; 0; 0; 0. P; Cost of reconstitution syringes needed; L x cr; 0; 0; 0. Q; Cost of safety boxes needed; M x cs; 0.00; 0; 0. R; Freight cost for vaccines needed; N x fv; 69,277; 3,771; 65,506. S; Freight cost for devices needed; (O+P+Q) x fd; 0; 0; 0. T; Total fund needed; (N+O+P+Q+R+S); 1,454,805; 79,173; 1,375,632. U; Total country co-financing; I 3 cc; 79,173. V; Country co-financing % of GAVI supported proportion; U / T; 5.44 %... Table Annex 1.1 D: Estimated numbers for Rotavirus, 3 -dose schedule, associated injection safety material and related co-financing budget (page 2). Formula; 2014. Total; Government; GAVI. A; Country co-finance; 5.44 %. B; Number of children to be vaccinated with the first dose; Table 1; 277,752; 15,116; 262,636. C; Number of doses per child; Vaccine parameter (schedule); 3.00. D; Number of doses needed; B x C; 833,256; 45,348; 787,908. E; Estimated vaccine wastage factor; Wastage factor table; 1.05. F; Number of doses needed including wastage; D x E; 874,919; 47,615; 827,304. G; Vaccines buffer stock; (F – F of previous year) * 0.25; 139,557; 7,595; 131,962. I; Total vaccine doses needed; F + G; 1,014,476; 55,210; 959,266. J; Number of doses per vial; Vaccine parameter; 1.00. K; Number of AD syringes (+ 10% wastage) needed; (D + G) x 1.11; 0; 0; 0. L; Reconstitution syringes (+ 10% wastage) needed; I / J * 1.11; 0; 0; 0. M; Total of safety boxes (+ 10% of extra need) needed; (K + L) /100 * 1.11; 11,261; 0; 11,261. N; Cost of vaccines needed; I x g; 3,550,666; 193,235; 3,357,431. O; Cost of AD syringes needed; K x ca; 0; 0; 0. P; Cost of reconstitution syringes needed; L x cr; 0; 0; 0. Q; Cost of safety boxes needed; M x cs; 0.00; 0; 0. R; Freight cost for vaccines needed; N x fv; 177,534; 9,662; 167,872. S; Freight cost for devices needed; (O+P+Q) x fd; 0; 0; 0. T; Total fund needed; (N+O+P+Q+R+S); 3,728,200; 202,896; 3,525,304. U; Total country co-financing; I 3 cc; 202,896. V; Country co-financing % of GAVI supported proportion; U / T; 5.44 %... Table Annex 1.1 D: Estimated numbers for Rotavirus, 3 -dose schedule, associated injection safety material and related co-financing budget (page 3). Formula; 2015. Total; Government; GAVI. A; Country co-finance; 5.44 %. B; Number of children to be vaccinated with the first dose; Table 1; 712,183; 38,759; 673,424. C; Number of doses per child; Vaccine parameter (schedule); 3.00. D; Number of doses needed; B x C; 2,136,549; 116,275; 2,020,274. E; Estimated vaccine wastage factor; Wastage factor table; 1.05. F; Number of doses needed including wastage; D x E; 2,243,377; 122,089; 2,121,288. G; Vaccines buffer stock; (F – F of previous year) * 0.25; 342,115; 18,619; 323,496. I; Total vaccine doses needed; F + G; 2,585,492; 140,708; 2,444,784. J; Number of doses per vial; Vaccine parameter; 1.00. K; Number of AD syringes (+ 10% wastage) needed; (D + G) x 1.11; 0; 0; 0. L; Reconstitution syringes (+ 10% wastage) needed; I / J * 1.11; 0; 0; 0. M; Total of safety boxes (+ 10% of extra need) needed; (K + L) /100 * 1.11; 25,555; 0; 25,555. N; Cost of vaccines needed; I x g; 9,049,222; 492,476; 8,556,746. O; Cost of AD syringes needed; K x ca; 0; 0; 0. P; Cost of reconstitution syringes needed; L x cr; 0; 0; 0. Q; Cost of safety boxes needed; M x cs; 0.00; 0; 0. R; Freight cost for vaccines needed; N x fv; 452,462; 24,624; 427,838. S; Freight cost for devices needed; (O+P+Q) x fd; 0; 0; 0. T; Total fund needed; (N+O+P+Q+R+S); 9,501,684; 517,099; 8,984,585. U; Total country co-financing; I 3 cc; 517,099. V; Country co-financing % of GAVI supported proportion; U / T; 5.44 %... Table Annex 1.1 D: Estimated numbers for Rotavirus, 3 -dose schedule, associated injection safety material and related co-financing budget (page 4). Formula; 2016. Total; Government; GAVI. A; Country co-finance; 5.44 %. B; Number of children to be vaccinated with the first dose; Table 1; 782,538; 42,588; 739,950. C; Number of doses per child; Vaccine parameter (schedule); 3.00. D; Number of doses needed; B x C; 2,347,614; 127,762; 2,219,852. E; Estimated vaccine wastage factor; Wastage factor table; 1.05. F; Number of doses needed including wastage; D x E; 2,464,995; 134,150; 2,330,845. G; Vaccines buffer stock; (F – F of previous year) * 0.25; 55,405; 3,016; 52,389. I; Total vaccine doses needed; F + G; 2,520,400; 137,165; 2,383,235. J; Number of doses per vial; Vaccine parameter; 1.00. K; Number of AD syringes (+ 10% wastage) needed; (D + G) x 1.11; 0; 0; 0. L; Reconstitution syringes (+ 10% wastage) needed; I / J * 1.11; 0; 0; 0. M; Total of safety boxes (+ 10% of extra need) needed; (K + L) /100 * 1.11; 25,348; 0; 25,348. N; Cost of vaccines needed; I x g; 8,821,400; 480,077; 8,341,323. O; Cost of AD syringes needed; K x ca; 0; 0; 0. P; Cost of reconstitution syringes needed; L x cr; 0; 0; 0. Q; Cost of safety boxes needed; M x cs; 0.00; 0; 0. R; Freight cost for vaccines needed; N x fv; 441,070; 24,004; 417,066. S; Freight cost for devices needed; (O+P+Q) x fd; 0; 0; 0. T; Total fund needed; (N+O+P+Q+R+S); 9,262,470; 504,080; 8,758,390. U; Total country co-financing; I 3 cc; 504,080. V; Country co-financing % of GAVI supported proportion; U / T; 5.44 %......

Annex 2 - NVS Routine – Preferred Second Presentation... Annex 2.1 - NVS Routine Support (Rotavirus, 2 -dose schedule). Table Annex 2.1 A: Rounded up portion of supply that is procured by the country and estimate of relative costs in US$.. 2013; 2014; 2015; 2016. Number of vaccine doses; #; 21,600; 55,300; 140,800; 137,200. Number of AD syringes; #; 0; 0; 0; 0. Number of re-constitution syringes; #; 0; 0; 0; 0. Number of safety boxes; #; 0; 0; 0; 0. Total value to be co-financed by country; $; 79,500; 203,000; 517,500; 504,500...

Table Annex 2.1 B: Rounded up portion of supply that is procured by GAVI and estimate of relative costs in US$... 2013; 2014; 2015; 2016. Number of vaccine doses; #; 374,400; 959,300; 2,444,800; 2,383,300. Number of AD syringes; #; 0; 0; 0; 0. Number of re-constitution syringes; #; 0; 0; 0; 0. Number of safety boxes; #; 4,400; 11,275; 25,575; 25,350. Total value to be co-financed by country; $; 1,376,000; 3,525,500; 8,985,000; 8,758,500....

Table Annex 2.1 C: Summary table for vaccine Rotavirus, 2 -dose schedule. ID; Data from; 2013; 2014; 2015; 2016. Number of surviving infants; Table 5.2; #; 670,250; 694,379; 719,377; 745,274. Number of children to be vaccinated with the first dose; Table 5.2; #; 100,537; 277,752; 712,183; 782,538. Number of children to be vaccinated with the second dose; Table 5.2; #; 100,537; 277,752; 640,245; 708,010. Immunisation coverage with the second dose; Table 5.2; %; 15.00 %; 40.00 %; 89.00 %; 95.00 %. Number of doses per child; Parameter; #; 2; 2; 2; 2. Estimated vaccine wastage factor; Table 5.2; #; 1; 1; 1; 1. Number of doses per vial; Parameter; #; 1; 1; 1; 1. AD syringes required; Parameter; #; No; No; No; No. Reconstitution syringes required; Parameter; #; No; No; No; No. Safety boxes required; Parameter; #; No; No; No; No. g; Vaccine price per dose; Table Annexes 4A; $; 2.55; 2.55; 2.55; 2.55. cc; Country co-financing per dose; Table 6.4.1; $; 0.2; 0.2; 0.2; 0.2. ca; AD syringe price per unit; Table Annexes 4A; $; 0.0465; 0.0465; 0.0465; 0.0465. cr; Reconstitution syringe price per unit; Table Annexes 4A; $; 0; 0; 0; 0. cs; Safety box price per unit; Table Annexes 4A; $; 0.0058; 0.0058; 0.0058; 0.0058. fv; Freight cost as % of vaccines value; Table Annexes 4B; %; 5.00 %; 5.00 %; 5.00 %; 5.00 %. fd; Freight cost as % of devices value; Parameter; %; 10.00 %; 10.00 %; 10.00 %; 10.00 %....

Table Annex 2.1 D: Estimated numbers for Rotavirus, 2 -dose schedule, associated injection safety material and related co-financing budget (page 1). Formula; 2013. Total; Government; GAVI. A; Country co-finance; 5.44 %. B; Number of children to be vaccinated with the first dose; Table 1; 100,537; 5,472; 95,065. C; Number of doses per child; Vaccine parameter (schedule); 3.00. D; Number of doses needed; B x C; 301,611; 16,415; 285,196. E; Estimated vaccine wastage factor; Wastage factor table; 1.05. F; Number of doses needed including wastage; D x E; 316,692; 17,235; 299,457. G; Vaccines buffer stock; (F – F of previous year) * 0.25; 79,173; 4,309; 74,864. I; Total vaccine doses needed; F + G; 395,865; 21,544; 374,321. J; Number of doses per vial; Vaccine parameter; 1.00. K; Number of AD syringes (+ 10% wastage) needed; (D + G) x 1.11; 0; 0; 0. L; Reconstitution syringes (+ 10% wastage) needed; I / J * 1.11; 0; 0; 0. M; Total of safety boxes (+ 10% of extra need) needed; (K + L) /100 * 1.11; 4,395; 0; 4,395. N; Cost of vaccines needed; I x g; 1,385,528; 75,403; 1,310,125. O; Cost of AD syringes needed; K x ca; 0; 0; 0. P; Cost of reconstitution syringes needed; L x cr; 0; 0; 0. Q; Cost of safety boxes needed; M x cs; 0.00; 0; 0. R; Freight cost for vaccines needed; N x fv; 69,277; 3,771; 65,506. S; Freight cost for devices needed; (O+P+Q) x fd; 0; 0; 0. T; Total fund needed; (N+O+P+Q+R+S); 1,454,805; 79,173; 1,375,632. U; Total country co-financing; I 3 cc; 79,173. V; Country co-financing % of GAVI supported proportion; U / T; 5.44 %... Table Annex 2.1 D: Estimated numbers for Rotavirus, 2 -dose schedule, associated injection safety material and related co-financing budget (page 2). Formula; 2014. Total; Government; GAVI. A; Country co-finance; 5.44 %. B; Number of children to be vaccinated with the first dose; Table 1; 277,752; 15,116; 262,636. C; Number of doses per child; Vaccine parameter (schedule); 3.00. D; Number of doses needed; B x C; 833,256; 45,348; 787,908. E; Estimated vaccine wastage factor; Wastage factor table; 1.05. F; Number of doses needed including wastage; D x E; 874,919; 47,615; 827,304. G; Vaccines buffer stock; (F – F of previous year) * 0.25; 139,557; 7,595; 131,962. I; Total vaccine doses needed; F + G; 1,014,476; 55,210; 959,266. J; Number of doses per vial; Vaccine parameter; 1.00. K; Number of AD syringes (+ 10% wastage) needed; (D + G) x 1.11; 0; 0; 0. L; Reconstitution syringes (+ 10% wastage) needed; I / J * 1.11; 0; 0; 0. M; Total of safety boxes (+ 10% of extra need) needed; (K + L) /100 * 1.11; 11,261; 0; 11,261. N; Cost of vaccines needed; I x g; 3,550,666; 193,235; 3,357,431. O; Cost of AD syringes needed; K x ca; 0; 0; 0. P; Cost of reconstitution syringes needed; L x cr; 0; 0; 0. Q; Cost of safety boxes needed; M x cs; 0.00; 0; 0. R; Freight cost for vaccines needed; N x fv; 177,534; 9,662; 167,872. S; Freight cost for devices needed; (O+P+Q) x fd; 0; 0; 0. T; Total fund needed; (N+O+P+Q+R+S); 3,728,200; 202,896; 3,525,304. U; Total country co-financing; I 3 cc; 202,896. V; Country co-financing % of GAVI supported proportion; U / T; 5.44 %... Table Annex 2.1 D: Estimated numbers for Rotavirus, 2 -dose schedule, associated injection safety material and related co-financing budget (page 3). Formula; 2015. Total; Government; GAVI. A; Country co-finance; 5.44 %. B; Number of children to be vaccinated with the first dose; Table 1; 712,183; 38,759; 673,424. C; Number of doses per child; Vaccine parameter (schedule); 3.00. D; Number of doses needed; B x C; 2,136,549; 116,275; 2,020,274. E; Estimated vaccine wastage factor; Wastage factor table; 1.05. F; Number of doses needed including wastage; D x E; 2,243,377; 122,089; 2,121,288. G; Vaccines buffer stock; (F – F of previous year) * 0.25; 342,115; 18,619; 323,496. I; Total vaccine doses needed; F + G; 2,585,492; 140,708; 2,444,784. J; Number of doses per vial; Vaccine parameter; 1.00. K; Number of AD syringes (+ 10% wastage) needed; (D + G) x 1.11; 0; 0; 0. L; Reconstitution syringes (+ 10% wastage) needed; I / J * 1.11; 0; 0; 0. M; Total of safety boxes (+ 10% of extra need) needed; (K + L) /100 * 1.11; 25,555; 0; 25,555. N; Cost of vaccines needed; I x g; 9,049,222; 492,476; 8,556,746. O; Cost of AD syringes needed; K x ca; 0; 0; 0. P; Cost of reconstitution syringes needed; L x cr; 0; 0; 0. Q; Cost of safety boxes needed; M x cs; 0.00; 0; 0. R; Freight cost for vaccines needed; N x fv; 452,462; 24,624; 427,838. S; Freight cost for devices needed; (O+P+Q) x fd; 0; 0; 0. T; Total fund needed; (N+O+P+Q+R+S); 9,501,684; 517,099; 8,984,585. U; Total country co-financing; I 3 cc; 517,099. V; Country co-financing % of GAVI supported proportion; U / T; 5.44 %... Table Annex 2.1 D: Estimated numbers for Rotavirus, 2 -dose schedule, associated injection safety material and related co-financing budget (page 4). Formula; 2016. Total; Government; GAVI. A; Country co-finance; 5.44 %. B; Number of children to be vaccinated with the first dose; Table 1; 782,538; 42,588; 739,950. C; Number of doses per child; Vaccine parameter (schedule); 3.00. D; Number of doses needed; B x C; 2,347,614; 127,762; 2,219,852. E; Estimated vaccine wastage factor; Wastage factor table; 1.05. F; Number of doses needed including wastage; D x E; 2,464,995; 134,150; 2,330,845. G; Vaccines buffer stock; (F – F of previous year) * 0.25; 55,405; 3,016; 52,389. I; Total vaccine doses needed; F + G; 2,520,400; 137,165; 2,383,235. J; Number of doses per vial; Vaccine parameter; 1.00. K; Number of AD syringes (+ 10% wastage) needed; (D + G) x 1.11; 0; 0; 0. L; Reconstitution syringes (+ 10% wastage) needed; I / J * 1.11; 0; 0; 0. M; Total of safety boxes (+ 10% of extra need) needed; (K + L) /100 * 1.11; 25,348; 0; 25,348. N; Cost of vaccines needed; I x g; 8,821,400; 480,077; 8,341,323. O; Cost of AD syringes needed; K x ca; 0; 0; 0. P; Cost of reconstitution syringes needed; L x cr; 0; 0; 0. Q; Cost of safety boxes needed; M x cs; 0.00; 0; 0. R; Freight cost for vaccines needed; N x fv; 441,070; 24,004; 417,066. S; Freight cost for devices needed; (O+P+Q) x fd; 0; 0; 0. T; Total fund needed; (N+O+P+Q+R+S); 9,262,470; 504,080; 8,758,390. U; Total country co-financing; I 3 cc; 504,080. V; Country co-financing % of GAVI supported proportion; U / T; 5.44 %......

Annex 3 - NVS Preventive campaign(s).

No NVS Prevention Campaign Support this year.

| Annex 4. |
| --- |
| Table Annex 4A: Commodities Cost. |
| Vaccine; Presentation; 2013; 2014; 2015; 2016. DTP-HepB, 10 dose(s) per vial, LIQUID; 10. DTP-HepB-Hib, 1 dose(s) per vial, LIQUID; 1; 2.017; 1.986; 1.933; 1.927. DTP-HepB-Hib, 10 dose(s) per vial, LIQUID; 10; 2.017; 1.986; 1.933; 1.927. DTP-HepB-Hib, 2 dose(s) per vial, LYOPHILISED; 2; 2.017; 1.986; 1.933; 1.927. HPV bivalent, 2 dose(s) per vial, LIQUID; 2; 5.000; 5.000; 5.000; 5.000. HPV quadrivalent, 1 dose(s) per vial, LIQUID; 1; 5.000; 5.000; 5.000; 5.000. Measles, 10 dose(s) per vial, LYOPHILISED; 10; 0.242; 0.242; 0.242; 0.242. Meningogoccal, 10 dose(s) per vial, LIQUID; 10; 0.520; 0.520; 0.520; 0.520. MR, 10 dose(s) per vial, LYOPHILISED; 10; 0.494; 0.494; 0.494; 0.494. Pneumococcal (PCV10), 2 dose(s) per vial, LIQUID; 2; 3.500; 3.500; 3.500; 3.500. Pneumococcal (PCV13), 1 dose(s) per vial, LIQUID; 1; 3.500; 3.500; 3.500; 3.500. Rotavirus, 2-dose schedule; 1; 2.550; 2.550; 2.550; 2.550. Rotavirus, 3-dose schedule; 1; 3.500; 3.500; 3.500; 3.500. Yellow Fever, 10 dose(s) per vial, LYOPHILISED; 10; 0.900; 0.900; 0.900; 0.900. Yellow Fever, 5 dose(s) per vial, LYOPHILISED; 5; 0.900; 0.900; 0.900; 0.900. |
| Note for HPV and MR: These prices are indicative only as GAVI has not procured HPV and MR vaccines for GAVI countries yet. Prices will be finalised through tender processes in Q3. GAVI will only fund HPV vaccines if an acceptable price reduction is secured from the current price indicated. The MR price is based on the current price to UNICEF. |
| Supply; Form; 2013; 2014; 2015; 2016. AD-SYRINGE; SYRINGE; 0.047; 0.047; 0.047; 0.047. RECONSTIT-SYRINGE-PENTAVAL; SYRINGE; 0.047; 0.047; 0.047; 0.047. RECONSTIT-SYRINGE-YF; SYRINGE; 0.004; 0.004; 0.004; 0.004. SAFETY-BOX; SAFETYBOX; 0.006; 0.006; 0.006; 0.006. |
| Note: WAP - weighted average price (to be used for any presentation: For DTP-HepB-Hib, it applies to 1 dose liquid, 2 dose lyophilised and 10 dose liquid. For Yellow Fever, it applies to 5 dose lyophilised and 10 dose lyophilised). |
| Table Annex 4B: Freight cost as percentage of value. |
| Vaccine Antigen; Vaccine Type; No Threshold; 500,000$. <=; >. DTP-HepB; HEPBHIB; 2.00 %. DTP-HepB-Hib; HEPBHIB; 23.80 %; 6.00 %. HPV bivalent; HPV; 3.50 %. HPV quadrivalent; HPV; 3.50 %. Measles; MEASLES; 14.00 %. Meningogoccal; MENINACONJUGATE; 10.20 %. MR; MR; 13.20 %. Pneumococcal (PCV10); PNEUMO; 3.00 %. Pneumococcal (PCV13); PNEUMO; 6.00 %. Rotavirus; ROTA; 5.00 %. Yellow Fever; YF; 7.80 %. |  |
| Table Annex 4C: Low - Minimum country's co-payment per dose of co-financed vaccine.. |
| Vaccine; 2013; 2014; 2015; 2016. Rotavirus, 1 dose(s) per vial, ORAL; 0.132; 0.132; 0.132; 0.132. |
| Table Annex 4D: Wastage rates and factors. |
| Countries are expected to plan for a maximal wastage rate of:. |
| • 50% - for a lyophilised vaccine in 10 or 20-dose vial,. |
| • 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,. |
| • 10% - for a lyophilised/liquid vaccine in 2-dose vial, and. |
| • 5% - for a liquid vaccine in 1-dose vial. |
| Vaccine wastage rate; 5%; 10%; 15%; 20%; 25%; 30%; 35%; 40%; 45%; 50%; 55%; 60%. Equivalent wastage factor; 1.05; 1.11; 1.18; 1.25; 1.33; 1.43; 1.54; 1.67; 1.82; 2; 2.22; 2.5. |
| Vaccine; Vaccine wastage rate; VaccineWastageFactor. |
| Table Annex 4E: Vaccine maximum packed volumes. |
| Vaccine product; Designation; Vaccine formulation; Admin route; No. Of doses in the schedule; Presentation (doses/vial, prefilled); Packed volume vaccine (cm3/dose); Packed volume diluents (cm3/dose). BCG; BCG; lyophilized; ID; 1; 20; 1.2; 0.7. Diphtheria-Tetanus-Pertussis; DTP; liquid; IM; 3; 20; 2.5. Diphtheria-Tetanus-Pertussis; DTP; liquid; IM; 3; 10; 3. Diphtheria-Tetanus; DT; liquid; IM; 3; 10; 3. Tetanus-Diphtheria; Td; liquid; IM; 2; 10; 3. Tetanus Toxoid; TT; liquid; IM; 2; 10; 3. Tetanus Toxoid; TT; liquid; IM; 2; 20; 2.5. Tetanus Toxoid UniJect; TT; liquid; IM; 2; Uniject; 12. Measles; Measles; lyophilized; SC; 1; 1; 26.1; 20. Measles; Measles; lyophilized; SC; 1; 2; 13.1; 13.1. Measles; Measles; lyophilized; SC; 1; 5; 5.2; 7. Measles; Measles; lyophilized; SC; 1; 10; 3.5; 4. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 1; 26.1; 26.1. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 2; 13.1; 13.1. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 5; 5.2; 7. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 10; 2.5; 4. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 1; 26.1; 26.1. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 2; 13.1; 13.1. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 5; 5.2; 7. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 10; 3; 4. Polio; OPV; liquid; Oral; 4; 10; 2. Polio; OPV; liquid; Oral; 4; 20; 1. Yellow fever; YF; lyophilized; SC; 1; 5; 6.5; 7. Yellow fever; YF; lyophilized; SC; 1; 10; 2.5; 3. Yellow fever; YF; lyophilized; SC; 1; 20; 1.5; 2. Yellow fever; YF; lyophilized; SC; 1; 50; 0.7; 1. DTP-HepB combined; DTP-HepB; liquid; IM; 3; 1; 9.7. DTP-HepB combined; DTP-HepB; liquid; IM; 3; 2; 6. DTP-HepB combined; DTP-HepB; liquid; IM; 3; 10; 3. Hepatitis B; HepB; liquid; IM; 3; 1; 18. Hepatitis B; HepB; liquid; IM; 3; 2; 13. Hepatitis B; HepB; liquid; IM; 3; 6; 4.5. Hepatitis B; HepB; liquid; IM; 3; 10; 4. Hepatitis B UniJect; HepB; liquid; IM; 3; Uniject; 12. Hib liquid; Hib_liq; liquid; IM; 3; 1; 15. Hib liquid; Hib_liq; liquid; IM; 3; 10; 2.5. Hib freeze-dried; Hib_lyo; lyophilized; IM; 3; 1; 13; 35. Hib freeze-dried; Hib_lyo; lyophilized; IM; 3; 2; 6. Hib freeze-dried; Hib_lyo; lyophilized; IM; 3; 10; 2.5; 3. DTP liquid + Hib freeze-dried; DTP+Hib; liquid+lyop.; IM; 3; 1; 45. DTP-Hib combined liquid; DTP+Hib; liquid+lyop.; IM; 3; 10; 12. DTP-Hib combined liquid; DTP-Hib; liquid; IM; 3; 1; 32.3. DTP-HepB liquid + Hib freeze-dried; DTP-Hib; liquid; IM; 3; 10; 2.5. DTP-HepB liquid + Hib freeze-dried; DTP-HepB+Hib; liquid+lyop.; IM; 3; 1; 22. DTP-HepB-Hib liquid; DTP-HepB+Hib; liquid+lyop.; IM; 3; 2; 11. DTP-HepB-Hib liquid; DTP-HepB-Hib; liquid; IM; 3; 10; 4.4. DTP-HepB-Hib liquid; DTP-HepB-Hib; liquid; IM; 3; 2; 13.1. DTP-HepB-Hib liquid; DTP-HepB-Hib; liquid; IM; 3; 1; 19.2. Meningitis A/C; MV_A/C; lyophilized; SC; 1; 10; 2.5; 4. Meningitis A/C; MV_A/C; lyophilized; SC; 1; 50; 1.5; 3. Meningococcal A/C/W/; MV_A/C/W; lyophilized; SC; 1; 50; 1.5; 3. Meningococcal A/C/W/Y; MV_A/C/W/Y; lyophilized; SC; 1; 10; 2.5; 4. Meningitis W135; MV_W135; lyophilized; SC; 1; 10; 2.5; 4. Meningitis A conjugate; Men_A; lyophilized; SC; 2; 10; 2.6; 4. Japanese Encephalitis; JE_lyo; lyophilized; SC; 3; 10; 15. Japanese Encephalitis; JE_lyo; lyophilized; SC; 3; 10; 8.1; 8.1. Japanese Encephalitis; JE_lyo; lyophilized; SC; 3; 5; 2.5; 2.9. Japanese Encephalitis; JE_lyo; lyophilized; SC; 3; 1; 12.6; 11.5. Japanese Encephalitis; JE_liq; liquid; SC; 3; 10; 3.4. Rota vaccine; Rota_lyo; lyophilized; Oral; 2; 1; 156. Rota vaccine; Rota_liq; liquid; Oral; 2; 1; 17.1. Rota vaccine; Rota_liq; liquid; Oral; 3; 1; 45.9. Pneumo. conjugate vaccine 7-valent; PCV-7; liquid; IM; 3; PFS; 55.9. Pneumo. conjugate vaccine 7-valent; PCV-7; liquid; IM; 3; 1; 21. Pneumo. conjugate vaccine 10-valent; PCV-10; liquid; IM; 3; 1; 11.5. Pneumo. conjugate vaccine 10-valent; PCV-10; liquid; IM; 3; 2; 4.8. Pneumo. conjugate vaccine 13-valent; PCV-13; liquid; IM; 3; 1; 12. Polio inactivated; IPV; liquid; IM; 3; PFS; 107.4. Polio inactivated; IPV; liquid; IM; 3; 10; 2.5. Polio inactivated; IPV; liquid; IM; 3; 1; 15.7. Human Papilomavirus vaccine; HPV; liquid; IM; 3; 1; 15. Human Papilomavirus vaccine; HPV; liquid; IM; 3; 2; 5.7. Monovalent OPV-1; mOPV1; liquid; Oral; 20; 1.5. Monovalent OPV-3; mOPV3; liquid; Oral; 20; 1.5. |

| 12. Banking Form |
| --- |
| In accordance with the decision on financial support made by the GAVI Alliance, the Government of Mali hereby requests that a payment be made via electronic bank transfer as detailed below:. Name of Institution (Account Holder):. Address:. City Country:. Telephone no.:; Fax no.:. Currency of the bank account:. For credit to:. Bank account's title:. Bank account no.:. Bank's name:. |
| Is the bank account exclusively to be used by this program?. |
| By who is the account audited?. |
| Signature of Government's authorizing official. |
| Seal. Name:. Title:. Signature:. Date:. |
| FINANCIAL INSTITUTION. Bank Name:. Branch Name:. Address:. City Country:. Swift Code:. Sort Code:. ABA No.:. Telephone No.:. FAX No.:. | CORRESPONDENT BANK. (In the United States). |
| I certify that the account No is held by at this banking institution. The account is to be signed jointly by at least (number of signatories) of the following authorized signatories:. 1; Name:. Title:. 2; Name:. Title:. 3; Name:. Title:. |
| Name of bank's authorizing official. Signature:. Date:. Seal:. |