|  |  |  |  |  | [V2.7]. |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| GAVI Alliance. |  |  |  |  |  |  |  |
| Application Form for Country Proposals. |  |  |  |  |  |  |  |
| For Support to:. |  |  |  |  |  |  |  |
| Preventive Campaign Support. |  |  |  |  |  |  |  |
| Submitted by. |  |  |  |  |  |  |  |
| The Government of. |  |  |  |  |  |  |  |
| Nigeria. |  |  |  |  |  |  |  |
| Date of submission: 9/2/2012 6. |  |  |  |  |  |  |  |
| Deadline for submission: 8/31/2012. |  |  |  |  |  |  |  |
| Select Start and End Year of your Comprehensive Multi-Year Plan (cMYP). |  |  |  |  |  |  |  |
| Start Year. | 2011. |  |  |  |  |  |  |
|  |  |  | End Year. | 2015. |  |  |  |
| Form revised in 2012. |  |  |  |  |  |  |  |
| (To be used with Guidelines of September 2012). |  |  |  |  |  |  |  |
| Please submit the Proposal using the online platform. https://AppsPortal.gavialliance.org/PDExtranet. |  |  |  |  |  |  |  |
| Enquiries to: proposals@gavialliance.org or representatives of a GAVI partner agency. The documents can be shared with GAVI partners, collaborators and general public. The Proposal and attachments must be submitted in English, French, Spanish, or Russian.. Note: Please ensure that the application has been received by the GAVI Secretariat on or before the day of the deadline.. The GAVI Secretariat is unable to return submitted documents and attachments to countries. Unless otherwise specified, documents will be shared with the GAVI Alliance partners and the general public.. |  |  |  |  |  |  |  |

GAVI ALLIANCE GRANT TERMS AND CONDITIONS. FUNDING USED SOLELY FOR APPROVED PROGRAMMES. The applicant country ("Country") confirms that all funding provided by the GAVI Alliance will be used and applied for the sole purpose of fulfilling the programme(s) described in the Country's application. Any significant change from the approved programme(s) must be reviewed and approved in advance by the GAVI Alliance. All funding decisions for the application are made at the discretion of the GAVI Alliance Board and are subject to IRC processes and the availability of funds.. AMENDMENT TO THE APPLICATION. The Country will notify the GAVI Alliance in its Annual Progress Report if it wishes to propose any change to the programme(s) description in its application.The GAVI Alliance will document any change approved by the GAVI Alliance, and the Country's application will be amended.. RETURN OF FUNDS. The Country agrees to reimburse to the GAVI Alliance all funding amounts that are not used for the programme(s) described in its application. The country's reimbursement must be in US dollars and be provided, unless otherwise decided by the GAVI Alliance, within sixty (60) days after the Country receives the GAVI Alliance's request for a reimbursement and be paid to the account or accounts as directed by the GAVI Alliance.. SUSPENSION/ TERMINATION. The GAVI Alliance may suspend all or part of its funding to the Country if it has reason to suspect that funds have been used for purpose other than for the programmes described in the Country's application, or any GAVI Alliance-approved amendment to the application.The GAVI Alliance retains the right to terminate its support to the Country for the programmes described in its application if a misuse of GAVI Alliance funds is confirmed.. ANTICORRUPTION. The Country confirms that funds provided by the GAVI Alliance shall not be offered by the Country to any third person, nor will the Country seek in connection with its application any gift, payment or benefit directly or indirectly that could be construed as an illegal or corrupt practice.. AUDITS AND RECORDS. The Country will conduct annual financial audits, and share these with the GAVI Alliance, as requested. The GAVI Alliance reserves the right, on its own or through an agent, to perform audits or other financial management assessment to ensure the accountability of funds disbursed to the Country.. The Country will maintain accurate accounting records documenting how GAVI Alliance funds are used. The Country will maintain its accounting records in accordance with its government-approved accounting standards for at least three years after the date of last disbursement of GAVI Alliance funds. If there is any claims of misuse of funds, Country will maintain such records until the audit findings are final. The Country agrees not to assert any documentary privilege against the GAVI Alliance in connection with any audit.. CONFIRMATION OF LEGAL VALIDITY. The Country and the signatories for the Country confirm that its application, and Annual Progress Report, are accurate and correct and form legally binding obligations on the Country, under the Country's law, to perform the programmes described in its application, as amended, if applicable, in the APR.. CONFIRMATION OF COMPLIANCE WITH THE GAVI ALLIANCE TRANSPARANCY AND ACCOUNTABILITY POLICY. The Country confirms that it is familiar with the GAVI Alliance Transparency and Accountability Policy (TAP) and complies with the requirements therein.. USE OF COMMERCIAL BANK ACCOUNTS. The Country is responsible for undertaking the necessary due diligence on all commercial banks used to manage GAVI cash-based support. The Country confirms that it will take all responsibility for replenishing GAVI cash support lost due to bank insolvency, fraud or any other unforeseen event.. ARBITRATION. Any dispute between the Country and the GAVI Alliance arising out of or relating to its application that is not settled amicably within a reasonable period of time, will be submitted to arbitration at the request of either the GAVI Alliance or the Country. The arbitration will be conducted in accordance with the then-current UNCITRAL Arbitration Rules. The parties agree to be bound by the arbitration award, as the final adjudication of any such dispute. The place of arbitration will be Geneva, Switzerland. . The languages of the arbitration will be English or French.. For any dispute for which the amount at issue is US$ 100,000 or less, there will be one arbitrator appointed by the GAVI Alliance. For any dispute for which the amount at issue is greater than US $100,000 there will be three arbitrators appointed as follows: The GAVI Alliance and the Country will each appoint one arbitrator, and the two arbitrators so appointed will jointly appoint a third arbitrator who shall be the chairperson.. The GAVI Alliance will not be liable to the country for any claim or loss relating to the programmes described in the application, including without limitation, any financial loss, reliance claims, any harm to property, or personal injury or death. Country is solely responsible for all aspects of managing and implementing the programmes described in its application..

1. Application Specification Please specify for which type of GAVI support you would like to apply to..

Type of Support; Vaccine; Start Year; End Year; Preferred second presentation[1]. Preventive Campaign Support; Yellow Fever, 10 dose(s) per vial, LYOPHILISED; 2013; 2015.

[1] This "Preferred second presentation" will be used in case there is no supply available for the preferred presentation of the selected vaccine ("Vaccine" column). If left blank, it will be assumed that the country will prefer waiting until the selected vaccine becomes available..

2. Table of Contents.

1. Application Specification. 2. Table of Contents. 3. Executive Summary. 4. Signatures. 4.1. Signatures of the Government and National Coordinating Bodies. 4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation. 4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation. 4.1.3. The Inter-Agency Coordinating Committee for Immunisation. 4.2. National Immunization Technical Advisory Group for Immunisation. 4.2.1. The NITAG Group for Immunisation. 5. Immunisation Programme Data. 5.1. Basic facts. 5.2. Baseline and Annual Targets (NVS Routine Support). 5.3. Baseline and Annual Targets for Preventive Campaign(s). 5.3.1 Baseline and annual targets (Yellow Fever campaign). 6. New and Under-Used Vaccines (NVS Routine). 7. NVS Preventive Campains. 7.1. Assessment of burden of relevant diseases related to campaigns (if available). 7.2 Requested for Yellow Fever, 10 dose(s) per vial, LYOPHILISED campaign support. 7.2.1 Summary for Yellow Fever campaign support. 7.2.2 Grant Support for Operational Costs of the Yellow Fever Campaign. 8. Procurement and Management. 8.1. Procurement and Management of New and Under-Used Vaccines Routine. 8.2. Procurement and Management for NVS Preventive Campaign(s). 8.2.1 Procurement and Management for Yellow Fever, 10 dose(s) per vial, LYOPHILISED campaign. 8.3. Vaccine Management (EVSM/EVM/VMA). 9. Additional Comments and Recommendations from the National Coordinating Body (ICC/HSCC). 10. Attachments. 11. Annexes. Annex 1 - NVS Routine Support. Annex 2 - NVS Routine – Preferred Second Presentation. Annex 3 - NVS Preventive campaign(s). Table Annex 3.1 C Summary table for vaccine Yellow Fever, 10 dose(s) per vial, LYOPHILISED. Table Annex 3.1 D Estimated numbers for Yellow Fever, 10 dose(s) per vial, LYOPHILISED, associated injection safety material and related co-financing budget (page 1). Annex 4. Table Annex 4A: Commodities Cost. Table Annex 4B: Freight cost as percentage of value. Table Annex 4C: Intermediate - Minimum country's co-payment per dose of co-financed vaccine.. Table Annex 4D: Wastage rates and factors. Table Annex 4E: Vaccine maximum packed volumes. 12. Banking Form.

3. Executive Summary.

Please provide a summary of your country's proposal, including the following the information:. l; For each specific request, NVS routine support or NVS campaign :. ¡; The duration of support. ¡; The total amount of funds. ¡; Details of the vaccine(s), if applicable. l; Relevant baseline data, including:. ¡; DTP3 and Measles coverage data (as reported on the WHO/UNICEF Joint Reporting Form). ¡; Birth cohort, targets and immunisation coverage by vaccines. l; Country preparedness. ¡; Summary of EVM assessment. l; The nature of stakeholders' participation in developing this proposal. ¡; Inter-Agency Coordinating Committee. Nigeria has a huge population atrisk of Yellow Fever in the African continent. Nigeria is the onlycountry out of the 13 West and Central African high risk countries that has notconducted a national preventive campaign under the Yellow fever Investment case(2007-2011). The risk assessment conducted in 2008, as part of the YFInvestment Case, identified 104 million people in 506 LGAs. Rather than focusing on selected LGAs, thevaccination of an entire State is considered more beneficial, since intra-statedifferences do not reflect a significant difference in terms of risk ofexposure to the disease. Between 1984 and 1991, Nigeriaexperiences a severe outbreak of YF resulting in the report to the WHO of 19,871cases. This has been the highest number of YF cases reported to the WHO sincereporting began in 1960. Therecent emergence of YF activity in neighbouring or nearby countries includingCameroon with outbreaks in 2011 from six districts (Guider, Bibemi, Gaschiga,Lagdo, May Oulo and Golombe) is a call for concern. Moreover, the country has nothad a mass vaccination campaign for the past 30 years and with the low routineYF coverage rates over the same period, Nigeria has accumulated a hugepopulation of people susceptible to YF infection. Nigeria is therefore ripe forthe occurrence, anytime from now, of a major YF outbreak, possibly of a muchhigher severity than previously reported In 2010 WHO/UNICEF estimatedthat only 69% of the 6 million child cohort received routine YF infantvaccines. Mathematical models suggest that if a YF outbreak occurred in alarge, urban city such as Lagos, it could result in 4.5 million cases and128,000 deaths, requiring over millions of YF vaccine doses. An outbreak atthis level would have enormous consequences on the Nigerian economy as well asthe health system. Additionally, there would be a high potential for diseasespread beyond Nigeria's borders. Vaccinating the 104 million atrisk individuals in Nigeria would consume almost the entire available YFvaccine for preventive campaigns for the next eight years. In terms of YFvaccine requirements, the total YF vaccines required to vaccinate 80% of thetarget population between 2013and 2016 is 62,270,749 million doses to vaccinate 59, 158,986 (80% of 73,948,733 million target population). These requirements are spread across the fourphases and vaccinating 80% of the target population as follows: 2013 13.6million; 2014 15.4 million doses; 2015 17.98 million doses and 2016 12.2 milliondoses. Inlight of the constraints in vaccine supply on the international market and inan effort to reduce the epidemic risk in Nigeria, while maintaining flexibilityto free resources for other at-risk countries, the document suggests toprioritize approximately 73.95 million at-risk individuals for preventivecampaigns in Nigeria. This figure represents 73% of the total number of personsindicated as living in higher risk areas (104 million) as per the 2008 riskassessment. Giventhe limitations in vaccine availability, the vaccination would target the population9 months to 45 years. The justification for selecting the 9 months to 45 yearage group were i).by the fact that the older population would be at lower risk of YF infection becausethey have been exposed to and survived previous YF epidemics and/or received YF vaccines duringmass vaccination campaigns between 1985 and 1992. In addition, the majority ofreported YF cases in West Africa is now occurring among <45 years oldpopulation. Due toher size among other issues, the nation on her own does not have the resourcesto contain an outbreak of YF especially when viewed against the backdrop thatwe do not produce the vaccines. The Yellow Fever campaign as envisaged will use up to 62.3million doses of vaccines which cannot be met at once and hence theneed to reach out to GAVI and fit into the GAVI preventive plan that hopes tomake available 66 million doses in aphased manner. For the States that will be covered in the 5th year and after,an alternative financing will be looked for from Government of Nigeria. Thefollowing criteria were used to rank States, as to level of risk for YFvulnerability, with a ranking of 5 for highest level of vulnerability, and 1 thelowest level. The criteria used were selected on priority basis using rankingof 1-5 (corresponding to years 1 to 4 of the plan): i) Vulnerability, ii) Proportion of high risk LGAs in the State iii) State bordering Cameroun, iv) Other competing priorities (like poliocampaigns), v) And any possible impediment to conduct YFcampaign, urban component, routine YF coverage, cold chain capacity, politicalacceptability. Vaccinationcampaigns will be carried out in order of risk ranking with campaigns done inthe first year in the states with the highest risks. With this prioritization,and to ensure ease of operation, neighboring states were grouped together for amaximum utilization of 19 million YF doses per year. The key components of theplanning phase include establishing a national coordinating body andinter-sectoral subcommittees, conducting resource mobilization activities,developing training materials, logistics and data management tools, conductinga KAP study in the respective populations, organizing state, LGA and wardmicro-planning and implementation training, and conducting social mobilizationactivities. With the completion of the coldchain expansion and rehabilitation at the national and zonal levels, Nigeriahas sufficient cold storage capacity for the YF vaccines for all the phases ofthe campaign including the routine immunization system. At the national levelthere is the NSCS and 6 zonal cold stores which provide a combined storagevolume of 373, 750 liters. Yellow Fever vaccines can be stored under-positiveand negative storage volume. However, this analysis concentrates on thepositive storage that will be effectively available to store the vaccine sincethe negative storage will be utilized for freezing ice packs. As part of the program, Nigeriahas established a pharmaco-vigilance system and the surveillance infrastructurefor YF case and laboratory based surveillance will be strengthened. Inaddition, the YF control program will be leveraged to strengthen criticalcomponents of the health system more broadly, including cold chain capacity, wastemanagement serological and entomological survey. Building on the experience withsuccessful MenAfriVac, measles and polio campaigns, and in light of the acutecommunity awareness of YF, demand for YF preventive vaccination is expected tobe high. A post-implementation coverage survey will be conducted within four toeight weeks of the conclusion of the campaign. The estimated cost of thecampaign in 2013 – 2016 is US$ 147,578,481including US$54,662, 908 for operational costs. The Government of Nigeria wouldwelcome GAVI support for the campaign and is committed to raise the resourcesnecessary to fund the remainder of the operational costs. Overall the cost per person vaccinatedin Nigeria will be 1.9 USD. GAVI is expected to provide the vaccines (bundled withsyringes, safety boxes and vaccination cards) as well as 0.65 cents per personfor the operational costs. The remaining costs of $0.312/person willbe supported by the country..

| 4. Signatures. |  |  |
| --- | --- | --- |
| 4.1. Signatures of the Government and National Coordinating Bodies. |  |  |
| 4.1.1. Government and the Inter-Agency Coordinating Committee for Immunisation. |  |  |
| The Government of Nigeria would like to expand the existing partnership with the GAVI Alliance for the improvement of the infants routine immunisation programme of the country, and specifically hereby requests for GAVI support for. |  |  |
|  | Yellow Fever, 10 dose(s) per vial, LYOPHILISED preventive campaigns. |  |
| The Government of Nigeria commits itself to developing national immunisation services on a sustainable basis in accordance with the Comprehensive Multi-Year Plan presented with this document. The Government requests that the GAVI Alliance and its partners contribute financial and technical assistance to support immunisation of children as outlined in this application.. |  |  |
| Table(s) in the NVS Routine section of this application shows the amount of support in either supply or cash that is required from the GAVI Alliance. Table(s) of this application shows the Government financial commitment for the procurement of this new vaccine (NVS support only).. |  |  |
| Following the regulations of the internal budgeting and financing cycles the Government will annually release its portion of the co-financing funds in the month of March.. |  |  |
| The payment for the first year of co-financed support will be around March 2013 for Yellow Fever, 10 dose(s) per vial, LYOPHILISED.. |  |  |
| Please note that this application will not be reviewed or approved by the Independent Review Committee (IRC) without the signatures of both the Minister of Health and Minister of Finance or their delegated authority.. |  |  |
| Minister of Health (or delegated authority); Minister of Finance (or delegated authority). Name; Prof Onyebuchi Christian CHUKWU; Name; Dr Ngozi Okonjo-Iweala. Date; Date. Signature; Signature. |  |  |
| This report has been compiled by (these persons may be contacted in case the GAVI Secretatiat has queries on this document):. |  |  |
| Full name; Position; Telephone; Email. Dr A J OTERI; Deputy Director GAVI Focal Point; +2348026724545; josephoteri@yahoo.co.uk. Dr Nneka ONWU; Deputy Director Head Non Polio SIAs; +2348023024254; nnekaonwu@yahoo.com. |  |  |
| 4.1.2. National Coordinating Body - Inter-Agency Coordinating Committee for Immunisation. |  |  |
| We the members of the ICC, HSCC, or equivalent committee [1] met on the 16/08/2012 to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.. |  |  |
| [1] Inter-agency Coordinating Committee or Health Sector Coordinating Committee, or equivalent committee which has the authority to endorse this application in the country in question.. |  |  |
| The endorsed minutes of this meeting are attached as document number 4.. |  |  |
| Name/Title*; Agency/Organisation*; Signature. Alhaji Abdu Garba; USAID. Dr Ado J G Muhammad, Executive Director; National Primary Health Care Development Agency. Dr Anthony Ayeke, International Aid/Cooperation Officer; EC Delegation. Dr Ben Anyene, National Immunization Policy Advisor; PRRINN-MNCH. Dr David Okello, WHO Representative; WHO. Dr Mansur Kabir, Director Public Health; Federal Ministry of Health. Dr Muhammad Ali-Pate, Hon. Minister of State for Health; Federal Ministry of Health. Dr Owen Wiwa, Country Director; Clinton Health Access Initiative. Dr Yemi-Esan Sade, Director HPR&S; Federal Ministry of Health. Mr Jacques Boyer, Ag Country Representative; UNICEF. Mrs Fatima Bamidele, Permanent Secretary; Federal Ministry of Health. Prof Onyebuchi C Chukwu, Hon. Minister of Health; Federal Ministry of Health. |  |  |
| 4.1.3. The Inter-Agency Coordinating Committee for Immunisation. |  |  |
| Agencies and partners (including development partners and NGOs) supporting immunisation services are co-ordinated and organised through an inter-agency coordinating mechanism (ICC, HSCC, or equivalent committee). The ICC, HSCC, or equivalent committee is responsible for coordinating and guiding the use of the GAVI NVS routine support and/or campaign support. Please provide information about the ICC, HSCC, or equivalent committee in your country in the table below.. |  |  |
| Profile of the ICC, HSCC, or equivalent committee. |  |  |
| Name of the committee; Inter - agency Coordinating Committee for Immunization in Nigeria. Year of constitution of the current committee; 2000. Organisational structure (e.g., sub-committee, stand-alone); Stand alone with subcommittees (CORE group and ICC Finance) with 5 working groups. Frequency of meetings; Quarterly plus additional meetings if necessary. |  |  |
| Composition. |  |  |
| Function; Title / Organisation; Name. Chair; Honourable Minister of Health Fed Ministry of Health; Prof Onyebuchi Christian CHUKWU. Secretary; National Primary Health Care Development Agency; National Primary Health Care Development Agency. Members; Honourable Minister of State for Health Federal Ministry of Health; Dr Muhammad ALI PATE. Permanent Secretary /Federal Ministry of Health; Mrs Fatima BAMIDELE. Director HPR&S/ Federal Ministry of Health; Dr Yemi-ESAN SADE. Director Public Health/ Federal Ministry of Health; Dr Mansur KABIR. Executive Director/ National Primary Health Care Development Agency; Dr Ado J G MUHAMMAD. WHO Representative/ WHO; Dr David OKELLO. Ag Country Representative/ UNICEF; Mr Jacques BOYER. International Aid/Cooperation Officer/ EU Delegation; Dr Anthony AYEKE. Country Director/ Clinton Health Access Initiative; Dr Owen WIWA. USAID; Alhaji Abdu Garba. National Immunization Policy Advisor/ PRRINN-MNCH; Dr Ben Anyene. |  |  |
| Major functions and responsibilities of the ICC/HSCC:. |  |  |
| The ICC provided a forum for regular information sharing and networking amongst the major stakeholders so as to ensure synergy and complementarity of programme implementation. Mobilization of resources for supplemental and Routine Immunisation Review and endorsement of action plans: 5 year comprehensive Multi Year Plan (cMYP) and Annual plans Coodination of Partners efforts in support of Govt. activities. Review of progress reports on Immuinzation in the country.. |  |  |
| Three major strategies to enhance the committee's role and functions in the next 12 months. |  |  |
| 1.; Improved partnership coordination and information sharing. 2.; oint budgeting and resource mobilization. 3.; Facilitating the establishment of functioning ICCs at lower levels (States and LGAs). |  |  |
| 4.2. National Immunization Technical Advisory Group for Immunisation. |  |  |
| (If it has been established in the country). |  |  |
| We the members of the NITAG met on the to review this proposal. At that meeting we endorsed this proposal on the basis of the supporting documentation which is attached.. |  |  |
| The endorsed minutes of this meeting are attached as document number 4.. |  |  |

4.2.1. The NITAG Group for Immunisation.

Profile of the NITAG.

Name of the NITAG. Year of constitution of the current NITAG. Organisational structure (e.g., sub-committee, stand-alone). Frequency of meetings.

Composition.

Function; Title / Organisation; Name. Chair. Secretary. Members; EPI Team Leader WHO; Dr Alex GASASIRA. EPI Team Leader UNICEF; Dr Boubacar DIENG. National Immunization Policy Advisor PRRINN MNNCH; Dr Ben ANYENE. USAID Senior Programme Manager; Alhaji Abdu GARBA. Health Adviser DFID; Dr Ebere ANYACHUKWU.

Major functions and responsibilities of the NITAG.

The CORE Group is the Technical arm of the ICC. It has the following working groups Operations, Logistics, Monitoring & Evaluation, Social mobilization, Training,.

Three major strategies to enhance the NITAG's role and functions in the next 12 months.

1.. 2.. 3..

5. Immunisation Programme Data.

5.1. Basic facts.

Please complete the tables below, using data from available sources. Please identify the source of the data, and the date. Where possible use the most recent data and attach the source document..

▪; Please refer to the Comprehensive Multi-Year Plan for Immunisation (cMYP) (or equivalent plan) and attach a complete copy (with an Executive Summary) as DOCUMENT NUMBER : 6. ▪; Please attach relevant Vaccine Introduction Plans as DOCUMENT NUMBER : 7. ▪; Please refer to the two most recent annual WHO/UNICEF Joint Reporting Forms (JRF) on Vaccine Preventable Diseases. ▪; Please refer to Health Sector Strategy documents, budgetary documents, and other reports, surveys etc, as appropriate..

For the year 2012 (most recent; specify dates of data provided).

Figure; Year; Source. Total population; 169,019,328; 2012; Projection from 2006 National census. Infant mortality rate (per 1000); 75; 2007; 2008 Nigeria Demographic & Health survey(NDHS). Surviving infants[1]; 6,344,760; 2012; Projection from 2006 National census. GNI per capita (US$); 1,190; 2009; World Bank(Atlas method). Total Health Expenditure (THE) as a percentage of GDP; 75; %; 2009; Projection from National Health Account 1995 - 2009. General government expenditure on health (GGHE) as % of General government expenditure; 6; %; 2009; Projection from National Health Account 1995 - 2009.

[1] Surviving infants = Infants surviving the first 12 months of life.

Please provide some additional information on the planning and budgeting context in your country. National Strategic Health Development Plan 2010-2015. Please indicate the name and date of the relevant planning document for health. National planning and budgeting is an Annual planning cycle (January - December). Is the CMYP (or updated Multi-Year Plan) aligned with the document (timing, content, etc.). Yes it is aligned. The 2009 - 2014 cMYP has been updated to 2011 - 2015 to align with the National Strategic Health Development Plan. The content of the immunization section is aligned with the National Health Plan. Please indicate the national planning budgeting cycle for health. The National planning budgeting is annual (Jan - December). Please indicate the national planning cycle for immunisation. Annual planning (January - December ). Please indicate if sex disaggregated data (SDD) is used in immunisation routine reporting systems. It is not used routinely but the National Immunization Coverage Surveys disaggregates by Sex. Please indicate if gender aspects relating to introduction of a new vaccine have been addressed in the introduction plan. No, because gender is not an issue in Immunization in the country. Please describe any recent evidence of socio-economic and/or gender barriers to the immunisation programme through studies or surveys?. Country should provide an outline of all preparatory activities for vaccine(s) introduction. Yellow fever risk assessment conducted in 2008 First Stakeholders meeting 17th March 2011 Technical meeting with IST Mission and Prof Tomori on case base plan Constitution of National Yellow Fever Committee Feb 2012 Cold Chain assessment of implementing State Preparation of the introductory plan Meeting with Directors Primary Health Care of implementing States Sensitization meeting of implementing States Review of status of laboratories.

5.2. Baseline and Annual Targets (NVS Routine Support)

No NVS Routine Support is requested.

| 5.3. Baseline and Annual Targets for Preventive Campaign(s).. |  |
| --- | --- |
| 5.3.1 Baseline and annual targets (Yellow Fever campaign). Cohort for Yellow Fever is population 1-29 years old.. Table 5.3.1 Baseline NVS preventive campaign figures for Yellow Fever.. Number; Base Year; Baseline and Targets; Baseline and Targets; Baseline and Targets. 2011; 2013; 2014; 2015. Total births; 163,884,360; 174,442,422; 180,049,323; 185,847,096. Total population 1-29 years old; 11,464,130; 122,109,695; 126,034,526; 130,092,967. Target population vaccinated with Yellow Fever; 0; 17,022,913; 19,264,088; 22,473,454. Yellow Fever (campaign) coverage (%) [1]; 0.00 %; 13.94 %; 15.28 %; 17.27 %. Wastage rate in base year and thereafter (%) for Yellow Fever (campaign); 5; 5; 5; 5. Wastage factor in base year and thereafter for Yellow Fever; 1.05; 1.05; 1.05; 1.05.. [1] Number of persons vaccinated out of total births... |  |

6. New and Under-Used Vaccines (NVS Routine)

No NVS Routine Support is requested.

7. NVS Preventive Campains

7.1. Assessment of burden of relevant diseases related to campaigns (if available).

Disease; Title of the assessment; Date; Results. Cerobrospinal Meningitis; CSM surveillance in Nigeria; December 2008; Cases: 6835 Deaths: 492 CFR: 7.2 Cumulative A/Rate:6.7 No bacteriology data. Cerobrospinal Meningitis; CSM surveillance in Nigeria; December 2009; Cases: 56,135 Deaths: 2489 CFR: 4.4 Cumulative A/Rate: 52.6. Cerobrospinal Meningitis; Evaluation report of the preparedness and response to the 2009 CSM epidemic in Nigeria; 2010; Bacteriology information indiciated a preponderance of Men A (with 375 positivies) followed by W135 (20 cases). Cerobrospinal Meningitis; CSM surveillance in Nigeria; December 2010; Cases: 4983 Deaths: 337 CFR: 6.8 Cumulative A/Rate: 4.7 NmA: 43 W135:58. Yellow Fever; Yellow Fever Risk Assessment; 2008; 104,000,000 people at risk of Yellow Fever in 506 LGAs.

If Yellow Fever vaccines have already been introduced in your country during campaigns, please give details of the lessons learned from previous introduction(s) specifically for: storage capacity, protection from accidental freezing, staff training, cold chain, logistics, coverage and drop-out rates, wastage rate, etc., and suggest action points to address them..

Lessons Learned; Action Points. High wastage; Capacity building of health workers.

7.2.Requested for Yellow Fever, 10 dose(s) per vial, LYOPHILISED campaign support 7.2.1. Summary for Yellow Fever campaign support. Please give a summary of the cMYP and/or the Yellow Fever, 10 dose(s) per vial, LYOPHILISED campaign introduction plan sections that refer to the introduction of Yellow Fever, 10 dose(s) per vial, LYOPHILISED campaign. Outline the key points that informed the decision-making process (data considered etc):. Nigeria is one of the YF endemic countries and lies approximately between latitudes 14°and 4°N of the equator. It is bordered beginning from the west by Benin, Nigerto the North, and Chad in the North East, Cameroon to the East and EquatorialGuinea and Atlantic Ocean to the South. Often referred to as Africa’s mostpopulous country, her 2013 population as projected from the national census of2006 is about 174.5 million using a growth rate of 3%. Presently, Nigeria is made up of 36 statesand a Federal Capital Territory with 774 constitutionally recognised localgovernment areas. Nigeria has a huge population at risk of Yellow Feverin the African continent with many of its residents living in dense, urbanareas. The risk assessment conducted in 2008, as part of the YF InvestmentCase, identified 104 million people to be at risk of YF (unpublished report). Of additional concern, in 1987, Nigeria was affectedby one of the largest YF epidemics in the last 35 years, with the estimatednumber of cases being greater than 116,000 with 24,000 deaths (5). The recentemergence of YF activity in neighbouring or nearby countries including Cameroonwith outbreaks in 2011 from six districts (Guider, Bibemi, Gaschiga, Lagdo, MayOulo and Golombe) is a call for concern. The 2008, assessment of Yellow Fever burden visited 19states with reported cases (Anambra, Bauchi, Benue, Borno, Cross River, Delta,Ekiti, Enugu, Imo, Kaduna, Kano, Katsina, Lagos, Niger, Ogun, Ondo, Osun, Oyo,Plateau, and Sokoto) and Arboviruslaboratories at Lagos, Ibadan and Enugu. Five data collectors were assigned tovisit the selected states in order to gather the following information for eachLocal Government Area (LGA): Annual number ofconfirmed Yellow Fever cases between 1960 and 2007 Annual number ofsuspected Yellow Fever cases between 1960 and 2007 Number ofchildren vaccinated against YF through EPI Number of personsvaccinated against YF during preventive campaigns Population datafor the ten largest cities in the state Avulnerability profile was constructed looking at exposure and susceptibility. Thesummary of cases from the survey is as shown in figure 4 below. In comparison with existing reports on YellowFever, the survey identified Yellow Fever cases reported in the states in morerecent years, but failed to retrieve information dating back to the largeepidemic in 1980s to 1990s. A large number of LGAs affected by previous and recent outbreaks were identified. However, considerable differences between the existing data (state level) and the data collected (LGA level) suggested that the survey had failed to identify several cases. Reasons for the discrepancies include poor record keeping, changes in administrative divisions, and exclusion of states previously reporting large Yellow Fever outbreaks. Conversely, the survey identified several cases/outbreaks that had not previously been notified to the Federal Ministry of Health. Yellow Fever outbreak investigations are rare and access to laboratory diagnosis was poor. Information on earlier outbreaks was mostly retrieved from published papers. A risk assessment conducted in 2008, as part of the YF Investment Case, identified 104 million people to be at risk of YF (unpublished report). This population is spread across 506 LGAs as shown in the map below. Vaccinating the 104 million at risk individuals in Nigeria would consume almost the entire available YF vaccine for preventive campaigns for the next eight years. Instead of focusing on selected LGAs, vaccination of an entire State is believed to be beneficial since intra-state differences do not reflect a significant difference in terms of risk of exposure to the disease. The Yellow Fever campaign plan will cover more than four year period, but the use of GAVI support is proposed for the first 4 years in a phased approach. Ideally and eventually, 100% of States in the country should be covered. For States to be covered in the 5th year and after, an alternative financing will be sourced. States were selected on priority basis using ranking of 1-5 (corresponding to risk ranking of 1 to 5):vulnerability, proportion of high risk LGAs in the State, State bordering Cameroun, other competing priorities (like polio campaigns), any possible impediment to conduct YF campaign, urban component, routine YF coverage, cold chain capacity, political acceptability. In prioritizing States for the 1st phase of the campaign in 2013, States in the North Central Zone and South South Zone that share border with Cameroun (Benue, Plateau, Nasarawa, Cross River and Akwa Ibom) are proposed. The target population (9months to 45 years) in those five States is 17, 022,913. The second phase in 2014 will target other five states in the South and NE zones along the Cameroun border. These states (Imo, Anambra, Delta, Adamawa and Taraba) have target population of 19,264,088. The third phase in 2015 will include another five States along NE and NW part of the country with a target population of 22,473,454. These are Kaduna, Bauchi, Borno, Gombe and Yobe. The fourth phase 2016 will include three States in SW zone (Osun, Oyo and Ogun) with a target population of 15,188,278. After the completion of the phased plans for 2013-2016, the two most populous States in the country (Lagos and Kano) with a target population of 22,495,382 and the remaining other States are considered in another plan. Please summarise (1) the waste management plan and (2) the cold chain capacity and readiness to accommodate new vaccines, stating how the cold chain expansion (if required) will be financed, and when it will be in place.Please indicate if the supplies for the campaign will have any impact in the shipment plans for your routine vaccines and how it will be handled:. 1) The Waste Management plan Nigeria has made significant gains recently with a health care waste management policy that has been developed and approved by the National Assembly. The ICC at its recent meeting of 16th August 2012 gave approval for incineration of campaign wastes and 17units of 100kg capacity incinerators are already underway to MenAfriVac implementing states based on 1:1, 000,000 vaccinations given. This practice will be applied to the YF campaign. The YF preventive vaccination campaign will provide an additional platform for the entrenchment of appropriate waste management practices in the system. 2) The Cold Chain capacity and readiness to accomodate new vaccines At the national level there is the NSCS and 6 zonal cold stores which provide a combined storage volume of 373, 750 liters. Yellow Fever vaccines can be stored under-positive and negative storage volume. However, this analysis concentrates on the positive storage that will be effectively available to store the vaccine since the negative storage will be utilized for freezing ice packs. From the table below, it seems all states for this campaign are in deficit of effective storage volume to store the vaccines along with the other vaccines in the immunization schedule which includes new vaccines of Pentavalent and Pneumococcal conjugate vaccines. This is so because the analysis looked at only presently available functional capacity. Majority of states have cold rooms procured and awaiting installation (Adamawa, Benue, Imo). Some have cold rooms that require repairs (Bauchi -2, Plateau – 1, Yobe -2, Lagos -1, Oyo – 1, Ogun -1 requires re-location only). These have been planned for October 2012 and will be available before the March 2013 scheduled date of Phase 1 campaign. Plans have reached advanced stages to procure cold rooms for Kano, Nasarawa and Delta states. Each cold room will add a positive storage space of 6, 250L. Serious efforts are underway to expand cold chain facilities across the country at all levels. The Federal Government is injecting some $2m and substantial funds have been mobilized from EU- SIGN, JICA and UNICEF. Other funding support is expected from GAVI HSS re-programming. Nasarawa which is implementing by March 2013 will be fast tracked in getting a cold room installed. Table 4: Storage volume for YF campaign vaccines StateTarget population YF doses required (WR@5%)YF Volume (Litres) Req'd (2.5cm3/dose)Storage Volume in Liters for other vaccines(RI+NVI=62.5cm3)Total Available Positive Functional Storage Volume (Liters) Gap (Liters)Akwa Ibom426040944845071121123856720-6786Cross River3034929319456679988227114-2507Benue44626594697395117412973900-13247Plateau329414634674188679576387-10056Nasarawa197077020744335195729945-5303Imo43538114582821114612656774-13028Anambra448570547216531180130408497-5723Delta45347094773235119313182562-13814Adamawa342468436048229019955882-9975Taraba2465178259484664971666961-854Kaduna6807319716538417911978913364-8216Bauchi543376757195831430157967107-10119Gombe2687818282919770778137049-1472Yobe272111728642487167910648-7978Borno4823433507714612691402210145-5146Osun403431842465231062117286961-5828Oyo671798570713511768195297330-13967Ogun443597446693061167128951334-12729Lagos 109615061153808128853186518556-16193Kano11533876121405583035335297609-28955Total9644411310151707325379280361113845-191895KEY Phase 1 (2013) Phase 4 (2016) Phase 2 (2014) Phase 5 (2017) Phase 3 (2015) Other measures that will be put in place include: 1. Adjust RI vaccines shipments to accommodate the YF vaccines expected for the campaign in line with the timelines for the campaign implementation. 2. Use of the zonal and adjoining state cold stores as transit points for the YF vaccines to the states 3. Store lyophilized vaccines (including the YF) at negative temperatures 4. Deploy national level logisticians to support the state and LGA level planning for vaccine storage and distribution It is also pertinent to add here that lessons learnt from the MenAfriVac campaigns will be used in developing a robust cold chain and logistics plan for the YF campaigns which include within State tactical and cyclical distributions. Logistics micro-planning will be conducted in each state and LGA well in advance of the campaign, such that there is minimal impact on the supply of routine vaccines. The government does not anticipate any challenges for the RI program due to the YF campaign, particularly as the campaign will be condensed over a brief 10-day period. In the distribution system, there are four cold vans at the national strategic cold store used for distributing vaccines as soon as they arrive to the various states. Quite often, private transporters are engaged with security escort to ferry vaccines also for which a standing budget exists and these funds come directly from the National Primary Health Care Development Agency. In terms of clearance of the vaccines, a standing waiver which is annually renewed exists that facilitates easy clearance of vaccines within 24hrs of arrival. The waiver for 2012 is being processed... 7.2.2. Grant Support for Operational Costs of the Yellow Fever Campaign.. Please indicate in the tables below how the support Grant [1] will be used to support the operational costs of the campaign and other critical pre-introduction activities. GAVI's support may not be enough to cover the full needs so please indicate in the table below how much and who will be complementing the funds needed (refer to the cMYP and the Yellow Fever, 10 dose(s) per vial, LYOPHILISED campaign introduction plan)... Table 7.2.2: calculation of grant to support the operational costs of the campaigns.. Year of Yellow Fever support; Target population vaccinated (from Table 5.3); Share per population 1-29 years old in US$; Total in US$. 2013; 17,022,913; 0.65; 11,064,893. 2014; 19,264,088; 0.65; 12,521,657. 2015; 22,473,454; 0.65; 14,607,745.. [1] The Grant will be based on a maximum award of $0.65$ per cohort population.. Cost (and finance) of the Yellow Fever, 10 dose(s) per vial, LYOPHILISED campaign US$.. Cost Category Full needs for new vaccine introduction in US$; Funded with GAVI introduction grant in US$. 2013; 2013. Training; 0. Social Mobilization, IEC and advocacy; 0. Cold Chain Equipment & Maintenance; 0. Vehicles and Transportation; 0. Programme Management; 0. Surveillance and Monitoring; 0. Human Resources; 0. Waste Management; 0. Technical Assistance; 0. Planning; 0. Volunteer incentives; 0. Other (please specify). Total; 0; 0... Cost Category Full needs for new vaccine introduction in US$; Funded with GAVI introduction grant in US$. 2014; 2014. Training; 0; 0. Social Mobilization, IEC and advocacy; 0; 0. Cold Chain Equipment & Maintenance; 0; 0. Vehicles and Transportation; 0; 0. Programme Management; 0; 0. Surveillance and Monitoring; 0; 0. Human Resources; 0; 0. Waste Management; 0; 0. Technical Assistance; 0; 0. Planning; 0; 0. Volunteer incentives; 0; 0. Other (please specify). Total; 0; 0... Cost Category Full needs for new vaccine introduction in US$; Funded with GAVI introduction grant in US$. 2015; 2015. Training; 0; 0. Social Mobilization, IEC and advocacy; 0; 0. Cold Chain Equipment & Maintenance; 0; 0. Vehicles and Transportation; 0; 0. Programme Management; 0; 0. Surveillance and Monitoring; 0; 0. Human Resources; 0; 0. Waste Management; 0; 0. Technical Assistance; 0; 0. Planning; 0; 0. Volunteer incentives; 0; 0. Other (please specify). Total; 0; 0..... Please describe others sources of funding if available to cover your full needs...

8. Procurement and Management.

8.1. Procurement and Management of New and Under-Used Vaccines Routine.

No NVS Routine Support is requested.

8.2. Procurement and Management for NVS Preventive Campaign(s).

8.2.1. Procurement and Management for Yellow Fever, 10 dose(s) per vial, LYOPHILISED campaign. a) Please show how the support will operate and be managed including procurement of vaccines (GAVI expects that countries will procure vaccine and injection supplies through UNICEF):. The Government of Nigeria has an MOU with UNICEF for the procuring of her routine immunization vaccines and this will be used for the procurment yellow fever vaccine.. b) Please indicate when you are planning to conduct the campaign (month and year) and how the campaign is going to be rolled out (e.g. in different phases or one time).. The preventive campaign is planned from 2013 to 2016 and it is going to be a phased campaign In the 1st phase of the campaign in 2013, States in the North Central Zone and South South Zone that share border with Cameroun (Benue, Plateau, Nasarawa, Cross River and Akwa Ibom) are proposed. The target population (9months to 45 years) in those five States is 17, 022,913 million. The second phase in 2014 will target other five states in the South and North East zones along the Cameroun border. These states (Imo, Anambra, Delta, Adamawa and Taraba) have target population of 19,264,088 million (9months to 45 years). The third phase in 2015 will include another five States along North East and North West part of the country with a target population of 22,473,454 million (9months to 45 years). These are Kaduna, Bauchi, Borno, Gombe and Yobe. The fourth phase 2016 will include three States in the South West zone (Osun, Oyo and Ogun) with a target population of 15,188,278 million (9months to 45 years). After the completion of the phased plans for 2013-2016, the two most populous States in the country (Lagos and Kano) with a target population of 22,495,382 million and the remaining other States (target million) are considered in another plan.. c) Please outline how coverage of the new vaccine will be monitored and reported (refer to the cMYP and/or the Yellow Fever, 10 dose(s) per vial, LYOPHILISED campaign introduction plan). The tools to be used to evaluate pre campaign implementation, implementation of the campaign and post implementation are as follows: 1) Pre-implementation data tool: pre-implementation checklist, micro-planning verification checklist, training checklist and proposal for KAP survey in the implementing population for baseline information. 2) Implementation tools: tally sheet by age and location, vaccination cards, daily summary sheets, supervisory checklists, inside and outside-household monitoring checklist 3) Post-implementation data tools: these are for independent monitoring which is in line with the monitoring for post MenAfriVac, polio and measles campaign. Also, coverage survey will be conducted within four weeks of the conclusion of the campaign. To facilitate the evaluation, vaccination cards will be distributed for those that receive the YF vaccination. The methodologies used to evaluate the MenAfriVac campaign will be adapted for YF campaign coverage surveys. In addition, a specific effort will be put on pharmaco-vigilance activities in order to monitor AEFI in Nigeria following the introduction of the vaccine. AEFI case investigation forms would be completed for every case and treatmens kits stationed at all vaccination sites. Surveillance will be intensified in sentinel referral/ teaching hosptials in state captials with case based abd bateriology information..

8.3. Vaccine Management (EVSM/EVM/VMA).

Did the country have Effective Vaccine Management Assessment (VMA) in the past? Yes. When was the last VMA conducted? December 2010. Did the country have Effective Vaccine Store Management (EVSM) in the past? Yes. When was the last EVSM conducted? December 2010. Did the country have Effective Vaccine Management (EVM) in the past? Yes. When was the EVM conducted? December 2010. If your country conducted either EVSM or VMA in the past two years, please attach relevant reports. (Document N°13). A VMA report must be attached from those countries which have introduced a New and Underused Vaccine with GAVI support before 2008.. Please note that Effective Vaccine Store Management (EVSM) and Vaccine Management Assessment(VMA) tools have been replaced by an integrated Effective Vaccine Management (EVM) tool. The information on EVM tool can be found at http://www.who.int/immunization_delivery/systems_policy/logistics/en/index6.html. For countries which conducted EVSM, VMA or EVM in the past, please report on activities carried out as part of either action plan or improvement plan prepared after the EVSM/VMA/EVM.. Following the EVM assessment a vaccine management improvement plan has been articulated and actualised and it includes the following: - Consultative meeting between NLWG, DFA, Director Human Resources, Director Admin & Supplies and Zonal Coordinators on immediate implementation of the approved Concept Note on operationalization of the zonal cold stores. - Completion of the construction work on the North West zonal cold store and ongoing expansion work on other zonal stores • Regualr supervision and assessment of quality of work • Test running of all installed equipments including temperature monitoring devices • Revision of SOPs and re-orient staff - Expansion of the existing contractual agreements for planned preventive as well as break-down maintenance to all zonal stores and follow up on implementation of the maintenance works. - Review of the human resources needs for each store against expected workload, identification of gaps and re-deployment or recruitment where necessary. - Conducting training needs assessment and follow up with appropriate capacity building (supply chain management, maintenance, information management systems etc. - Improving power by allocating special lines to stores, - Additional dry storage for national stores will come on board by 2013 to address gaps The greatest challenge exists in vaccine supply chain management at the LGA-health facility level i.e. between the 774 LGAs and 25,000 public health facilities providing conducting routine immunization. The LGA stores serve as vaccine depots for the health facilities and in most cases, double as storage facility for returned vaccine where the MDVP is applied. The pull system of vaccine distribution/collection is commonly used at this level but some LGAs combine the push and pull systems depending on the proximity of the HFs to the LGA cold store. Key issues at this level include the replacement of passive cold chain equipment (cold boxes and geostyle) that no longer meet WHO Standards. Permanent reliable means of transportation and communication are grossly inadequate/mostly absent with personal phones being widely used as a means to perform official functions. To improve the vaccine distribution between these two levels, the following activities are planned: - Provision of standard cold storage equipment as in solar refrigerators. While this will require heavy investment interms of procurement of cold chain equipment, maintenance and training of the users, it will minimize wastage as the MDVP will be applied easily and missed opportunities will be reduced leading to high coverage. - Renovation of buildings and provision of transport. In this regard, resources from NPHCDA, GAVI HSS, MDGs and Partners are gradually being invested. The investments are also heavy and require time. - Provision of standard generator set with adequate fuel tank capacity. Funding would also be provided for running and maintenance. - Stock recording is a prerequisite for adequate vaccine security. Standardised stock recording templates in the form of ledgers, issue/receipt vouchers and bin cards would be introduced for recording stock movements. These will be printed and distributed to all levels. - Training of lower level cold chain officers using the MLM training format on the proper management of vaccines, cold chain and stocks management. - Provision of computerized for stock management system at the LGA level - Standardization of building plans for LGA cold stores and HFs to adopt and advocacy for provision of communication facilities or the means of communication (e.g. stipends for recharge cards) to facilitate communication. Does the country plan to conduct an Effective Vaccine Management (EVM) Assessment in the future? Yes. When is the next Effective Vaccine Management (EVM) Assessment planned? January 2013. Under new guidelines, it will be mandatory for the countries to conduct an EVM prior to an application for introduction of new vaccine..

9. Additional Comments and Recommendations from the National Coordinating Body (ICC/HSCC).

Comments and Recommendations from the National Coordinating Body (ICC/HSCC).

10. Attachments.

10.1. List of documents attached to this proposal.

Document Number; Document; Section; Mandatory; File. In lieu doc.docx. 1; MoH Signature (or delegated authority) of Proposal; File desc:. Date/time: 9/2/2012 5:49:31 PM. Size: 26357. In lieu doc.docx. 2; MoF Signature (or delegated authority) of Proposal; File desc:. Date/time: 9/2/2012 5:49:31 PM. Size: 26357. In lieu doc.docx. 3; Signatures of ICC or HSCC or equivalent in Proposal; File desc:. Date/time: 9/2/2012 5:49:31 PM. Size: 26357. Scanned minutes of the 3rd ICC meeting - 16th august 2012.pdf. 4; Minutes of ICC/HSCC meeting endorsing Proposal; File desc:. Date/time: 8/31/2012 12:09:38 PM. Size: 6165577. cMYP 2011-2015 country final.pdf. 5; comprehensive Multi Year Plan - cMYP; File desc:. Date/time: 8/31/2012 11:32:30 AM. Size: 5821464. Nigeria cMYP 2011_ 2015 Costing_Tool Revised 050511.xlsx. 6; cMYP Costing tool for financial analysis; File desc:. Date/time: 8/31/2012 11:47:16 AM. Size: 1606988. Introduction plan for YF preventive campaigns Nigeria 2012 FINAL.docx. 7; Plan for NVS introduction (if not part of cMYP); 5.1; File desc:. Date/time: 8/31/2012 2:05:29 PM. Size: 1707387. Copy of EVM Improvement plan 15082012.xlsx. 8; Improvement plan based on EVM; File desc:. Date/time: 8/31/2012 11:47:16 AM. Size: 97975.

11. Annexes.

Annex 1 - NVS Routine Support.

No NVS Routine Support is requested.

Annex 2 - NVS Routine – Preferred Second Presentation.

No NVS Routine – Preferred Second Presentation requested this year.

Annex 3 - NVS Preventive campaign(s)... Annex 3.1 - NVS Preventive campaign(s) (Yellow Fever, 10 dose(s) per vial, LYOPHILISED). Table Annex 3.1 C: Summary table for CAMPAIGN Yellow Fever, 10 dose(s) per vial, LYOPHILISED.. Data from; 2013; 2014; 2015. Total campaign population; Table 5.3.1; #; 122,109,695; 126,034,526; 130,092,967. Immunization coverage; Table 5.3.1; %; 14.00 %; 15.00 %; 17.00 %. Number of persons to be vaccinated; Table 5.3.1; #; 17,022,913; 19,264,088; 22,473,454. Number of doses per persons; Parameter; #; 1; 1; 1. Estimated vaccine wastage factor; Table 5.3.1; #; 1.05; 1.05; 1.05. Number of doses per vial; Parameter; #; 10; 10; 10. AD syringes required; Parameter; #; Yes; Yes; Yes. Reconstitution syringes required; Parameter; #; Yes; Yes; Yes. Safety boxes required; Parameter; #; Yes; Yes; Yes. Vaccine price per dose; Table Annexes 4A; $; 0.9; 0.9; 0.9. AD syringe price per unit; Table Annexes 4A; $; 0.0465; 0.0465; 0.0465. Reconstitution syringe price per unit; Table Annexes 4A; $; 0.0037; 0.0037; 0.0037. Safety box price per unit; Table Annexes 4A; $; 0.0058; 0.0058; 0.0058. Freight cost as % of vaccines value; Table Annexes 4B; %; 8.00 %; 8.00 %; 8.00 %. Freight cost as % of devices value; Parameter; %; 0; 0; 0...

Table Annex 3.1 D: Estimated number of Yellow Fever, 10 dose(s) per vial, LYOPHILISED associated injection safety material and related co-financing budget (page 1). Formula; GAVI. 2013; 2014; 2015. B; Number of persons to be vaccinated with the first dose; 17,022,913; 19,264,088; 22,473,454. C; Number of doses per persons; 1; 1; 1. D; Number of doses needed; B x C; 17,022,913; 19,264,088; 22,473,454. E; Estimated vaccine wastage factor; Wastage factor table; 1.05; 1.05; 1.05. F; Number of doses needed including wastage; D x E; 17,874,059; 20,227,293; 23,597,127. G; Vaccines buffer stock; (F – F of previous year) * 0.25; 4,468,515; 588,309; 842,459. I; Total vaccine doses needed; F + G; 22,342,574; 20,815,602; 24,439,586. J; Number of doses per vial; Vaccine parameter; 10; 10; 10. K; Number of AD syringes (+ 10% wastage) needed; (D + G) x 1.11; 23,855,486; 22,036,161; 25,880,664. L; Reconstitution syringes (+ 10% wastage) needed; I / J * 1.11; 2,480,026; 2,310,532; 2,712,795. M; Total of safety boxes (+ 10% of extra need) needed; (K + L) /100 * 1.11; 292,325; 270,249; 317,388. N; Cost of vaccines needed; I x g; 0.9; 0.9; 0.9. O; Cost of AD syringes needed; K x ca; 1,109,280.099; 1,024,681.4865; 1,203,450.876. P; Cost of reconstitution syringes needed; L x cr; 9,177; 8,549; 10,038. Q; Cost of safety boxes needed; M x cs; 1,696; 1,568; 1,841. R; Freight cost for vaccines needed; N x fv; 0; 0; 0. S; Freight cost for devices needed; (O+P+Q) x fd; 0; 0; 0. T; Total fund needed; (N+O+P+Q+R+S); 21,228,470.099; 19,768,840.4865; 23,210,957.876... Note: There is no cofinancing for NVS preventive campaigns...

| Annex 4. |  |  |
| --- | --- | --- |
| Table Annex 4A: Commodities Cost. |  |  |
| Vaccine; Presentation; 2013; 2014; 2015; 2016. DTP-HepB, 10 dose(s) per vial, LIQUID; 10. DTP-HepB-Hib, 1 dose(s) per vial, LIQUID; 1; 2.017; 1.986; 1.933; 1.927. DTP-HepB-Hib, 10 dose(s) per vial, LIQUID; 10; 2.017; 1.986; 1.933; 1.927. DTP-HepB-Hib, 2 dose(s) per vial, LYOPHILISED; 2; 2.017; 1.986; 1.933; 1.927. HPV bivalent, 2 dose(s) per vial, LIQUID; 2; 5.000; 5.000; 5.000; 5.000. HPV quadrivalent, 1 dose(s) per vial, LIQUID; 1; 5.000; 5.000; 5.000; 5.000. Measles, 10 dose(s) per vial, LYOPHILISED; 10; 0.242; 0.242; 0.242; 0.242. Meningogoccal, 10 dose(s) per vial, LIQUID; 10; 0.520; 0.520; 0.520; 0.520. MR, 10 dose(s) per vial, LYOPHILISED; 10; 0.494; 0.494; 0.494; 0.494. Pneumococcal (PCV10), 2 dose(s) per vial, LIQUID; 2; 3.500; 3.500; 3.500; 3.500. Pneumococcal (PCV13), 1 dose(s) per vial, LIQUID; 1; 3.500; 3.500; 3.500; 3.500. Rotavirus, 2-dose schedule; 1; 2.550; 2.550; 2.550; 2.550. Rotavirus, 3-dose schedule; 1; 3.500; 3.500; 3.500; 3.500. Yellow Fever, 10 dose(s) per vial, LYOPHILISED; 10; 0.900; 0.900; 0.900; 0.900. Yellow Fever, 5 dose(s) per vial, LYOPHILISED; 5; 0.900; 0.900; 0.900; 0.900. |  |  |
| Note for HPV and MR: These prices are indicative only as GAVI has not procured HPV and MR vaccines for GAVI countries yet. Prices will be finalised through tender processes in Q3. GAVI will only fund HPV vaccines if an acceptable price reduction is secured from the current price indicated. The MR price is based on the current price to UNICEF. |  |  |
| Supply; Form; 2013; 2014; 2015; 2016. AD-SYRINGE; SYRINGE; 0.047; 0.047; 0.047; 0.047. RECONSTIT-SYRINGE-PENTAVAL; SYRINGE; 0.047; 0.047; 0.047; 0.047. RECONSTIT-SYRINGE-YF; SYRINGE; 0.004; 0.004; 0.004; 0.004. SAFETY-BOX; SAFETYBOX; 0.006; 0.006; 0.006; 0.006. |  |  |
| Note: WAP - weighted average price (to be used for any presentation: For DTP-HepB-Hib, it applies to 1 dose liquid, 2 dose lyophilised and 10 dose liquid. For Yellow Fever, it applies to 5 dose lyophilised and 10 dose lyophilised). |  |  |
| Table Annex 4B: Freight cost as percentage of value. |  |  |
| Vaccine Antigen; Vaccine Type; No Threshold; 500,000$. <=; >. DTP-HepB; HEPBHIB; 2.00 %. DTP-HepB-Hib; HEPBHIB; 23.80 %; 6.00 %. HPV bivalent; HPV; 3.50 %. HPV quadrivalent; HPV; 3.50 %. Measles; MEASLES; 14.00 %. Meningogoccal; MENINACONJUGATE; 10.20 %. MR; MR; 13.20 %. Pneumococcal (PCV10); PNEUMO; 3.00 %. Pneumococcal (PCV13); PNEUMO; 6.00 %. Rotavirus; ROTA; 5.00 %. Yellow Fever; YF; 7.80 %. |  |  |
| Table Annex 4C: Intermediate - Minimum country's co-payment per dose of co-financed vaccine.. |  |  |
| Vaccine. |  |  |
| Table Annex 4D: Wastage rates and factors. |  |  |
| Countries are expected to plan for a maximal wastage rate of:. |  |  |
| • 50% - for a lyophilised vaccine in 10 or 20-dose vial,. |  |  |
| • 25% - for a liquid vaccine in 10 or 20-dose vial or a lyophilised vaccine in 5-dose vial,. |  |  |
| • 10% - for a lyophilised/liquid vaccine in 2-dose vial, and. |  |  |
| • 5% - for a liquid vaccine in 1-dose vial. |  |  |
| Vaccine wastage rate; 5%; 10%; 15%; 20%; 25%; 30%; 35%; 40%; 45%; 50%; 55%; 60%. Equivalent wastage factor; 1.05; 1.11; 1.18; 1.25; 1.33; 1.43; 1.54; 1.67; 1.82; 2; 2.22; 2.5. |  |  |
| Vaccine; Vaccine wastage rate; VaccineWastageFactor. Yellow Fever, 10 dose(s) per vial, LYOPHILISED; 5%; 1.05. |  |  |
| Table Annex 4E: Vaccine maximum packed volumes. |  |  |
| Vaccine product; Designation; Vaccine formulation; Admin route; No. Of doses in the schedule; Presentation (doses/vial, prefilled); Packed volume vaccine (cm3/dose); Packed volume diluents (cm3/dose). BCG; BCG; lyophilized; ID; 1; 20; 1.2; 0.7. Diphtheria-Tetanus-Pertussis; DTP; liquid; IM; 3; 20; 2.5. Diphtheria-Tetanus-Pertussis; DTP; liquid; IM; 3; 10; 3. Diphtheria-Tetanus; DT; liquid; IM; 3; 10; 3. Tetanus-Diphtheria; Td; liquid; IM; 2; 10; 3. Tetanus Toxoid; TT; liquid; IM; 2; 10; 3. Tetanus Toxoid; TT; liquid; IM; 2; 20; 2.5. Tetanus Toxoid UniJect; TT; liquid; IM; 2; Uniject; 12. Measles; Measles; lyophilized; SC; 1; 1; 26.1; 20. Measles; Measles; lyophilized; SC; 1; 2; 13.1; 13.1. Measles; Measles; lyophilized; SC; 1; 5; 5.2; 7. Measles; Measles; lyophilized; SC; 1; 10; 3.5; 4. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 1; 26.1; 26.1. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 2; 13.1; 13.1. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 5; 5.2; 7. Measles-Rubella freeze dried; MR; lyophilized; SC; 1; 10; 2.5; 4. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 1; 26.1; 26.1. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 2; 13.1; 13.1. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 5; 5.2; 7. Measles-Mumps-Rubella freeze dried; MMR; lyophilized; SC; 1; 10; 3; 4. Polio; OPV; liquid; Oral; 4; 10; 2. Polio; OPV; liquid; Oral; 4; 20; 1. Yellow fever; YF; lyophilized; SC; 1; 5; 6.5; 7. Yellow fever; YF; lyophilized; SC; 1; 10; 2.5; 3. Yellow fever; YF; lyophilized; SC; 1; 20; 1.5; 2. Yellow fever; YF; lyophilized; SC; 1; 50; 0.7; 1. DTP-HepB combined; DTP-HepB; liquid; IM; 3; 1; 9.7. DTP-HepB combined; DTP-HepB; liquid; IM; 3; 2; 6. DTP-HepB combined; DTP-HepB; liquid; IM; 3; 10; 3. Hepatitis B; HepB; liquid; IM; 3; 1; 18. Hepatitis B; HepB; liquid; IM; 3; 2; 13. Hepatitis B; HepB; liquid; IM; 3; 6; 4.5. Hepatitis B; HepB; liquid; IM; 3; 10; 4. Hepatitis B UniJect; HepB; liquid; IM; 3; Uniject; 12. Hib liquid; Hib_liq; liquid; IM; 3; 1; 15. Hib liquid; Hib_liq; liquid; IM; 3; 10; 2.5. Hib freeze-dried; Hib_lyo; lyophilized; IM; 3; 1; 13; 35. Hib freeze-dried; Hib_lyo; lyophilized; IM; 3; 2; 6. Hib freeze-dried; Hib_lyo; lyophilized; IM; 3; 10; 2.5; 3. DTP liquid + Hib freeze-dried; DTP+Hib; liquid+lyop.; IM; 3; 1; 45. DTP-Hib combined liquid; DTP+Hib; liquid+lyop.; IM; 3; 10; 12. DTP-Hib combined liquid; DTP-Hib; liquid; IM; 3; 1; 32.3. DTP-HepB liquid + Hib freeze-dried; DTP-Hib; liquid; IM; 3; 10; 2.5. DTP-HepB liquid + Hib freeze-dried; DTP-HepB+Hib; liquid+lyop.; IM; 3; 1; 22. DTP-HepB-Hib liquid; DTP-HepB+Hib; liquid+lyop.; IM; 3; 2; 11. DTP-HepB-Hib liquid; DTP-HepB-Hib; liquid; IM; 3; 10; 4.4. DTP-HepB-Hib liquid; DTP-HepB-Hib; liquid; IM; 3; 2; 13.1. DTP-HepB-Hib liquid; DTP-HepB-Hib; liquid; IM; 3; 1; 19.2. Meningitis A/C; MV_A/C; lyophilized; SC; 1; 10; 2.5; 4. Meningitis A/C; MV_A/C; lyophilized; SC; 1; 50; 1.5; 3. Meningococcal A/C/W/; MV_A/C/W; lyophilized; SC; 1; 50; 1.5; 3. Meningococcal A/C/W/Y; MV_A/C/W/Y; lyophilized; SC; 1; 10; 2.5; 4. Meningitis W135; MV_W135; lyophilized; SC; 1; 10; 2.5; 4. Meningitis A conjugate; Men_A; lyophilized; SC; 2; 10; 2.6; 4. Japanese Encephalitis; JE_lyo; lyophilized; SC; 3; 10; 15. Japanese Encephalitis; JE_lyo; lyophilized; SC; 3; 10; 8.1; 8.1. Japanese Encephalitis; JE_lyo; lyophilized; SC; 3; 5; 2.5; 2.9. Japanese Encephalitis; JE_lyo; lyophilized; SC; 3; 1; 12.6; 11.5. Japanese Encephalitis; JE_liq; liquid; SC; 3; 10; 3.4. Rota vaccine; Rota_lyo; lyophilized; Oral; 2; 1; 156. Rota vaccine; Rota_liq; liquid; Oral; 2; 1; 17.1. Rota vaccine; Rota_liq; liquid; Oral; 3; 1; 45.9. Pneumo. conjugate vaccine 7-valent; PCV-7; liquid; IM; 3; PFS; 55.9. Pneumo. conjugate vaccine 7-valent; PCV-7; liquid; IM; 3; 1; 21. Pneumo. conjugate vaccine 10-valent; PCV-10; liquid; IM; 3; 1; 11.5. Pneumo. conjugate vaccine 10-valent; PCV-10; liquid; IM; 3; 2; 4.8. Pneumo. conjugate vaccine 13-valent; PCV-13; liquid; IM; 3; 1; 12. Polio inactivated; IPV; liquid; IM; 3; PFS; 107.4. Polio inactivated; IPV; liquid; IM; 3; 10; 2.5. Polio inactivated; IPV; liquid; IM; 3; 1; 15.7. Human Papilomavirus vaccine; HPV; liquid; IM; 3; 1; 15. Human Papilomavirus vaccine; HPV; liquid; IM; 3; 2; 5.7. Monovalent OPV-1; mOPV1; liquid; Oral; 20; 1.5. Monovalent OPV-3; mOPV3; liquid; Oral; 20; 1.5. |  |  |

| 12. Banking Form |  |
| --- | --- |
| In accordance with the decision on financial support made by the GAVI Alliance, the Government of Nigeria hereby requests that a payment be made via electronic bank transfer as detailed below:. Name of Institution (Account Holder):. Address:. City Country:. Telephone no.:; Fax no.:. Currency of the bank account:. For credit to:. Bank account's title:. Bank account no.:. Bank's name:. |  |
| Is the bank account exclusively to be used by this program?. |  |
| By who is the account audited?. |  |
| Signature of Government's authorizing official. |  |
| Seal. Name:. Title:. Signature:. Date:. |  |
| FINANCIAL INSTITUTION. Bank Name:. Branch Name:. Address:. City Country:. Swift Code:. Sort Code:. ABA No.:. Telephone No.:. FAX No.:. | CORRESPONDENT BANK. (In the United States). |
| I certify that the account No is held by at this banking institution. The account is to be signed jointly by at least (number of signatories) of the following authorized signatories:. 1; Name:. Title:. 2; Name:. Title:. 3; Name:. Title:. |  |
| Name of bank's authorizing official. Signature:. Date:. Seal:. |  |